HELVETAS Swiss Intercooperation Bangladesh, TRAIDCRAFT, Dhaka Ahsania Mission, Bangladesh Agro Procesor’s Association (BAPA) and Jamalpur Chamber of Commerce and Industry Partnership

SHAMERTO: – Sustainable Skills and Employment in Small Scale Agro-Food Processing Projec

Terms of Reference: Business Competition Event

# Introduction:

| Project Name | SHAMERTO – Sustainable Skills and Employment in Small Scale Agro-Food Processing |
| --- | --- |
| Project Location | Bangladesh – Mymensingh, Sherpur, Jamalpur, Kurigran, Gaibanda, Shariatpur and Barisal districts |
| Project duration | 36 months from 1st February 2017 |
| Donors | Co-funded by EU |
| Implementing agency and partners | The project is led by Helvetas Swiss Intercooperation and co-implemented by Traidcraft Exchange (TX) Bangladesh Agro-Food Processors Association (BAPA) Dhaka Ahsania Misson (DAM) and District Chamber of Commerce and Industry (DCC) |

SHAMERTO project is being implemented to create an improved enabling environment for skills development, employment, decent work conditions and promotion of environmental standards in small, micro and cottage agro-food processing enterprises (SMCE) to achieve the goal, “to strengthen the skills, employability and income of workers and entrepreneurs in agro-food processing Small, Micro and Cottage Enterprises (SMCE) with focus on scaling-up value addition and increasing the competitiveness of these enterprises in the wheat, rice, groundnut, lentil, mung bean, spice and mustard value chains”. Specifically, it aims to increase gainful employment of workers and job seekers, who will be counselled, trained and skill-tested, and receive satisfactory job placement by enhancing the competitiveness and capacity for employment of the targeted SMCE through better integration in the selected sub-sector value chains and improvements in the business environment. The focus will be on scaling-up value addition and increasing competitiveness of SMCE in the wheat, rice, groundnut, lentil, mug bean, spice and mustard sub-sector value chains in 7 districts, in three geographic clusters in the North West (Kurigam, Gaibandha Districts / 11 Sub-districts), North East (Jamalpur, Sherpur, Mymensingh Districts / 14 Sub-districts) and South-West (Barisal, Shariatpur Districts / 11 sub-districts).

In Bangladesh most of the food processing units are small and rural based with very limited capacity to invest in technology. So, these small scale agro-food processors are engaged in low value adding manufacturing using unskilled and inefficient labour, outdated technology with little consideration for rules and regulations, compliance with decent work conditions, labour rights and norms, food safety standards and environmental regulations that limiting their business growth and employability.

The project plan to support the SMCEs to test on innovative use of products/ technologies/ practices.

# Purpose and Objectives:

Purpose:

The main purpose of this assignment is to develop a concept note, disseminate it to the SMCEs, collect and evaluate the proposals and scoring them.

Objectives:

The main objectives are:

- To develop a concept note including guidelines and template for participants of Business Plan Competition.

- To disseminate the concept to the SMCEs.

- To collect the proposals from the interested SMCES.

- To evaluate the proposals and to score them.

- To recommend the proposal for supporting.

- Geographical coverage

The project has been implementing in 7 districts, in three geographic clusters in the North West (Kurigam, Gaibandha Districts / 11 Sub-districts), North East (Jamalpur, Sherpur, Mymensingh Districts / 14 Sub-districts) and South-West (Barisal, Shariatpur Districts / 11 sub-districts).

- Methodology:

To meet the above-mentioned objectives, the consultant should follow the following process:

- A desk review/research of project information including the key documents like project proposal, log frame, other relevant resources.

- Research on innovative use of products/ technologies/ practices

- Develop a concept note on innovative use of products/ technologies/ practices

- Disseminate the concept note to the SMCEs and collect proposal from the SMCEs.

- Identification and selection of potential proposals and recommend for support.

- Submission of final report.

# Documents that we will provide

- As per need of the consultant (subject to the availability)

# Expected Deliverables

The main deliverables will be

- A concept note on Business Plan Competition

- Template for the participants of Business Plan Competition

- Guidelines for participants on how to complete the template and submit their applications

# Time table

There is a specific timeframe for the assignment and the consultant should need to work around the following time frame:

| Activity | Deadlines |
| --- | --- |
| Sending TOR to Consultants/ Agencies no later than | 16 August 2018 |
| Receipt of Proposals (EOI) | 27 August 2018 |
| Completion of contracting formalities | 2 September 2018 |
| Submission of draft Concept Note/Template | 10 September 2018 |
| Submission of Final Concept Note/Template | 16 September 2018 |
| Presentation/Workshop for SMCEs | 18 September 2018 |

# Application Process

Interested agency/firm/ individuals are requested to submit their Expression of Interest (EoI) electronically to the following address on or before 27  August 2018

To

Mohammed Ashraf Uddin

Apt. 1B, House # 11, Road # 13, Dhanmondi, Dhaka 1212

Please email to: TX_Bangladesh@traidcraft.org with copy to sonya.firoz@traidcraft.org

The EoI should include:

- Contact details

- Up to date and detailed CV of the consultant(s) with brief descriptions of similar assignments

- A clear overview of how this piece of work will be approached, the methodology proposed and the outputs generated, with a clear timeline for each of the specified activity and a budget apportioned for the assignment

- Two references

The EOI, excluding the consultant CVs, should not be more than -08 pages long, should have 1.15 spacing, and use Times New Roman typeface with a minimum font size of 12.

# Selection Criteria

On receipt of the EOI designated project management team will study the proposals and take the decision about the consultant/s/ agency for the study.  Selection of the consultant/s/ agency will be based on:

| Selection criteria | Scores |
| --- | --- |
| Proposed plan – well thought out, logical, strong methodology and approach, well-timed, level of details, would meet objectives | 10 |
| Relevant experiences | 15 |
| Knowledge/Experience on Value chain development and BDS, Agro-food processing sub-sector. | 05 |
| Scoring on CVs | 10 |
| Costs – value for the assignment | 10 |
| TOTAL | 50 |

# Mode of Payment

- Total fees for the assignment will be paid in three installments. The first installment (40% of the total fee) will be paid on signing the contract, 2nd installment (40% of the total fee) will be paid after the submission of business cases and the remaining amount (20%) will be paid upon acceptance of the final Report.

- The payment would be made in crossed cheque by the name of the organization/individual.

- Any VAT/TAX incurred from this assignment must be deducted at source as per government rule and policy.

General terms and conditions

- TX reserve the right to accept or reject any proposal without giving any verbal and/or written rationale;

- All reports and documents prepared during the assignment will be treated as TX property

- The reports/documents or any part, therefore, cannot be sold, used and reproduced in any manner without prior written approval of  TX

- TX or its representatives reserve the right to monitor the quality and progress of the work during the assignment.