# Terms of Reference (TOR)

# Development of Strategic Plan of AFAD

## 1. Background

AFAD (Association For Alternative Development) is a women-led non-profit organization (NGO) based in northern Bangladesh, actively working since 1999 to empower women and girls for a world of equal opportunities and full potential. AFAD is a dynamic force for positive change, championing gender equality and women's empowerment. The organization addresses a wide range of critical issues, including gender equality, education, economic empowerment, disaster risk reduction (DRR), climate change resilience, WASH, livelihood, and the localization of humanitarian aid. AFAD is registered with the NGO Affairs Bureau (NGOAB) of the Prime Minister's Office of the People's Republic of the Government of Bangladesh, with registration number 2443. It also obtained registration from the Directorate of Women's Affairs (DWA). Simultaneously, AFAD is registered with the Directorate of Youth Development, Government of Bangladesh.

With the support of Malteser International, AFAD has been implementing a localization project titled "ToGETHER! - Towards Greater Effectiveness and Timeliness in Humanitarian Emergency Response" in Bangladesh since 2021. The project aims to transcend organizational boundaries, enabling local and international partners to develop approaches to humanitarian responses and create synergies during crisis response collaboratively. It also supports local actors in enhancing their capabilities in humanitarian response, preparedness, coordination, and advocacy. Additionally, the program aims to create opportunities for establishing complementary partnerships and promoting the roles of local partners. Capacity-strengthening and exchange measures are based on LHPs' self-defined needs and priorities, as well as the broader humanitarian context within their countries and contexts. As part of the project's partner organizational capacity strengthening activities, AFAD is going to hire consultant/ Consultancy Firm to develop Strategic Plan in English.

## 2. Scope of Work

AFAD is going to develop its organizational strategic plan for the next ten years (2024-2034) which should be aligned with the organization's mission, vision, and values, and should comply with all applicable laws and regulations. Broaders scope of work are given below:

- Pre-discussion with Executive Committee members, AFAD staff members, and different-level stakeholders.

- Study and review AFAD's Vision, Mission, programs/projects, policies, resources, systems and approaches, various AFAD publications, Annual Reports, MIS reports, internal Audit Reports, different project reports and proposals, Project Agreements with Donors, EC meeting notes, and AGM meeting notes, etc.

- Conduct desk analysis SWOT analysis together with AFAD staff and the Management team.

- Interview different stakeholders (CBO leaders, community representatives, women leaders, government ministries, agencies, and departments engaged with AFAD, donor agencies) in the field and at the office level (as appropriate).

- Capture the direction, opinions, and observations of AFAD management.

- Develop Strategic Plan & organize a workshop with AFAD management, Board, and staff members for their final input within the draft.

Top of Form

Supports from AFAD

- AFAD will extend all necessary cooperation and support to the consultant for the proper execution of the assignment.

- AFAD will provide all necessary documents and information required by the consultant.

- AFAD will assign a focal person to liaise and coordinate with the consultant to accomplish the assigned task within the stipulated timeframe.

## 3.  Duration of the assignment

The contract period is from 20 January 2024 to 19 February 2024.(Maximum 30 days).

## 4.  Deliverables

- It is expected to prepare a Strategic Plan for  AFAD in English, not exceeding 50 pages (recommended but not limited to).

- An orientation will be conducted with the concerned staff of AFAD on how to implement the manual.

## 5. Qualification Experience of Consultant/Consultancy Firm

- At least master’s in social science or an relevant subject.  (For individual consultant)

- A minimum of 5 years of relevant work experience in developing strategic plans or relevant areas.

- Proficiency in English & Bengali, with a focus on presentation/reporting skills.

- Good communication and relationship-building skills.

- Strong analytical and communication skills.

## 6. Duration and Implementation Schedule

The total length of the concerned consultancy will not exceed 30 working days to be spread out from 15 January 2024 to 25 February 2023.

## 7. Terms of Payment

The payment will be made through the A/C Payee Cheque in favor of the contract holder. All expenditures during survey will be taken care of by the consultant/ firm. AFAD will deduct TAX and VAT according to Regulation of the Government of Bangladesh. The payment will be made according to the following schedule:

- 1st Payment: 40 % upon signing of the contract.

- Final Payment: 60 % upon the submission of final Strategic Plan including staff orientation, subject to its acceptance by AFAD.

AFAD will not settle any payment unless the consultancy institution accomplished all the tasks in a timely fashion.

## 8. Application Procedure

Interested candidates/ should submit their application material by 05:00 pm, January 19, 2024. Please mention “AFAD-Strategic Plan” in the email subject line.

Email: yesminafad@gmail.com ,muzahid.afad@gmail.com

Or drop the proposal by in-person / courier.

AFAD Head office, R.K Road Khalilganj Bazar, Kurigram

For further information, please contact to,

Name: Sayda Yesmin

Designation: Chief Executive, AFAD

Mobile: 01719691409

Email: yesminafad@gmail.com

The application itself should include the following components:

- Curriculum Vitae (CV) of Consultant/ Short description of Firm

- A technical proposal including proposed methodology and work plan.

- Financial proposal

The above areas might be re-arranged as follows: Interested applicants to send a technical and financial proposal for the work in line with the following guidance:

- Capability statement: How the consultant or firm is structured for the assignment, the role each member of staff will play including the CVs of the key personnel who will take part in the consultancy.

- Technical Proposal: The consultant’s understanding and interpretation of the Terms of Reference, a detailed methodology on how the data collection and analysis will be done and detailed implementation schedule for the baseline as well as any other proposed approaches the consultant may deem fit for this assessment.

- Financial proposal: Itemized budget proposal that should include the consultancy fees, operational costs, and all associated costs including VAT and tax. AFAD will select potential candidates and will invite them for an online interview after the application deadline.

## 9. Ethical Considerations and Data protection

Any data, information, documents, and other materials related to the work shall remain the property of

AFAD and shall be kept confidential by the Consultant/ Consultant Firm. The Consultant/ firm is not allowed to transfer or divulge any information to any other person or organization without prior approval of AFAD.

## 10. Contact Information

For inquiries or clarification, please contact:

Sayda Yesmin, Chief Executive, AFAD

Email: yesminafad@gmail.com

Mobile: 01719691409