## Results Framework
RESULTS FRAMEWORK | Prevention of and response to GBV and sexual violence to Rohingya refugee children and adolescents
Objective Hierarchy | Results Chain Goals, Outcomes and Outputs | Indicators NB: Two indicators link to specific indicators of the SDGs (marked in blue). Overall, the project will contribute to SDG 3, 4, 5 and 16. Many other indicators link to indicators of the JRP2019 and the draft JRP2020 for Child protection (as all NGOs responding to the Rohingya refugee crisis are urged to contribute to these plans) or to indicators of the global Educo Bangladesh Rohingya Refugee Response Program. | Source and mean of verification | Assumptions
Overall goal | To contribute to SDG 5 in order to achieve gender equality and create an environment that prevents, responds to and protects children and adolescents from various child protection violations, forms of gender-based violence and sexual violence while empowering communities, adolescents and children. | NA | NA | NA
Outcomes | Outcome 1: Adolescents - amongst them survivors, witnesses and/or victims of GBV and sexual violence - are able to prevent and respond to child protection issues, especially GBV and sexual violence, and access quality case management services | KNOWLEDGE AND SKILLS ++ % of adolescents (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence ++ % of adolescents (disaggregated by sex) with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services ATTITUDES ++ % of adolescents (disaggregated by sex) with positive change in attitudes towards early/child marriage ++ % of adolescent boys with positive change in attitudes towards the right to education for girls INCREASED SOCIAL CAPITAL ++ % of adolescents (disaggregated by sex) with increased connections to peers // to caring adults/role models SAFE ACCESS TO SERVICES ++ no of affected and/or at-risk adolescents (disaggregated by sex) referred to quality age and gender sensitive case management services, specifically to GBV and sexual violence case management services ++ % of adolescents reporting their club/group environment is safe to learn | Survey with adolescents (most likely administered by an interviewer) and FGDs KIIs with facilitators training/supporting the clubs and groups Physical observation of the meeting points of Adolescent Clubs and groups Confidential documentation of referrals done (informed by facilitators) -- no of referrals done and adolescents who got access to services | Proactive engagement with RRRC to obtain FD7. The security situation in the camps remains stable. The project promotes and ensures compliance with humanitarian principles. Awareness raising and continuous information of all stakeholders working to support Rohingya communities for a good understanding of the project. Continuous dialogue with the authorities.
| Outcome 2: Caregivers, formal and informal teachers as well as religious leaders and majhis are proactive in preventing and responding to child protection issues, especially to GBV and sexual violence, affecting children and adolescents | KNOWLEDGE ++ % of caregivers/teachers (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence ++ % of caregivers (diaggregated by sex) with improved knowledge about positive parenting ++ % of teachers (diaggregated by sex) with improved knowledge on positive discipline ++ % of teachers (diaggregated by sex) with improved knowledge on PSS (Psychological Support) and PFA (Psychological First Aid) ++ % of careigivers/ teachers (disaggregated by sex) with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services ATTITUDES ++ % of caregivers with positive change in attitudes towards early/child marriage ++ % of caregivers with positive change in attitudes towards positive parenting (e.g. corporal punishment, listening to the opinion my child) ++ % of teachers with positive change in attitudes towards corporal punishment and verbal abuse CODE OF CONDUCT ++ % of teachers of Learning Centers having signed the code of conduct --> INDICATOR LINKED TO SDG5: Whether or not legal frameworks are in place to promote, enforce and monitor equality and non-discrimination on the basis of sex (Indicator 5.1.1 ) ++ % of Learning Centers having put the code of conduct visible SAFE ACCESS TO CASE MANAGEMENT SERVICES ++ no of affected and/or at-risk adolescents (disaggregated by sex) referred to quality age and gender sensitive case management services by teachers of Learning Centers and of home-based learning | Survey with caregivers (most likely administered by an interviewer) and teachers and FGDs, KIIs KIIs with facilitators training/supporting the caregivers/teachers Physical observation of teaching sessions, of visible code of conduct Confidential documentation of referrals done (informed by teachers) -- no of referrals done
| Outcome 3: Community-based Child Protection Mechanisms (CBCPMs) work effectively at community and camp level to prevent and respond to child protection issues, especially to GBV and sexual violence, affecting children and adolescents | KNOWLEDGE AND SKILLS OF CBCPMs ++ % of CBCPM members (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence ++ % of members of CBCPM with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services ++ % of CBCPM with a documentation on the referral mechanism (e.g. images, flowcharts) SAFE ACCESS TO CASE MANAGEMENT SERVICES ++ no of affected and/or at-risk adolescents (disaggregated by sex) referred to quality age and gender sensitive case management services by CBCPMs FORUM OF DIFFERENT CHILD PROTECTION ACTORS ++ Key issues of the forum of representatives of different child protection actors running CBCPMs are reported regularly to Child Protection focal point | Survey with members of CBCPMs (most likely administered by an interviewer) and FGDs, KIIs KIIs with facilitators training/supporting the CBCPMs Physical observation of documentation on referral mechanism Confidential documentation of referrals done (informed by members of CBCPMs) -- no of referrals done MOM of meetings of the forum of representatives of different child protection actors running CBCPMs + Notes to Child Protection focal point
Outputs | Output 1.1: Adolescents were empowered with new knowledge and skills, and changed attitudes on child protection, GBV and sexual violence, SRHR, child and women's rights, child labor, child trafficking and gender as well as DRR | INDICATOR LINKED TO ALL OUTPUTS OF THE PROJECT AND TO SDG 4: ++ Participation rate/no of youth and adults in formal and non-formal education and training [in the previous 12 months], by sex (Indicator 4.3.1) ADOLESCENT CLUBS ++ no of adolescent clubs established ++ no of adolescents (disaggregated by sex) trained on child protection, GBV and sexual violence ADOLESCENT-LED ACTIVITIES ++ no of adolescent-led actions supported by the program on key child protection topics, including GBV and sexual violence-related, for members of their community ++ no of community members reached by adolescent-led actions on key child protection issues, including GBV and sexual violence related GIRLS-ONLY GROUPS ++ no of adolescent girls groups established ++ no of adolescent girls trained more in depth on GBV and sexual violence (early/child marriage, rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), SRHR and women's rights BOYS-ONLY GROUPS ++ no of adolescent boys groups established ++ no of adolescent boys trained more in depth on GBV and sexual violence (rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), gender (equitable gender roles, equitable and respectful relations/relationships, SRHR and consent, women's rights | Records hold on number of groups, their participants, attendance, training sessions and their topics, activities organized per club for the communities, peer-to-peer sessions held Photos, where appropriate | The security situation remains stable. Families/caregivers allow adolescents, especially girls, to attend club activities. Cultural barriers do not prevent adolescent girls from fully participating. Agreement is reached with other actors in the camps on shared areas - where needed. No damage or lost of meeting/teaching facilities due to natural disasters. Referral systems are functional and updated frequently.
| Output 2.1: Caregivers obtained new knowledge, changed practices and attitudes on child protection, GBV and sexual violence, on domestic violence, child development and parenting, on child and women's rights as well as gender | CAREGIVERS ++ no of caregivers (disaggregated by sex) trained on key child protection issues (e.g. early/child marriage), GBV and sexual violence, on child and women's rights, and gender ++ no of caregivers (disaggregated by sex) trained on child development and positive parenting leading to improved relationships with the children under their care | Records hold on number of training sessions and their topics, number of participating caregivers Photos, where appropriate | The security situation remains stable. Families/caregivers are open to listen to the project messages. Agreement is reached with other actors in the camps on shared areas - where needed. No damage or lost of meeting/teaching facilities due to natural disasters. Referral systems are functional and updated frequently.
| Output 2.2: Teachers enhanced knowledge and skills on child protection, GBV and sexual violence, on DRR, on child development, child and women's rights as well as gender and changed practices towards positive discipline; Madrasha teachers/religious leaders increased their awareness and knowledge on child protection, GBV and sexual violence, as well as positive discipline | TEACHERS OF LEARNING CENTERS AND HOME-BASED LEARNING ++ no of teachers (including some head teachers and line managers…) trained on child protection, GBV and sexual violence, on child development and positive discipline, on child and women's rights and gender ++ no of teachers (including some head teachers and line managers…) trained on PSS (Psychological Support) and PFA (Psychological First Aid) so that they are able to identify children at risk and refer them ++ no of LCMC members (Learning Center Management Committees) trained on child protection and PFA MADRASHA TEACHERS, RELIGIOUS LEADERS ++ no of religious leaders/madrasha teachers the program is in regular contact with ++ no of religious leaders/madrasha teachers trained on child protection, GBV and sexual violence ++ no of religious leaders/madrasha teachers trained on positive discipline | Records hold on number of training sessions and their topics, number of participating teachers, madrasha teachers, religious leaders and majhis Photos, where appropriate | The security situation remains stable. Agreement is reached with other actors in the camps on shared areas - where needed. No damage or lost of meeting/teaching facilities due to natural disasters. Motivated teachers are recruited. Reference systems are functional and updated frequently. Religious leaders and madrasha teachers are open to listen to the project messages. Referral systems are functional and updated frequently.
| Output 3.1: CBCPMs members, including majhis, increased their knowledge on child protection, GBV and sexual violence, on DRR, on domestic violence, child and women's rights as well as gender, and agreed on actions for child protection | ++ no of CBCPM establised ++ no of CBCPM trained on child protection, GBV and sexual violence, domestic violence, child and women's rights and gender ++ no of CBCPM active (meet regularly) ++ no of CBCPM with a viable/ relevant action plan including (GBV/sexual violence) risk mitigation actions | Records hold on number of CBCPMs, number of members, number of training sessions and their topics, on Meeting resolutions or MOM of CBCPMs, action plans Photos, where appropriate | The security situation remains stable. Agreement is reached with other actors in the camps on shared areas - where needed. Positive and cooperative environment within the community. CBCPMs members are committed to their tasks and responsibilities. Referral systems are functional and updated frequently.
| Output 3.2: Coordination and follow-up were improved with different actors, especially those that work on CBCPMs and provide referral services | ++ A forum of representatives of different child protection actors running CBCPMs is created ++ no of meetings/ experience sharing gatherings | Records hold on number of meetings organized, participants (organizations), MOM, on topics communicated to Child Protection Focal Point | Other actors share the need for more cooperation and sharing of learning and challenges.
| Intervention Logic Activities per Output | Means
Preparatory phase of the program | 0.1 COLLABORATION: Organize several meetings of the three implemenenting partners to work and agree on: - finer program management/coordination mechanism of all partners - detailed implementation and M&E plan between the three implementing partners - standards, templates and schedules with regards to reporting - shared documents, materials, tools (e.g. jointly to be developed/used curricula for different target groups, M&E tools including a simple and confidential tool to be used for referrals done) - TOR for baseline study - Training plan for local staff re curricula and M&E and code of conduct etc. | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), Email, telephone and/or personal communication, one staff to lead the discussions according to prior agreed agenda, attendance sheets, pictures
| 0.2 CURRICULA: Develop all age and gender appropriate curricula including engaging and participatory activities/excersices for the different target groups and topics (see 2.1, B of the narrative proposal re topics) | Time of national or international consultant, time of expert staff of the three implementing partners, time of Educo experts (County office, head office), Email, telephone and/or personal communication
| 0.3 TRAINING: Train staff of all implementing partners involved in training of target groups on all curricula (overview) for the different target groups (done by curriculum development expert) | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national or international consultant, Email, telephone and/or personal communication, attendance sheets, pictures
| 0.4 IEC MATERIAL: Develop simple ICE materials/images; culturally sensible and priorly tested re their appropriateness for the Adolescent Clubs and girls-only and boys-only groups | Venue, transport, stationery (pens, marker pens, notebooks, and related materials), time of experts from the three implementing partners, contribution of beneficiaries (above all adolescents, if possible), time of illustrators, Email, telephone and/or personal communication
| 0.5 TRAINING: Develop common to be used M&E tools (including a simple and confidential tool to be used for referrals done) and train staff of all implementing partners on M&E system, M&E plan, indicators, responsibilties and use of M&E tools | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), M&E tools, plan… time of expert staff of the three implementing partners, time of Educo experts (County office, head office), Email, telephone and/or personal communication, attendance sheets, pictures
| 0.6 START UP WORKSHOP: Organize and run 2-3 days start up workshop | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), time of facilitator and of staff of the three implementing partners, Email, telephone and/or personal communication, attendance sheets, pictures
| 0.7 BASELINE STUDY: Run baseline study in month 1 and 2 (Publish TOR, chose external research team or consultants, support baseline, discuss results…) | External research team or consultants (national or international), time of experts of the three implementing partners and of field mobilization staff, Email, telephone and/or personal communication, venue, transport, stationery (pens, marker pens, notebooks, and related materials)
| 0.8 MAPPING: Pre-identify and map existing case management providers in the camps where the project will intervene to ensure synergies and close collaboration when referring those in need (child survivors, witnesses and/or victims) to (GBV and sexual violence) case management services run by these competent service providers in the camps | Transport and time of designated staff of the three implementing partners for each camp, written mapping for each camp
| 0.9 FOLLOW-UP MAPPING: Throughout the project: Update mapping where necessary and make the results of the mapping visible and accessible to beneficiaries | Transport and time of designated staff of the three implementing partners for each camp, written regularly updated mapping for each camp
Output 1.1 | Output 1.1: Adolescents were empowered with new knowledge and skills, and changed attitudes on child protection, GBV and sexual violence, SRHR, child and women's rights, child labor, child trafficking and gender as well as DRR
| 1.1.1 Train staff on specific age and gender appropriate curriculum for the Clubs and allow for time for adaptations that still might be needed | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national expert staff of implementing partners, attendance sheets, pictures
| 1.1.2 Establish Adolescent Clubs 12 to <17 years old | Transport, time of facilitator(s)
| 1.1.3 Train Adolescent Club members as per curriculum on child protection, GBV and sexual violence, domestic violence, child and women's rights, child labor, child trafficking and gender, as well as DRR, and organize refreshers | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 1.1.4 In training, address barriers that prevent identification of victims and demand for case management services and make known referral mechanisms to such services, specifically to GBV and sexual violence case management services | same as above
| Use a simple and confidential documentation re referrals done | see line 21, time of teachers and facilitator(s) to collect information, and of implementing partners to compile and analyse it
| 1.1.5 Support clubs to organise awareness raising activities on topics they chose, including sexual violence-related, for members of their community | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials) for preparation; transport to public space in camps, facilitator(s) to mentor and accompany
| 1.1.6 Ensure participation of 2 Adolescent Club members (M/F) in meetings of the respective CBCPM | Transport, facilitator(s) to accompany the adolescents
| 1.1.7 Train staff on specific age and gender appropriate curriculum for the girls groups and allow for time for adaptations that still might be needed | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national expert staff of implementing partners, attendance sheets, pictures
| 1.1.8 Train group of adolescent girls as per curriculum through a girls-only space more in-depth on GBV and sexual violence (early/child marriage, rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), SRHR and women's rights, and organize refreshers | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 1.1.9 Do home visits to households of adolescent girls | Transport, time of facilitator(s), attendance sheet, pictures
| 1.1.10 Train staff on specific age and gender appropriate curriculum for the boys groups and allow for time for adaptations that still might be needed | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national expert staff of implementing partners, attendance sheets, pictures
| 1.1.11 Train group of adolescent boys as per curriculum through a boys-only space more in-depth on GBV and sexual violence (rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), gender (equitable gender roles, equitable and respectful relations/relationships, SRHR and consent, women's rights, and organize refreshers | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 1.1.12 Do home visits to households of adolescent boys | Transport, time of facilitator(s), attendance sheet, pictures
Output 2.1 | Output 2.1: Caregivers obtained new knowledge, changed practices and attitudes on child protection, GBV and sexual violence, on domestic violence, child development and parenting, on child and women's rights as well as gender
| 2.1.1 Train staff on specific curriculum for caregivers and allow for time for adaptations that still might be needed | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national expert staff of implementing partners, attendance sheets, pictures
| 2.1.2 Mobilize caregivers | Transport, time of facilitator(s)
| 2.1.3 Train caregivers as per curriculum on child protection, GBV and sexual violence, on domestic violence, child development and positive parenting, on child and women's rights as well as gender, and organize refreshers | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 2.1.4 In training, address barriers that prevent identification of victims and demand for case management services and make known referral mechanisms to such services, specifically to GBV and sexual violence case management services | same as above
Output 2.2 | Output 2.2: Teachers enhanced knowledge and skills on child protection, GBV and sexual violence, on DRR, on child development, child and women's rights as well as gender and changed practices towards positive discipline; Madrasha teachers/religious leaders increased their awareness and knowledge on child protection, GBV and sexual violence, as well as positive discipline
| 2.2.1 Train staff on specific curriculum for teachers and madasha teachers/religious leaders and allow for time for adaptations that still might be needed | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national expert staff of implementing partners, attendance sheets, pictures
| 2.2.2 Train teachers of Learning Centers as per curriculum on child protection, GBV and sexual violence, on DRR, on child development and positive discipline, on child and women's rights and gender as well as PSS and PFA as well as on code of conduct, and organize refreshers | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 2.2.3 In training, address barriers that prevent identification of victims and demand for case management services and make known referral mechanisms to such services, specifically to GBV and sexual violence case management services | same as above
| Use a simple and confidential documentation re referrals done | see line 21, time of teachers and facilitator(s) to collect information, and of implementing partners to compile and analyse it
| 2.2.4 Train members of LCMC (Learning Center Management Committees) - where existing - on child protection and PFA | Venue, transport, lunch, stationery (pens, marker pens, notebooks, and related materials), training modules and manuals, trainer(s) to conduct training: national expert staff of implementing partners, attendance sheets, pictures
| 2.2.5 Train Madrasha teachers/religious leaders on child protection, GBV and sexual violence, as well as positive discipline, and organize refreshers | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 2.2.6 Ensure participation of one religious leader in meetings of the respective CBCPM | Transport
Output 3.1 | Output 3.1: CBCPMs members, including majhis, increased their knowledge on child protection, GBV and sexual violence, on DRR, on domestic violence, child and women's rights as well as gender, and agreed on actions for child protection
| 3.1.1 Establish CBCPMs | Transport, time of facilitator(s)
| 3.1.2 Train members of CBCPMs, including majhis, as per curriculum on child protection, GBV and sexual violence, on DRR, domestic violence, on child and women's rights and gender | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to conduct training, attendance sheets, pictures
| 3.1.3 Monitor and accompany CBCPMs to come up with an action plan including (GBV/sexual violence) risk mitigation actions | Venue, snacks, stationery (pens, marker pens, notebooks, and related materials), training materials, facilitator(s) to accompany and nurture the process, MoM, attendance sheets, action plans, pictures
| 3.1.4 In training, address barriers that prevent identification of victims and demand for case management services and make known referral mechanisms to such services, specifically to GBV and sexual violence case management services | same as in line 55
| Use a simple and confidential documentation re referrals done | see line 21, time of teachers and facilitator(s) to collect information, and of implementing partners to compile and analyse it
| 3.1.5 Ensure participation of 2 representatives (F/M) from the Adolescent Club and of 1 religious leader in the CBCPM | Transport
Output 3.2 | Output 3.2: Coordination and follow-up were improved with different actors, especially those that work on CBCPMs and provide referral services
| 3.2.1 Invite relevant actors to coordination and exchange meetings | Email, telephone and/or personal communication
| 3.2.2 Organize regular meetings | Venue, stationery, snacks, attendance sheets, MoM
| 3.2.3 Report regularly to Child Protection Focal point | Time of staff of the three implementing partners, written reports or notes on reported points
Note on D28: Gritt Richter: approx. 10-15 girls and 20 boys 1 member from each family of the sub-block or if there is a Learning Center/Adolescent Center, entry point will be there to select the members
Note on D43: Gritt Richter: Arrange meetings with caregivers (seperated male/female) to raise their awareness --> Go sub-block by sub-block: stay 1-2 months in a subblock to reach all caregivers and raise their awareness on a pre-defined set of different topics; move then to the next sub-block with the next set of topics (rotation approach recommended by SKUS)
Note on D51: Gritt Richter: ++ A one-to-one tailor made and rather informal approach needs to be used: - rapport building is crucial - then regular interaction with them Suggestions: ++ Explore progressive Qur'anic verses that can serve child protection causes e.g. re non-violence/non-violent teaching, protection of the weakest… ++ Identify more progressive imams that can potentially play a prominent role when working with/ approaching 'hardliners'
Note on D55: Gritt Richter: Meetings on: Roles and responsibilities, Code of conduct, Action Plan, Resource mapping in the community, Trainings --> Monthly meetings + extra meetings for trainings and refreshers

## TargetGroupMatrix
TARGET GROUP MATRIX
Outcome | Main Activity | Target group | Where will the activity take place? | Which number of female/male will benefit from the activity (target) |  |  | For which age group the activity is designed | Target re certain activities | Average number of participants | Type of target group
| Responsible organisation | Adolescents, caregivers/parents/legal guardians, teachers, madrasha teachers/religious leaders | Camp number | Female | Male | Total | 6-9 years old 10-14 years old 15-19 years old 20-24 years old 25 years old and above | Target number for clubs, groups, CBCPMs | Clubs, groups, CBCPMs | Direct or Indirect beneficiaries
Output 1.1: Adolescents were empowered with new knowledge and skills, and changed attitudes on child protection, GBV and sexual violence, SRHR, child and women's rights, child labor, child trafficking and gender as well as DRR | 1.1.3 Train Adolescent Club members as per curriculum on child protection, GBV and sexual violence, domestic violence, child and women's rights, child labor, child trafficking and gender, as well as DRR, and organize refreshers
Total direct beneficiaries: 1360 adolescents organized in 68 Adolescent Clubs Total indirect beneficiaries: around 6000 | Educo | adolescents: boys and girls | Camp 8E | 500 | 500 | 1000 | 12 to 14 years old 15 to 17 years old | 50 | 20 | Direct
| JCF | adolescents: boys and girls | Camp 8W | 160 | 160 | 320 | 12 to 14 years old 15 to 24 years old | 16 | 20 | Direct
| SKUS | adolescents: boys and girls | Camp 17 | 20 | 20 | 40 | 12 to 14 years old 15 to 24 years old | 2 | 20 | Direct
1.1.5 Support clubs to organise awareness raising activities on topics they chose, including sexual violence-related, for members of their community
| Educo, JCF, SKUS 2 campaigns per year per organization = 12 campaigns over the 2 years Estimation: approx. and max. 1000 community members reached per campaign (very large campaigns are not allowed in the camps) | Children and adolescents, Adults | Camp 8E Camp 8W Camp 17 | 1800 | 1800 | 3600 | most likely 20-24 years old 25 years old and above | 12 | 300 | Indirect
1.1.8 Train group of adolescent girls as per curriculum through a girls-only space more in-depth on GBV and sexual violence (early/child marriage, rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), SRHR and women's rights, and organize refreshers
Total direct beneficiaries: 680 adolescent girls organized in 34 groups (these girls are the same as in activity 1.1.3 above) | Educo | adolescent girls | Camp 8E | 500 | 0 | 500 | 12 to 14 years old 15 to 17 years old | 25 | 20 | Direct
| JCF | adolescents girls | Camp 8W | 160 | 0 | 160 | 12 to 14 years old 15 to 24 years old | 8 | 20 | Direct
| SKUS | adolescents girls | Camp 17 | 20 | 0 | 20 | 12 to 14 years old 15 to 24 years old | 1 | 20 | Direct
1.1.11 Train group of adolescent boys as per curriculum through a boys-only space more in-depth on GBV and sexual violence (rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), gender (equitable gender roles, equitable and respectful relations/relationships, SRHR and consent, women's rights, and organize refreshers
Total direct beneficiaries: 680 adolescent boys organized in 34 groups (these boys are the same as in activity 1.1.3 above) | Educo | adolescent boys | Camp 8E | 0 | 500 | 500 | 12 to 14 years old 15 to 17 years old | 25 | 20 | Direct
| JCF | adolescents boys | Camp 8W | 0 | 160 | 160 | 12 to 14 years old 15 to 24 years old | 8 | 20 | Direct
| SKUS | adolescents boys | Camp 17 | 0 | 20 | 20 | 12 to 14 years old 15 to 24 years old | 1 | 20 | Direct
Output 2.1: Caregivers obtained new knowledge, changed practices and attitudes on child protection, GBV and sexual violence, on domestic violence, child development and parenting, on child and women's rights as well as gender | 2.1.3 Train caregivers as per curriculum on child protection, GBV and sexual violence, on domestic violence, child development and positive parenting, on child and women's rights as well as gender, and organize refreshers
Total direct beneficiaries: 2210 adults | Educo | caregivers/parents/legal guardians | Camp 8E | 375 | 375 | 750 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
| JCF | caregivers/parents/legal guardians | Camp 8W | 480 | 480 | 960 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
| SKUS | caregivers/parents/legal guardians | Camp 17 | 250 | 250 | 500 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
Output 2.2: Teachers enhanced knowledge and skills on child protection, GBV and sexual violence, on DRR, on child development, child and women's rights as well as gender and changed practices towards positive discipline; Madrasha teachers/religious leaders increased their awareness and knowledge on child protection, GBV and sexual violence, as well as positive discipline | 2.2.2 Train teachers of Learning Centers as per curriculum on child protection, GBV and sexual violence, on DRR, on child development and positive discipline, on child and women's rights and gender as well as PSS and PFA as well as on code of conduct, and organize refreshers
Total direct beneficiaries: 256 adults Total indirect beneficiaries: 9490 children and adolescents | Educo | Teachers | Camp 8E | 20 | 20 | 40 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
| Educo | Children and adolescents | Camp 8E | 800 | 800 | 1600 | 6 to 9 years old 10 to 14 years old (mostly) 15 to 17 years old (for some) | NA | NA | Indirect
| JCF | Teachers | Camp 8W | 93 | 93 | 186 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
| JCF | Children and adolescents | Camp 8W | 3720 | 3720 | 7440 | 6 to 9 years old 10 to 14 years old (mostly) 15 to 17 years old (for some) | NA | NA | Indirect
| SKUS | Teachers | Camp 17 | 25 | 5 | 30 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
| SKUS | Children and adolescents | Camp 17 | 225 | 225 | 450 | 6 to 9 years old 10 to 14 years old (mostly) 15 to 17 years old (for some) | NA | NA | Indirect
| JCF and SKUS | Head teachers, line managers, technical officers from JCF and SKUS | Camp 8W Camp 17 | 30 | 30 | 60 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
| JCF | LCMC (Learning Center Management Committees) members | Camp 8W | 704 | 704 | 1408 | most likely 20-24 years old 25 years old and above | NA | NA | Direct
2.2.5 Train Madrasha teachers/religious leaders on child protection, GBV and sexual violence, as well as positive discipline, and organize refreshers
Total direct beneficiaries: 100 adults | Educo | Madrasha teachers/Religious leaders | Camp 8E | 0 | 20 | 20 | most likely 25 years old and above | NA | NA | Direct
| JCF | Madrasha teachers/Religious leaders | Camp 8W | 0 | 60 | 60 | most likely 25 years old and above | NA | NA | Direct
| SKUS | Madrasha teachers/Religious leaders | Camp 17 | 0 | 20 | 20 | most likely 25 years old and above | NA | NA | Direct
Output 3.1: CBCPMs members, including majhis, increased their knowledge on child protection, GBV and sexual violence, on DRR, on domestic violence, child and women's rights as well as gender, and agreed on actions for child protection | 3.1.2 Train members of CBCPMs, including majhis, as per curriculum on child protection, GBV and sexual violence, on DRR, domestic violence, on child and women's rights and gender
Total direct beneficiaries: 1100 adults | Educo | Adults: women and men | Camp 8E | 500 | 500 | 1000 | most likely 20-24 years old 25 years old and above | 50 | 20 | Direct
| JCF | Adults: women and men | Camp 8W | 0 | 0 | 0 | most likely 20-24 years old 25 years old and above | 0 | 0 | Direct
| SKUS | Adults: women and men | Camp 17 | 50 | 50 | 100 | most likely 20-24 years old 25 years old and above | 5 | 20 | Direct
Output 3.2: Coordination and follow-up were improved with different actors, especially those that work on CBCPMs and provide referral services | 3.2.2 Organize regular meetings
Total direct beneficiaries: 60 adults | Educo and SKUS | Adults: representatives of other NGOs | Camp 8E Camp 8W Camp 17 | 30 | 30 | 60 | most likely 20-24 years old 25 years old and above | 8 meetings | NA | Direct
Summary table Beneficiaries | Direct beneficiaries |  |  | Indirect beneficiaries
| Female | Male | Total | Female | Male | Total
Adolescents (Clubs and groups) | 680 | 680 | 1360 | NA | NA | NA
Community members reached via Adolescent Clubs | NA | NA | NA | 1800 | 1800 | 3600
Caregivers | 1105 | 1105 | 2210 | NA | NA | NA
Teachers, including some head teachers, line managers… | 168 | 148 | 316 | NA | NA | NA
LCMC (Learning Center Management Committees) members | 704 | 704 | 1408 | NA | NA | NA
Children and adolescents reached via teachers of Learning Centers | NA | NA | NA | 4745 | 4745 | 9490
Madrasha teachers/religious leaders | NA | 100 | 100 | NA | NA | NA
CBCPMs members | 550 | 550 | 1100 | NA | NA | NA
Representatives of other NGOs | 30 | 30 | 60 | NA | NA | NA
Total | 2533 | 2613 | 5146 | 6545 | 6545 | 13090
Note on E36: user: Relegious leader and Madrasa teachers are same person
Note on M27: Gritt Richter: 1 teacher is running 1 classroom and can therefore be considered 1 Learning Center Info Educo Cox, 1.1.2020
Note on G6: Gritt Richter: For some fields we had to work with guesstimates with regards to numbers of F and M, e.g. 1.1.5, 2.1.3 or under 2.2.2 re Head teachers, line managers, technical officers from JCF and SKUS or LCMC (Learning Center Management Committees) members

## IndicatorsBaselineTarget
MEASURABLE INDICATORS: BASELINES AND TARGETS
Outcome 1: Adolescents - amongst them survivors, witnesses and/or victims of GBV and sexual violence - are able to prevent and respond to child protection issues, especially GBV and sexual violence, and access quality case management services | Indicator | Baseline | Target
| % of adolescents (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence | will be informed after the baseline study was done | 80%
| % of adolescents (disaggregated by sex) with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services | will be informed after the baseline study was done | 80%
| % of adolescents (disaggregated by sex) with positive change in attitudes towards early/child marriage | will be informed after the baseline study was done | 80%
| % of adolescent boys with positive change in attitudes towards the right to education for girls | will be informed after the baseline study was done | 80%
| % of adolescents (disaggregated by sex) with increased connections to peers | will be informed after the baseline study was done | 80%
| % of adolescents (disaggregated by sex) with increased connections to caring adults/role models | will be informed after the baseline study was done | 80%
| no of affected and/or at-risk adolescents (disaggregated by sex) referred to quality age and gender sensitive case management services, specifically to GBV and sexual violence case management services | NA
| % of adolescents reporting their club/group environment is safe to learn | 0 | 80%
Outcome 2: Caregivers, formal and informal teachers as well as religious leaders and majhis are proactive in preventing and responding to child protection issues, especially to GBV and sexual violence, affecting children and adolescents | Indicator | Baseline | Target
| % of caregivers (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence | will be informed after the baseline study was done | 80%
| % of caregivers (diaggregated by sex) with improved knowledge about positive parenting | will be informed after the baseline study was done | 80%
| % of careigivers (disaggregated by sex) with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services | will be informed after the baseline study was done | 80%
| % of caregivers with positive change in attitudes towards early/child marriage | will be informed after the baseline study was done | 80%
| % of caregivers with positive change in attitudes towards positive parenting (e.g. corporal punishment, listening to the opinion my child) | will be informed after the baseline study was done | 80%
| % of teachers of Learning Centers (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence | will be informed after the baseline study was done | 80%
| % of teachers (diaggregated by sex) with improved knowledge on positive discipline | will be informed after the baseline study was done | 80%
| % of teachers (diaggregated by sex) with improved knowledge on PSS (Psychological Support) and PFA (Psychological First Aid) | will be informed after the baseline study was done | 80%
| % of teachers (disaggregated by sex) with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services | will be informed after the baseline study was done | 80%
| % of teachers with positive change in attitudes towards corporal punishment and verbal abuse | will be informed after the baseline study was done | 80%
| % of teachers of Learning Centers having signed the code of conduct --> INDICATOR LINKED TO SDG5: Whether or not legal frameworks are in place to promote, enforce and monitor equality and non-discrimination on the basis of sex (Indicator 5.1.1 ) | 0 | 80%
| % of Learning Centers having put the code of conduct visible | 0 | 90%
| no of affected and/or at-risk adolescents (disaggregated by sex) referred to quality age and gender sensitive case management services by teachers of Learning Centers and of home-based learning | NA
Outcome 3: Community-based Child Protection Mechanisms (CBCPMs) work effectively at community and camp level to prevent and respond to child protection issues, especially to GBV and sexual violence, affecting children and adolescents | Indicator | Baseline | Target
| % of CBCPM members (disaggregated by sex) with improved knowledge on key child protection issues, GBV and sexual violence | will be informed after the baseline study was done | 80%
| % of members of CBCPM with correct knowledge on referral mechanism to case management services, specifically to GBV and sexual violence case management services | will be informed after the baseline study was done | 80%
| % of CBCPM (female and male leader of the committee) with a documentation on the referral mechanism available in their committee (e.g. images, flowcharts) | NA | 90%
| no of affected and/or at-risk adolescents (disaggregated by sex) referred to quality age and gender sensitive case management services by CBCPMs | NA
| Key issues of the forum of representatives of different child protection actors running CBCPMs are reported regularly to the CP focal point | NA | Regular dialogue
| Indicator | Baseline | Target
Output 1.1: Adolescents were empowered with new knowledge and skills, and changed attitudes on child protection, GBV and sexual violence, SRHR, child and women's rights, child labor, child trafficking and gender as well as DRR | INDICATOR LINKED TO ALL OUTPUTS OF THE PROJECT AND TO SDG 4: ++ Participation rate/no of youth and adults in formal and non-formal education and training [in the previous 12 months], by sex (Indicator 4.3.1) | 0 | number of all direct beneficiaries: 5146
| no of adolescent clubs established | 9 | 68
| no of adolescents (disaggregated by sex) trained on child protection, GBV and sexual violence | 0 | 1360
| no of adolescent-led actions supported by the program on key child protection topics, including GBV and sexual violence-related, for members of their community | 0 | 12
| no of community members reached by adolescent-led actions on key child protection issues, including GBV and sexual violence related | 0 | 3600
| no of adolescent girls groups established | 0 | 68
| no of adolescent girls trained more in depth on GBV and sexual violence (early/child marriage, rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), SRHR and women's rights | 0 | 680
| no of adolescent boys groups established | 0 | 68
| no of adolescent boys trained more in depth on GBV and sexual violence (rape/sexual abuse within marriage or dating relationships, sexual harassement/exploitation in the camps), gender (equitable gender roles, equitable and respectful relations/relationships, SRHR and consent, women's rights | 0 | 680
Output 2.1: Caregivers obtained new knowledge, changed practices and attitudes on child protection, GBV and sexual violence, on domestic violence, child development and parenting, on child and women's rights as well as gender | Indicator | Baseline | Target
| no of caregivers (disaggregated by sex) trained on key child protection issues (e.g. early/child marriage), GBV and sexual violence, on child and women's rights, and gender | 0 | 2210
| no of caregivers (disaggregated by sex) trained on child development and positive parenting leading to improved relationships with the children under their care | 0 | 2210
Output 2.2: Teachers enhanced knowledge and skills on child protection, GBV and sexual violence, on DRR, on child development, child and women's rights as well as gender and changed practices towards positive discipline; Madrasha teachers/religious leaders increased their awareness and knowledge on child protection, GBV and sexual violence, as well as positive discipline | Indicator | Baseline | Target
| no of teachers of Learning Centers (including some head teachers and line managers…) trained on child protection, GBV and sexual violence, on child development and positive discipline, on child and women's rights and gender | 0 | 316
| no of teachers (including some head teachers and line managers…)trained on PSS (Psychological Support) and PFA (Psychological First Aid) so that they are able to identify children at risk and refer them | 0 | 316
| no of LCMC members (Learning Center Management Committees) trained on child protection and PFA | 0 | 1408
| no of religious leaders/madrasha teachers the program is in regular contact with | 0 | 100
| no of religious leaders/madrasha teachers trained on child protection, GBV and sexual violence | 0 | 100
| no of religious leaders/madrasha teachers trained on positive discipline | 0 | 100
Output 3.1: CBCPMs members, including majhis, increased their knowledge on child protection, GBV and sexual violence, on DRR, on domestic violence, child and women's rights as well as gender, and agreed on actions for child protection | Indicator | Baseline | Target
| no of CBCPM establised | 16 | 55
| no of CBCPM trained on child protection, GBV and sexual violence, domestic violence, child and women's rights and gender |  | 55
| no of CBCPM active (meet regularly) | 16 | 80% (44)
| no of CBCPM with a viable/ relevant action plan including (GBV/sexual violence) risk mitigation actions | 0 | 80% (44)
Output 3.2: Coordination and follow-up were improved with different actors, especially those that work on CBCPMs and provide referral services | Indicator | Baseline | Target
| A forum of representatives of different child protection actors running CBCPMs is created | No | Yes
| no of meetings/ experience sharing gatherings | NA | 8 meetings
Note on D40: Gritt Richter: to date 7 Educo and 2 SKUS
Note on D62: Gritt Richter: to date 11 Educo and 5 Skus
Note on E40: Gritt Richter: 34 in Year 1 34 in Year 2
Note on E42: Gritt Richter: 6 in Year 1 6 in Year 2
Note on E43: Gritt Richter: 1800 in Year 1 1800 in Year 2
Note on E44: Gritt Richter: 34 in Year 1 34 in Year 2
Note on E46: Gritt Richter: 34 in Year 1 34 in Year 2

## Definitions
DEFINITIONS
Definitions re age brackets The Lancet Commission on adolescent health and wellbeing defines: ++ early adolescence (10–14 years, Very Young Adolescents, VYAs); late adolescence (15–19 years) ++ "Adolescent": 10-19 years The WHO defines: ++ adolescent (10-19 years); youth (20-24 years); young people (10-24 years) Other: ++ "Infant": a child younger than 1 year of age; "Child": 0-9 years old ++ Age definition of adult/adulthood is different and changing (adulthood: a combination of age and the achievement of social milestones). Most countries have a legally defined age to determine when a person is considered an adult. This project works above all with adolescents (12-17 years ols) as direct beneficiaries and with regards to the Learning Centers with children and adolescents (6-17 years old) as indirect beneficiaries. | Definition Child Protection UNICEF defines child protection in referring to prevention and response to violence, exploitation and abuse against children – including commercial sexual exploitation, trafficking, child labour and harmful traditional practices, such as female genital mutilation/cutting and child marriage. The overall goal of this proposed project is directly linked to the Child Protection in Emergencies definition developed by the Cox’s Bazar Child Protection Sub-Sector for the Rohingya refugee response: - Child Protection in emergencies is “Preventing and responding to abuse, neglect, violence and exploitation. This includes protecting and advocating against all forms of discrimination; ensuring immediate access to appropriate services; and ensuring durable solutions in the child’s best interests. Child protection in emergencies includes specific activities […] including issues such as sexual exploitation, family separation, trafficking, child recruitment, child labour, danger and injuries, physical violence and harmful traditional practices, such as early marriage.” (JRNA) - Educo includes explicitly GBV and sexual violence in this definition, even though not literally mentioned herein. Definitions re Violence Gender-based violence (GBV) and violence against women (VAW) are terms that are often used interchangeably as it has been widely acknowledged that most gender-based violence is inflicted on women and girls, by men. (EIGE) According to the UN Declaration on the Elimination of Violence Against Women, GBV "results in, or is likely to result in, physical, sexual or psychological harm or suffering of women, including threats of such acts, coercion or arbitrary deprivation of liberty, whether occurring in public or in private life." Different types of GBV are: + Physical violence + Sexual violence + Emotional/psychological violence + Economic violence. (UNFPA) Sexual violence is one form of GBV and "any sexual act performed on an individual without their consent" (EIGE) The WHO defines the following forms and contexts of sexual violence: — rape within marriage or dating relationships; — rape by strangers; — systematic rape during armed conflict; — unwanted sexual advances or sexual harassment, including demanding sex in return for favours; — sexual abuse of mentally or physically disabled people; — sexual abuse of children; — forced marriage or cohabitation, including the marriage of children; — denial of the right to use contraception or to adopt other measures to protect against sexually transmitted diseases; — forced abortion — violent acts against the sexual integrity of women, including female genital mutilation and obligatory inspections for virginity; — forced prostitution and trafficking of people for the purpose of sexual exploitation.
Note on C6: Gritt Richter: EIGE https://eige.europa.eu/gender-based-violence/what-is-gender-based-violence UNFPA https://www.unfpa.org/sites/default/files/pub-pdf/cap-6.pdf WHO https://www.who.int/violence_injury_prevention/violence/global_campaign/en/chap6.pdf UNICEF https://www.unicef.org/protection/files/What_is_Child_Protection.pdf