Terms of Reference for Appointment Nutrition Expert/ Agency/Consulting Farm/NGO for “Development Entrepreneur led Disability Inclusive Nutrition and Food Security -SBCC materials for awareness and Behavior Change Communication”

Background:

Eco-Social Development Organization (ESDO) started its journey in 1988 with a noble vision to stand in solidarity with the poor and marginalized. Being a people` entered organization, ESDO envisioned for a society which will be free from inequality and injustice, a society where no child will cry from hunger and no life will be ruined by poverty. Near about three decades of relentless efforts to make this happen, ESDO has embraced new grounds and opened up new horizons to help the disadvantaged and vulnerable people to bring meaningful and lasting changes in their lives. During this long span, ESDO has adapted with the changing situation and provided the most time-bound services especially for the poor and disadvantaged. A community focused and people centered approach has been adapted by ESDO while consideration was given to the national policy and Sustainable Development Goals (SDGs) as its guiding principle. ESDO is one of the most dynamic organizations expanding its development interventions across 283 upazilas under 49 districts of Bangladesh covering over 10 million poor and vulnerable people.

Max Foundation Bangladesh has started implementing a 4-year (July 2022 – July 2026) Healthy Village Urban (HVU) Programme in Lalmonirhat district in Bangladesh and being implemented through partnering with ESDO. ESDO is implementing the Healthy Village in Urban (HVU) programme in Lalmonirhat municipality and six peri-urban Unions within Lalmonirhat district. The Healthy Village program of Max Foundation has been in operation since 2017. Already 409 villages in the South-coastal region of Bangladesh declared as Healthy Villages. With the technical and financial support provided by Max Foundation, we are scaling-up the Healthy Village program to urban and peri-urban areas of Lalmonirhat district. The programme targets reaching out 235,000 beneficiaries through 47,418HHs (with 14,700 children under five and an estimated 1,470 of those disabled, pregnant mother 1,630, Lactating mother 6,685 and women at the reproductive age 52,824), which is the total estimated urban and peri-urban population of the district

Project Goal: 235,000 improved lives through improved access to health care, WASH and nutrition by disability inclusive activities in the urban and peri-urban population in Lalmonirhat.

Project Outcome:

Outcome 1: Increased attention by caregivers and health providers to child growth and health, with growth data measured and used for improvement

Outcome 2: Children under five and mothers with improved nutrition

Outcome 3: Safe water, sanitation and hygiene practices improved so that waterborne and infectious diseases (such as COVID-19) are reduced

Outcome 4: Children and parents with disabilities have improved access to (government or other) services for health (hygiene, nutrition or disability related)

Outcome 5: Strengthened local market for WASH, health and nutrition products and services through female and male entrepreneurs and sales agents.

Outcome 6: Improved resilience for target communities to disasters (COVID-19 and flooding)

Key 5 Points to consider in developing Training Manual and guideline:

- Outcomes led: It is pertinent to mention here that disability inclusive nutrition and food security guidelines and training module will be guided by above-mentioned outcomes that led to attain the goal of the project.

- Better Nutrition:  Consultant / Consulting farms explore how to influence mothers, caregivers, parents and children with disabilities in our approach, so that all of them have improved nutrition and access of all available facilities for their better/improved lives

- Prevention of disability: As Healthy Village Programme aims to reduce stunting and ensure safe motherhood in an efficient way so that future disability can be prevented and help all children get a healthy start in life. So, how best this could be attained needs to incorporate in the SBCC materials and facilitator guideline

- Inclusion of people with a disability in our Healthy Village Programme : Some Healthy Village activities need to be adapted to ensure equitable participation of children/parents with disability. So, to explore any new activities for specific support to children or parents with disabilities need to be added to the Healthy Village approach needs to incorporate in SBCC materials and facilitator guideline

- The project will work together with Disabled People’s Organizations’ (DPOs), local government and schools to strengthen the voice of people with disabilities.

Therefore, HVUP programme will take initiative to develop entrepreneur led differently able inclusive nutrition and food security SBCC materials and facilitator guideline as well as to train project staff in this regard.

Project Working Area:

The project is implementing in 06 (Six) Unions and 01 (One) municipality under 02 (Two) Upazillas of Lalmonirhat district. The project areas are: Under Lalmonirhat Sadar Upzilla : Lalmonirhat municipality, Unions- Harati, Mahendranagar, Kulaghat and Mogolhat. Under Aditmari Upazila: Unions- Saptibari and Sarpukur.

Scope of Work

The consultancy agency/consultant is expected to undertake the following tasks and responsibilities:

- Desk Review

- Review the government/NGOs/INGOs existing disable and climate friendly nutrition and food security related SBCC materials emphasizing resilient livelihood creation materials like Poster, Brochure, Leaflet, sticker, flipchart, facilitator guideline etc.

- Identify critical gaps in the existing entrepreneur led differently able inclusive SBCC materials on nutrition considering food security and care and strengthening local market and product for the HPAs

- Thinking creatively to produce new ideas and concepts in developing SBCC materials

- Listed and collected a sample copy of each of the disable friendly SBCC materials already developed both electronic and printed ( If possible)

- Stakeholder Consultation/Interviews

- In consultation with the Institute of Public Health Nutrition (IPHN), NNS, BNNC, ADD, DORP, Handicap International, and others as appropriate and scope of the review of SBCC materials for their feedback which would be used during courtyard session, IEC/BCC session and interpersonal communication and advocacy.

- Consult with Nutrition and Entrepreneurship Capacity Building Expert – ESDO and Max Foundation Bangladesh, Program Manager on the SBCC materials to be developed.

- Facilitate a consultative workshop with relevant stakeholders at the national level to get feedback/comments and inputs for the SBCC materials and facilitator guidelines and recommendations.

- Produce SBCC materials and facilitator guideline Based on Desk Review and Consultations

- Prepare a list of the SBCC materials on nutrition considering food security and care of the disable children and strengthening local market and product for the health promotion agents (HPAs) in line with Healthy Village in urban project outcome. This will be treated as inception report

- Develop an advocacy and communication strategy brief based on the desk review and consultation.

- Develop checklist/tools for monitoring use of the SBCC materials of the ESDO staff at Lalmonirhat district and its level of understanding of the targeted beneficiaries

- Pre-test all the SBCC materials to be developed/used for on-the-job capacity building with the inclusion of feedback from the targeted beneficiaries’ stakeholders /mothers/ trainers for any necessary adjustments.

- Printing SBCC materials for use in the field with prior pre-testing and proof check by ESDO.

- Conduct Training of Master Trainers

- Consultant/agency will organize and conduct 3 days training to the ESDO staff on the developed SBCC materials, checklist following facilitation guideline.  So that later master trainers may acquire the skill in conducting the training at the field level targeted population.

Deliverables:

Based on the review of existing SBCC materials on basic nutrition and food security, WASH, and Entrepreneurship development. Following SBCC materials are expected to be developed by the consulting firm/Individuals but are not limited to

- Brochure (related to Health Village in Urban Program both Bangla and English).

- Pictorial Brochure (Entrepreneurship Development)

- Leaflet Pictorial.

- Poster (6 different posters on different issues in PVC).

- Flipchart (Health and Nutrition).

- Flipchart (focusing on Small and medium-sized enterprises (SMEs))

- Any other visual aids like Flash Card on different activities Like WASH, SRHR, Gender and Disability

- Sticker (with a different message related to Health Village in Urban Program)

- Roman Banner (Containing different appropriate messages)

- Pictorial Billboard for seven unions containing appropriate messages related to HVUP

- Facilitator guidebook/Handbook

- 5-6 script on 6 outcomes for street drama for mass awareness based on local context

- Development Piazzale Games

- Develop SBCC materials/facilitator guide for local use in Lalmonirhat district based on the findings of the review and consultations;

- Develop a checklist, tools, practice exercises, test questions, and other materials to assist post-training follow-up.

- Develop SBCC Advocacy and Communication Strategy aligned with outcome of the project.

- Conduct a 3 day training for master trainers to ESDO- staff on the developed SBCC materials on how to use them effectively for acquiring the necessary skill and knowledge to perform task like preparation, presentation, application, and evaluation

- The consultant will produce a comprehensive report giving findings from (a) document reviews, (b) field visits, (c) interviews with Max Foundation and ESDO personnel and other key players, (d) community consultation, (e) list of identified SBCC materials/ gaps (if any), and (f) suggestion of ways and means to address business development plan for the targeted population. This will be treated as a need assessment/inception report.

- The SBCC materials and facilitator guideline will produce following items upon completion and to be delivered to ESDO

- All planned, designed and illustrated copy of the final different types of SBCC materials (Each 100 copies in printed form)

- Final SBCC facilitator guideline and SBCC Strategy (100 copies in printed form each)

- Final designed version (both PDF and AI for printing) of Guideline and training materials as appropriate

Time Schedule:

The consultant farm/Individuals will make sure its deliverables as per following schedule:

| Sl.No | Particular of Deliverables | Date of completion |
| --- | --- | --- |
|  | Sign ToR by the concerned Authorities | 20th April 2024 |
|  | Review of existing disability-inclusive SBCC materials to prepare a stock-taking on available materials and methods and content for design and plan for SBCC materials. | 25th April 2024 |
|  | Field visit for Needs assessment to prepare, method and content of the SBCC materials and submission inception report. A brief report based on the desk review and consultation. This will be treated as an inception report. Submission of the Inception Report. | 27th April 2024 to 4th May 2024 |
|  | Prepare draft designed version all sets of SBCC materials with graphic design and illustrations or live pictures. A facilitator guide when and how best make it uses and checklist share with all concern | 6th May ,2024 to 6th June, 2024 |
|  | Pre-test all set of the SBCC materials developed with relevant stakeholders for feedback and to check appropriateness | 9th June ,2024 to 13th June, 2024 |
|  | Prepare and Submission approved final Set of SBCC materials, facilitators Guide line, Advocacy Strategy and check list share with all concern and printing required sets of SBCC materials | 30th June, 2024 |
|  | Conduct three days ToT to ESDO staff on the developed SBCC material and on Facilitation | 7th July 2024 to 10th July,2024 |

Consultancy Firms/ Individual Required Expertise:

For the purpose of this assignment, the consultant or consultancy agency should have the following:

- Agency/Consultant with at least 5-7 years of experience in conducting similar assignments in developing SBCC materials as per requirement, most preferably entrepreneur led disable friendly nutrition and food security programs.

- Extensive familiarity with Bangladesh’s Nutrition and food security program being implemented by the Government and NGOs and understanding of services relating to disability nutrition and health care.

- Experience in providing consulting services and excellent track record of completion of tasks according to timelines.

- Expertise in producing high quality SBCC materials in English and Bangla and sharing at national level and printing such best quality SBCC materials.

- Consulting firm/Individual should have sufficient knowledge on NGO activities and in developing SBCC materials.

Compliance Issues:

Consultant may not assign sub-contract, delegate, or otherwise transfer or dispose of any of its rights or obligations under this agreement. Additionally, no final deliverables are accepted after the deadline and in such case, penalty will be imposed as per ESDO’s procurement policy.

Budget and Payment:

Thirty (30) percent of the value of the contract will be paid after submission of the inception report. Thirty (30) percent will be paid upon submission of the first draft of all the materials. Rest Forty (40%) percent will be paid after acceptance of the final SBCC materials with printed sets and facilitator guideline and other deliverables.

- Payment will be made through cheque and eligible vat & tax will be deducted as per tax regulation of Bangladesh Government. Copies of NID, TIN, VAT Registration and Trade License, as applicable

- No traveling, per diem and daily allowances will be paid to consultant for the field visit, meeting, group discussion and any other purposes.

Terms and Conditions for this agreement:

- This contract will be fully short-term basis and not aligned with the organizational HR policy, recognized as regular or contract staff member of ESDO. This contract could be terminated with the prior notice of both parties due to failure the terms and conditions and commitment mentioned in this agreement.

- Total working days will be 80 days (over the period of April-20 to 10 July,24) for accomplishing the task. Comprising review, the project documents and preparation for design & development SBCC materials and facilitator guidelines, field visit and ToT of the ESDO staff.

- Developed SBCC materials and facilitator guidelines will be Max Foundation Bangladesh and ESDO’s property and copyright will be of Max Foundation Bangladesh and ESDO. All soft and hard copy (both PDF and AI) will be submitted to ESDO.

- Technological (print, photocopy) and other related information support will be given for this task. But no regular equipment support will be given like computer, lap top etc. A press-ready file for training modules ensuring that it meet organization standards.

- After preparing the 1st draft of the materials and facilitator guideline will have to arrange a workshop for sharing and collecting the feedback from relevant staff /stakeholders for finalization

Submission of Expression of Interest

The interested parties shall be asked to submit their technical and financial proposal. The main component of the technical proposal shall be

- Statement highlighting their past expertise (max. 2 page)

- C.V. of the team leader and associate

-  a brief how and what to develop proposed disable friendly SBCC and facilitator guideline   highlighting the contents in details (3to 4 pages).

Financial proposal to include detailed budget for design, developing SBCC and printing.

On the basis of technical and financial proposal submission, ESDO in consultation with Max Foundation Bangladesh management will select and invite one organization/consultant for this particular task.

Interested consultancy firm/consultant are requested to submit the proposals, including relevant experience, qualifications, methodology, timeline, and budget through both Hard copy and Soft copy to the ESDO Central Procurement Department, House #748, Road#8, Biatul Aman Housing Society, Adabor, Dhaka-1207 and email @ by April 15, 2024.

#### Max Foundation and ESDO Responsibilities:

- Under the guidance of the Max Foundation and ESDO management, Consultant/Organization will be responsible of all aspects of SBCC materials development, design, lay-out, formats style design, corrections for the final production.

- Advisor, and Nutrition Expert, and M&E Expert of ESDO in consultation with Max Foundation, Bangladesh will supervise the organization/consultant and will provide technical and logistical support.

- For the quality assurance of the key exercise, draft and final SBCC materials and other necessary documents will be shared to obtain their technical input and clearance before finalization of the draft and final SBCC materials.

- Provide recommendations on the best and most relevant visual design style. technical support and develop over all layout design of training materials and ensuring that the layouts fit the target audience (from a technical, professional and cultural standpoint

Contact Person:  Nutrition and Entrepreneurship Capacity Building Expert – ESDO will be the contact person for overall this consultancy service.  From the Max Foundation Bangladesh office, the PM will oversee the assignment.

Signature_________ 						Signature_____________

Agency/Consultant				                          Health Village in Urban Project