## Sheet1
MEAL Plan
Project Title : Enhancing the participation of community based organizations (CBOs) and CSOs in democratic governance in Bangladesh
Performance indictor | Operationalization of Indicator | Baseline Value (Reference Year Aug, 2018) | Mileston of the targeted Indicator |  |  |  |  | Data & information Source | Data & information Collection methods& tools | Frequency | Responsible data collection | Responsible data analysis and reporting | PCM Analysis
|  |  | Year -1 | Year -2 | Year -3 | Year -4 | Total ( At the end of the Project)
Overall Objective (Impact ) : To enhance the participation of community based organizations (CBOs) of vulnerable and marginalized communities and civil society organizations (CSOs) in democratic governance in Bangladesh
1. Percentage of targeted CBOs/CSOs participating and influencing governance in the targeted districts | *Participation: Participation is process by actively engagement of CBO, CSO and Community people in the planning, budgeting, implementing, monitoring of government services related interventions to ensure access to citizen rights. Participation may be regarded as a way of empowerment and as vital part of democratic governance. * Influence: Influenc is ability of the CBO and CSO to raise voice, create pressure, and sensitize services providers to ensure citizen rights and entitlement. | 1.1) Only 28.5% CBO and CSO are aware on alliance meeting ( district network meeting) 1.2) Of them, 29.6% CBOs participated in alliance meeting, Of them,79% of the meetings held at union level |  |  |  |  | 1) 80% of targeted CBOs/CSOs participating and influencing governance in the targeted districts at the end of project (260 CBO) . | Theory of change, Project Proposal, Baseline study report, Periodic Monitoring report, Midterm and endline evaluation report, Annual Report, Project Completion Report, Media coverage Report, Event reports, Projects Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, Van diagram and Case study. | Midterm and Final Quarter of the Project Period | External Evaluator, MEAL team of Oxfam | External Evaluator | Sustaibility & Impact
2. Number of targeted districts where LAs institutionalize mechanisms for the participation of CBOs/CSOs in planning, budgeting, implementation and oversight of policies | Institutionalize mechanisms: Institutionalize mechanisms means LAs will establish formal sustainable approved platform to ensure participation of CSOs/CBOs in planning, budgeting, implementation on different topics related to SDG | 2.1) The participation of CBOs with LAs in planning, budgeting, implementation and oversight of policies were present in 8 districts out of 13 2.2) The participation rate of CBO members was 62% 2.3) Of them, 87% in planning, 62% in implementation, 60% in budgeting and 18% in oversight of polices |  |  |  |  | At least 10 targeted districts where LAs institutionalize mechanisms for participation of CSOs/CBOs in planning, budgeting implementation and oversight of policies | Theory of change, Project Proposal, Baseline study report, Periodic Monitoring report, Midterm and endline evaluation report, Annual Report, Project Completion Report, Media coverage Report, Event reports, Projects Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, Van diagram and Case study. | Mid term and Final Quarter of the Project Period | External Evaluator, MEAL team of Oxfam | External Evaluator | Sustaibility & Impact
3) % of CSO/CBO representatives who express satisfaction with public budget allocations and implementation of SDG and NFYP related policies and programmes | *CBO: CBO refers to Community based organizations, which are nonprofit groups that work at a local level to improve life for residents *CSO: CSO: CSO is civil society organizations or social pressure or voice raise group including association, community leaders, teacher who work for vulnerable. . | 3) Overall 21% CBOs were satisfied with public budget allocations and were satisfied 4% implementation of SDG and NFYP related policies and programmes |  |  |  |  | At least 70% of CSO/CBO representatives who express satisfaction with public budget allocations and implementation of SDG and NFYP related policies and programmes (228 CBO) | Theory of change, Project Proposal, Baseline study report, Periodic Monitoring report, Midterm and endline evaluation report, Annual Report, Project Completion Report, Media coverage Report, Event reports, Projects Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, Van diagram and Case study. | Mid term and Final Quarter of the Project Period | External Evaluator, MEAL team of Oxfam | External Evaluator | Sustaibility & Impact
Specific Objectives: (Outcomes ): To strengthen grassroots CBOs and CSOs to secure the social and economic rights of vulnerable individuals and communities in the design and implementation of government policies and budgets related to Sustainable Development Goals (SDGs)
1) Number of targeted CBOs/CSOs actively participating in district accountability networks | Accountability network: Accountability network is a platform of the stakeholders including LA, CBO, CSO where they will evaluate on their performance or behavior related to ensure the social and economic rights of vulnerable individuals and communities in the design and implementation of government policies and budgets related to Sustainable Development Goals (SDGs). The obligation to demonstrate and take responsibility for performance in light of agreed expectations. Responsibility is the obligation to act; accountability is the obligation to answer for action | Members of 29 CBO are aware and participate on district accountability networks |  | At least 100 CBOs/CSOs actively participating in district networks | At least 100 CBOs/CSOs actively participating in district networks | At least 100 CBOs/CSOs actively participating in district networks | At least 300 CBOs/CSOs actively participating in district networks by end of the action | Theory of change, Project Proposal, Baseline study report, Periodic Monitoring report, Midterm and endline evaluation report, Annual Report, Project Completion Report, Media coverage Report, Event reports, Projects Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, Van diagram, meeting, and Case study. | Periodic Monitoring( yearly), Mid term and Final Quarter of the Project Period | External Evaluator, MEAL team of Oxfam | External Evaluator | Impact and Effectiveness
2) Number of targeted CBOs/CSOs engaged with LAs in the joint implementation and oversight of policies relating to SDGs and NFYP |  | 2.1)59 CBOs/CSOs engaged with LAs in the joint implementation relating to SDGs and NFYP 2.2) 53 CBOs/CSOs engaged with LAs in the joint oversight of policies relating to SDGs and NFYP |  | At least 100 CBOs/CSOs engaged with LAs in the joint implementation and oversight of policies relating to SDGs and NFYP | At least 100 CBOs/CSOs engaged with LAs in the joint implementation and oversight of policies relating to SDGs and NFYP | At least 100 CBOs/CSOs engaged with LAs in the joint implementation and oversight of policies relating to SDGs and NFYP | At least 300 CBOs/CSOs engaged with LAs in the joint implementation and oversight of policies relating to SDGs and NFYP | Theory of change, Project Proposal, Baseline study report, Periodic Monitoring report, Midterm and endline evaluation report, Annual Report, Project Completion Report, Media coverage Report, Event reports, Projects Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, Van diagram, meeting, and Case study. | Periodic Monitoring( yearly), Mid term and Final Quarter of the Project Period | External Evaluator, MEAL team of Oxfam | External Evaluator | Impact and Effectiveness
3) Number of target CSOs/CBOs organize and facilitate vulnerable communities’ participation in planning, implementation and oversight of policies and budgets related to SDGs and NFYPs | Vulnerable Community: People who are living under extreme poverty line and suffering inequality, lack of WASH, livelihood skill, face nature disaster etc. | 59 CBOs organize and facilitate vulnerable communities’ participation in planning, implementation and oversight of policies and budgets |  | at least 100 targeted CSOs/CBOs organize and facilitate vulnerable communities’ participation in planning, implementation and oversight of policies and budgets related to SDGs and NFYPs | at least 100 targeted CSOs/CBOs organize and facilitate vulnerable communities’ participation in planning, implementation and oversight of policies and budgets related to SDGs and NFYPs | at least 100 targeted CSOs/CBOs organize and facilitate vulnerable communities’ participation in planning, implementation and oversight of policies and budgets related to SDGs and NFYPs | By end of the action, at least 300 targeted CSOs/CBOs organize and facilitate vulnerable communities’ participation in planning, implementation and oversight of policies and budgets related to SDGs and NFYPs | Theory of change, Project Proposal, Baseline study report, Periodic Monitoring report, Midterm and endline evaluation report, Annual Report, Project Completion Report, Media coverage Report, Event reports, Projects Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, Van diagram, meeting, and Case study. | Periodic Monitoring( yearly), Mid term and Final Quarter of the Project Period | External Evaluator, MEAL team of Oxfam | External Evaluator | Impact and Effectiveness
Ouput:1 (Result) : CBOs and CSOs have enhanced organizational and influencing capacity to work with local authorities (LAs) to address government commitments on SDGs and the National Five Year Plan (NFYP).
1.1) Percentage of trained CBO/CSO and media representatives with improved knowledge on SDG targets, PFM, SAcc, budget analysis, and advocacy at local level | Social accountability : is an approach towards building accountability that relies on community engagement, in which citizens participate directly or indirectly in demanding accountability from service providers and public officials. Social accountability generally combines information on rights and service delivery with collective action for change. Examples of social accountability tools and mechanisms include participatory social audits, public expenditure tracking, citizen report cards, community score cards, citizen charters, and right to information acts. | 1.1) 3% CBO/CSO and 0% media representatives trained on SDG targets, PFM, SAcc, budget analysis, and advocacy level |  | 1.1) 75% of the trained CBO/CSO and media representatives (60% of which are women) with improved knowledge on SDG targets, PFM, SAcc, budget analysis, and advocacy by end of year 2 of the action ( 244 CBO). |  |  | 1.1) 75% of the trained CBO/CSO and media representatives (60% of which are women) with improved knowledge on SDG targets, PFM, SAcc, budget analysis, and advocacy ( 244 CBO) | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, interim report, donor report, case study report, minutes, Project Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
1.2) Percentage of LA representatives with improved knowledge and understanding of SDG targets and related government policies and programmes | LA (Local Authority): Local government Official | 1.2) 18 % LA representatives with improved knowledge and understanding of SDG targets and related government policies and programmes |  | 1.2) 70% of LA representatives (40% of which are women) with improved knowledge and understanding of SDG targets and related government policies and programmes by end of year 2 of the action |  |  | 1.2) 70% of LA representatives (40% of which are women) with improved knowledge and understanding of SDG targets and related government policies and programmes | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, interim report, donor report, case study report, minutes, Project Actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
1.3) Number of District Networks on Accountability formed by CBOs and CSOs and linked with Citizen's Platform for SDGs, Bangladesh | District network : The platform of CBO,CSO and Community leaders | 1.3.1) None of the CBOs was aware of Citizen's Platform for SDG. 1.3.2) 0 District network on Accountabilityformed by CBOs |  | 13 District Networks on Accountability formed by CBOs and CSOs and linked with Citizen's Platform for SDGs, Bangladesh by end of the action |  |  | 1.3) 13 District Networks on Accountability formed by CBOs and CSOs and linked with Citizen's Platform for SDGs, Bangladesh by end of the action | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes , Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
1.4) Number of District networks with agreed action plan to advocate for SDG implementation at local level |  | 1.4) None of the LA representative agreed to the fact that they have agreed action plan to advocate for SDG implementation at local level. |  | 1.4) 13 District networks with agreed action plan to advocate for SDG implementation at local level by end of year 2 of the action |  |  | 1.4) 13 District networks with agreed action plan to advocate for SDG implementation at local level by end of year 2 of the action | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes , Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
1.5) Set of SAcc tool adapted to local contexts | Social accountability tools : Social accountability tools and mechanisms include participatory social audits, public expenditure tracking, citizen report cards, community score cards, citizen charters, and right to information acts. | 1.5) Respondents were yet to receive training on SAcc tool | 1.5) 3 District adopted Set of SAcc tool accroding to local contexts | 1.5) 10 District adopted Set of SAcc tool accroding to local contexts |  |  | 1.5) 13 District adopted Set of SAcc tool accroding to local contexts | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes , Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
Output-2 ( Short and mid term Result): CBOs and CSOs support LAs/LGs to effectively deliver people-centred services as per existing laws and policies relating to SDGs.
2.1) Number of research studies on public service delivery effectiveness published at national level | Public service delivery effectiveness: The structure of the government services delivery system and mechanism. And the effectiveness of the public service delivery is people participation in the government services activities to ensure access to people rights and services. | 2.1. No research study publised |  | 2.1) 2 research studies on public service delivery effectiveness published |  |  | 2.1) 2 research studies on public service delivery effectiveness published by end of the action | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes, Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
2.2) Number of community consultations organized by CBOs/CSOs with LAs on SDG related policy implementation gaps. | Community consultations: Local level consultation with local authorities is very important for proper implementation of SDG related policies and programs. community consultations will take at Upazila level where the government duty bearers and CBO/CSO members will participate in the meeting. | 2.2.1) Each CBO organized 1.5 Community consultation meetings on average in last 1 year with LAs on SDG related policy implementation gaps. 2.2.2) Each LA representative organized 2.58 Community consultation meetings on average in last 1 year on SDG related policy implementation gaps |  | 2.2 ) 6 community consultations organized by CBOs/CSOs with LAs on SDG related policy implementation | 2.2 ) 4 community consultations organized by CBOs/CSOs with LAs on SDG related policy implementation . | 2.2 ) 3 community consultations organized by CBOs/CSOs with LAs on SDG related policy implementation | 2.2 ) At least 13 community consultations organized by CBOs/CSOs with LAs on SDG related policy implementation gaps by end of the action. | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
2.3) Number of targeted LAs with joint action mechanisms for implementation of SDG and NFYP related policies | To ensure accelerated progress in implementation of SDG-linked policies and programs, the project will organize dialogues between government and civil society stakeholders to devise joint action mechanisms for policy implementation. | 2.3) 0 LAs with joint action mechanisms for implementation of SDG and NFYP related policies | 2.3) 2 targeted LAs with joint action mechanisms for implementation of SDG and NFYP related policies | 2.3) 4 targeted LAs with joint action mechanisms for implementation of SDG and NFYP related policies | 2.3) 4 targeted LAs with joint action mechanisms for implementation of SDG and NFYP related policies | 2.3) 3 targeted LAs with joint action mechanisms for implementation of SDG and NFYP related policies | 2.3) 13 targeted LAs with joint action mechanisms for implementation of SDG and NFYP related policies | Theory of change, Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes, Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
2.4) Number of Newspaper supplements/Op-ed published highlighting public service delivery successes and best practices. | The dialogues will try to devise policy commitments from the policymakers and will also influence the advocacy agenda of other CSOs. The CBOs will discuss development issues and findings directly with policymakers and other stakeholders. The topics of the dialogues will include the research studies conducted as well as contemporary and medium-term SDG-linked development issues. | 2.4) 0 Newspaper supplements and Op-eds published |  | 2.4) 4 Newspaper supplements and Op-eds published | 2.4) 4 Newspaper supplements and Op-eds published | 2.4) 2 Newspaper supplements and Op-eds published | 2.4) At least 10 Newspaper supplements and Op-eds published by end of the action | Baseline study report, project proposal, Research paper, Media coverage Report, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes , Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
Output : 3 ( Result): Communities, CBOs, and CSOs hold LAs and interest groups accountable on existing laws and policies relating to SDGs
3.1) Percentage of target CBOs/CSOs that demonstrate capacity to implement SAcc tools adequately |  | 3.1) Respondents were yet to receive training on SAcc tool |  |  | 3.1) 70% of target CBOs/CSOs demonstrate capacity to implement SAcc tools adequately by year 3 of the action ( 228 CBO) |  | 3.1) 70% of target CBOs/CSOs demonstrate capacity to implement SAcc tools adequately | Baseline study report, project proposal, , Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes, Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
3.2) Number of target districts with data collection and analysis processes in place, as per SAcc tools | Data collection and analysis processes: Social audit data will be collected and analysis will be taken place on different services on targeting, delivery, gaps, malpractice, satisfaction of the recipients and limitation of the services providers. | Respondents were yet to receive training on SAcc tool |  | 3.2) At least 10 target districts with data collection and analysis processes in place, as per SAcc tools, by year 2 of the action |  |  | 3.2) At least 10 target districts with data collection and analysis processes in place, as per SAcc tools | Baseline study report, project proposal, , Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, data based, ToR, Project actors | Review data based, Key Informant interview, FGD, Observation, workshop, meeting . | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
3.3) Number of dialogues organized between /CSOs, government and interests groups for citizen oversight of SDG and NFYP related policies | Citizen oversight: Is monitoring of SDG and NFYP related policy and action | 3.3) No meeting organized |  | 3.3) 10 dialogues organized between /CSOs, government and interests groups for citizen oversight of SDG and NFYP related policies | 3.3) 10 dialogues organized between /CSOs, government and interests groups for citizen oversight of SDG and NFYP related policies | 3.3) 6 dialogues organized between /CSOs, government and interests groups for citizen oversight of SDG and NFYP related policies | 3.3) 26 dialogues organized between /CSOs, government and interests groups for citizen oversight of SDG and NFYP related policies by end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes, Project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
3.4) Number of CBO members and CSO representatives engaged in oversight of relevant policies and programs relating to SDGs and NFYP | Citizen oversight: Is monitoring of SDG and NFYP related policy and action | 3.4) A total 18.5% CBO and CSO representatives engaged in oversight of relevant policies and programs relating to SDGs and NFYP |  | 3.4) 25,000 CBO members and 162 CSO representatives engaged in oversight of relevant policies and programs relating to SDGs and NFYP by end of the action | 3.4) 25,000 CBO members and 163 CSO representatives engaged in oversight of relevant policies and programs relating to SDGs and NFYP by end of the action |  | 3.4) 50,000 CBO members and 325 CSO representatives engaged in oversight of relevant policies and programs relating to SDGs and NFYP by end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes, project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
3.5) Number of media briefings held at national and local level on violations of laws and policies. |  | 3.5) 0 media briefings held at national and local level on violations of laws and policies. |  | 3.5) At least 10 media briefings held at national and local level on violations of laws and policies | 3.5) At least 10 media briefings held at national and local level on violations of laws and policies | 3.5) At least 6 media briefings held at national and local level on violations of laws and policies | 3.5) At least 26 media briefings held at national and local level on violations of laws and policies by end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes, project actors | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
Output -4:( Short term result): Relevance and effectiveness of SDG framework is enhanced through contextualization at local, national and global levels
4.1) Number of research reports on local contextualization of SDG targets published on international peer-reviewed journals |  | 4.1) No research conducted on local contextualization of SDG targets |  | 4.1) Around 2 research conducted on local contextualization of SDG targets |  |  | 4.1) 2 research reports published on peer-reviewed journals by the end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
4.2) Number of reports published by the Citizen's Platform for SDGs as per SDG Tracking tool | Citizen platform : It is SDG implementation platform | 4.2) No SDG tracking tool developed |  | 4.2) 2 Reports published by the Citizen's Platform for SDGs as per SDG Tracking tool by the end of the action |  |  | 4.2) 2 Reports published by the Citizen's Platform for SDGs as per SDG Tracking tool by the end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
4.3) Number of national platforms where the project´s documentation of good practices have been disseminated | Documentation of good practices: To document significant changes of the project intervention | 4.3) 0 national platforms |  | 4.3) At least 1 national platforms where the project´s documentation of good practices have been disseminated | 4.3) At least 2 national platforms where the project´s documentation of good practices have been disseminated | 4.3) At least 2 national platforms where the project´s documentation of good practices have been disseminated | 4.3) At least 5 national platforms where the project´s documentation of good practices have been disseminated by the end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
4.4) Number of Global CSO dialogues and platforms where the project´s documentation of good practices have been disseminated |  | 4.4) No dialogues conducted |  | 4.4 ) At least 2 Global CSO dialogues and platforms where the project´s documentation of good practices have been disseminated | 4.4 ) At least 1 Global CSO dialogues and platforms where the project´s documentation of good practices have been disseminated |  | 4.4 ) At least 3 Global CSO dialogues and platforms where the project´s documentation of good practices have been disseminated by the end of the action | Baseline study report, project proposal, Periodic evaluation report/ result monitoring report, quarterly report, interim report, donor report, monthly cumulative report, case study report, minutes | Checklist, Questionnaire, Survey, Key Informant interview, FGD, Observation, workshop, meeting and Case study. | Six monthly, Yearly, Mid term and Final Quarter of the Project Period | MEAL team of Oxfam, External Evaluator, Project M&E staff | MEAL team of Oxfam, External Evaluator, Project M&E staff | Impact and Effectiveness
Activity Activity
Activity : under Ouput:1 (Result) : CBOs and CSOs have enhanced organizational and influencing capacity to work with local authorities (LAs) to address government commitments on SDGs and the National Five Year Plan (NFYP).
1) Module development and Training of Trainers (TOT) of project staff on SDG-linked policies and programs |  | Module yet to develop | Module development and Training of Trainers (TOT) of project staff |  |  |  | Module development and Training of Trainers (TOT) of project staff | Monthly and Quarterly Report, Module, Minutes, picture, Attendance shit | Document Review | Quarterly ( Q-3,4) of the 1st year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
2) Orient CBOs, CSOs, LAs and media on SDG-linked policies and programs |  | None of them got orientation | Orient CBOs, CSOs, LAs and media on SDG-linked policies and programs |  |  |  | Orient CBOs, CSOs, LAs and media on SDG-linked policies and programs | Monthly and Quarterly Report, Module, Minutes, picture, Attendance shit | Document Review, Observation, Checklist, Key Informant interview, FGD, Observation . | Quarterly ( Q-3,4) of the 1st year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
3) Development of SAcc tools |  | No social Accountibility tools in place | Development of SAcc tools |  |  |  | Development of SAcc tools | Monthly and Quarterly Report, Project Proposal, SA tools related documents | Document Review | Quarterly ( Q-3) of the 1st year | Project M&E Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
4) Module development on social accountability, public finance management and TOT for project staff |  | Module yet to develop | Module development on social accountability, public finance management and TOT for project staff |  |  |  | Module development on social accountability, public finance management and TOT for project staff | Monthly and Quarterly Report, Module, Minutes, picture, Attendance shit | Document Review | Quarterly ( Q-3,4) of the 1st year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
5) CBO training on social accountability and public finance management |  | None of them got training on SA | CBO training on social accountability and public finance management in 3 district | CBO training on social accountability and public finance management in 10 district |  |  | CBO training on social accountability and public finance management in 13 districts | Monthly and Quarterly Report, Module, Minutes, picture, Attendance shit | Document Review, Observation, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-3,4) of the 1st year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
6) Develop and incentivize Community Volunteers |  | 0 Volunteer developed | A total of 13 Community Volunteers are developed and incentivized | A total of 13 Community Volunteers are developed and incentivized | A total of 13 Community Volunteers are developed and incentivized | A total of 13 Community Volunteers are developed and incentivized | A total of 13 Community Volunteers are developed and incentivized | Monthly and Quarterly Report, ToR, Minutes, Attendance shit | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-3,4) of the 1st year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
7) CBOs, CSOs form and join district/national networks |  | CBOs and CSOs are existed, but they never been join any join district/national networks | 325 CBOs and 300 CSOs formed | 325 CBOs and 300 CSOs formed and join district/national networks | 325 CBOs and 300 CSOs formed and join district/national networks |  | 325 CBOs and 300 CSOs formed and join district/national networks | Monthly and Quarterly Report, Minutes, Attendance shit | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-2, 3,4) of the 1st year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
8) Form district level networks |  | No district level networks |  | Formed 13 district level networks |  |  | Formed 13 district level networks | Monthly and Quarterly Report, Minutes, Attendance shit | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-2 ) of the 2nd year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
9) Link networks with national SDG platform |  | No networks with national SDG platform |  | Link networks with national SDG platform |  |  | Linked networks with national SDG platform | Monthly and Quarterly Report, Minutes, Attendance shit | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-2 ) of the 2nd year | Project Staff, Oxfam staff | CPD, Project M&E Staff, Oxfam staff | Relevancy and Efficiency
10) Annual CBO/CSO conference |  | No annual CBO/CSO conference held |  | 1 Annual CBO/CSO conference | 1 Annual CBO/CSO conference |  | 2 Annual CBO/CSO conference | Monthly and Quarterly Report, Minutes, Attendance shit | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-4 in 2nd year and Q-4 in 3rd year of the project priod ) | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
Activity under Output /Result- 2: CBOs and CSOs support LAs to effectively deliver people-centred services as per existing laws and policies relating to SDGs.
1) Research on service delivery effectiveness |  | No related research conducted | 1) Research on service delivery effectiveness | 1) Research on service delivery effectiveness | 1) Research on service delivery effectiveness |  | Research on service delivery effectiveness | Monthly and Quarterly Report, Theory of change, ToR, Research Report | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( 1st year - ( Q1,2), 2nd year - Q-4 in, 3rd year - Q-1,2) | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
2) CBOs organize community consultations with LAs on policy implementation |  | 0 Consultation | CBOs organize community consultations with LAs on policy implementation | CBOs organize community consultations with LAs on policy implementation | 2) CBOs organize community consultations with LAs on policy implementation | CBOs organize community consultations with LAs on policy implementation | CBOs organize community consultations with LAs on policy implementation | Monthly and Quarterly Report, Minutes, Attendance shit | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff | Project Staff, Oxfam staff | Relevancy and Efficiency
3) Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level |  | 0 olicy dialogues to develop | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Monthly and Quarterly Report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
4) Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level |  | 0 Policy dialogues to develop | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Policy dialogues to develop joint action mechanisms involving CBOs, CSOs and LAs at subnational level | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
5) Policy dialogues between CBOs, CSOs and LAs to influence effective delivery of people-centred services at national level |  | 0 Policy dialogues to develop |  | Policy dialogues between CBOs, CSOs and LAs to influence effective delivery of people-centred services at national level | Policy dialogues between CBOs, CSOs and LAs to influence effective delivery of people-centred services at national level | Policy dialogues between CBOs, CSOs and LAs to influence effective delivery of people-centred services at national level | Policy dialogues between CBOs, CSOs and LAs to influence effective delivery of people-centred services at national level | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
6) Media mobilization to popularize SDG policies, targets and best practices |  | 0 Media mobilization | 6) Media mobilization to popularize SDG policies, targets and best practices | 6) Media mobilization to popularize SDG policies, targets and best practices | 6) Media mobilization to popularize SDG policies, targets and best practices | 6) Media mobilization to popularize SDG policies, targets and best practices | 6) Media mobilization to popularize SDG policies, targets and best practices | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff (CPD), Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
Activity under output / Result 3: Communities, CBOs, and CSOs hold LAs and interest groups accountable on existing laws and policies relating to SDGs.
1) Data collection to facilitate citizen-led oversight |  | Data is not available |  | Data collection to facilitate citizen-led oversight | Data collection to facilitate citizen-led oversight | Data collection to facilitate citizen-led oversight | Data collection to facilitate citizen-led oversight | Monthly and Quarterly Report, Six monthly report, Annual report, databased, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff , CBO | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
2) Dialogue between CBOs/CSOs, government and interests groups at local levels |  | No Dialogue held between CBOs/CSOs, government and interests groups at local levels yet |  | 2) Dialogue between CBOs/CSOs, government and interests groups at local levels | 2) Dialogue between CBOs/CSOs, government and interests groups at local levels | 2) Dialogue between CBOs/CSOs, government and interests groups at local levels | 2) Dialogue between CBOs/CSOs, government and interests groups at local levels | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
3) CBO/CSO-led media briefings/press conferences and popular mobilization on violations of relevant laws and policies. |  | No media briefings/press conference |  | 3) CBO/CSO-led media briefings/press conferences and popular mobilization on violations of relevant laws and policies. | 3) CBO/CSO-led media briefings/press conferences and popular mobilization on violations of relevant laws and policies. | 3) CBO/CSO-led media briefings/press conferences and popular mobilization on violations of relevant laws and policies. | 3) CBO/CSO-led media briefings/press conferences and popular mobilization on violations of relevant laws and policies. | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly | Project Staff, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
Activity under Output /Result 4: Relevance and effectiveness of SDG framework is enhanced through contextualization at local, national and global levels.
1) Research to contextualize SDG targets at local and national levels. |  | No Research to contextualize SDG targets at local and national levels | 1) Research to contextualize SDG targets at local and national levels. |  |  |  | 1) Research to contextualize SDG targets at local and national levels. | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-3,4) of the 1st year | Project Staff (CPD), Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
2)Dialogues to discuss research and implications of SDG targets and policies |  | No Research conducted | Dialogues to discuss research and implications of SDG targets and policies |  | Dialogues to discuss research and implications of SDG targets and policies | Dialogues to discuss research and implications of SDG targets and policies | Dialogues to discuss research and implications of SDG targets and policies | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-3,4) of the 1st year | Project Staff (CPD), Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
3) Development and application of SDG tracking tool. |  | No SDG tracking tool developed | 3) Development and application of SDG tracking tool. |  |  |  | 3) Development and application of SDG tracking tool. | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-3,4) of the 1st year | Project Staff (CPD), CBO, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
4) Participation in/organization of global CSO dialogue to exchange experiences |  | No one participated | 4) Participation in/organization of global CSO dialogue to exchange experiences |  |  |  | 4) Participation in/organization of global CSO dialogue to exchange experiences | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-1,2) of the 1st year | Project Staff (CPD), CBO, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
5) Documentary on effective service delivery through CBO, CSO and LA joint action |  | NO Documentary developed |  | 5) Documentary on effective service delivery through CBO, CSO and LA joint action |  |  | 5) Documentary on effective service delivery through CBO, CSO and LA joint action | Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( Q-3,4) of the 2nd year | Project Staff Oxfam staff | Project Staff, Oxfam staff | Relevancy and Efficiency
6) Documentation of practices and compilation of a resource document |  | 0 |  | Documentation of practices and compilation of a resource document | Documentation of practices and compilation of a resource document | Documentation of practices and compilation of a resource document | Documentation of practices and compilation of a resource document | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( from 2nd year) | Project Staff, CBO, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
7) Dissemination of resource document on oversight practices |  | 0 |  | 7) Dissemination of resource document on oversight practices | 7) Dissemination of resource document on oversight practices | 7) Dissemination of resource document on oversight practices | 7) Dissemination of resource document on oversight practices | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( from 2nd year) | Project Staff, CBO, Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
8) Participation in/organization of global CSO dialogue to exchange experiences |  | 0 |  | 8) Participation in/organization of global CSO dialogue to exchange experiences | 8) Participation in/organization of global CSO dialogue to exchange experiences | 8) Participation in/organization of global CSO dialogue to exchange experiences | 8) Participation in/organization of global CSO dialogue to exchange experiences | Monthly and Quarterly Report, Six monthly report, Annual report, Theority of change report, Minutes, Attendance shit, proposal | Document Review, Checklist, Key Informant interview, FGD, Observation. | Quarterly ( from 2nd year) | Project Staff (CPD), Oxfam staff | Project M&E Staff, Oxfam staff | Relevancy and Efficiency
PCM Analysis
The project monitoring people has scope to follow PCM analysis including relevancy, efficiency, effectiveness, impact and sustainability during monitoring. The key questions on regarding areas are given below :-
Relevancy analysis ( At activity level) : Are the services relevant to the beneficiaries. |  Does the project presently response to the needs of the targeted group?  Do all key stakeholders still demonstrate effective commitment  Is the Stakeholders being relevant the project objectives?  Is there effective coordination system at local, district and national level including Community people, CBO,CSO, partner and donor?  Are the suitable and informative OVI /targeted  Are the activities, output and outcome planned appropriate to achieve the goal.  Are there any risk and assumption holding true?  Have key stakeholders been involved in the designing process  Have the relevant cross cutting issues been adequate by mainstream in the project designing?  Does a logframe or similar tool exist? If yes, what is its present quality (does it clearly show how activities will achieve results and impact)? If not, why not?  Are the OO, PP and results clear and logical, and do they address clearly identified needs?  Is the PP achievable in the project framework?
Efficiency Analysis: Does the project Use it resources wisely |  What degree are inputs provided available on time to implement?  Are the inputs monitored regularly to encourage cost effective implementation? By whom are they monitor?  Project resources managed in transparent and accountable manner?  Is the logframe or similar tool used as a management tool? If not, why not?  Is an activity schedule (or work plan) and resource schedule available and used by the project management?  To what extent are activities implemented as scheduled? If there are delays how can they be rectified?  How well are activities monitored by the project and are corrective measures taken if required?  Have all planned outputs been delivered to date? And in a logic sequence?  What is the quality of outputs to date?  Are the outputs achieved likely to contribute to the intended results? Are they correctly reflected through the OVIs/targets?
Effectiveness: Has the project achieved its stated objectives? Using result for improving the project |  Have the planned results to date been achieved?  What is the quality of the results/services available?  Have all planned target groups access to / using project results available so far?  Are there any factors which prevent target groups accessing the results/services?  To what extent has the project adapted or is able to adapt to changing external conditions (risks and assumptions) in order to ensure benefits for the target groups?  If any unplanned negative effects on target groups occurred, or are likely to occur through the project, to what extent did the project management take appropriate measures?  To what extent are unplanned positive effects contributing to results produced / services provided?
Impact : Have people's lives changes as a result of the project? Analyzing collecting information |  What are the direct impact prospects of the project at Overall Objectives level? What, if any impacts are already apparent? What impacts appear likely? Are the current OVIs/targets realistic and are they likely to be met? Are any external factors likely to jeopardise the project’s direct impact?  To what extent does/will the project have any indirect positive and/or negative impacts? (i.e. environmental, social, cultural, gender and economic). Have there been/ will there be any unplanned positive impacts on the planned target groups or other non-targeted communities arising from the project? How did this affect the impact? Did the project take timely measures for mitigating the unplanned negative impacts? What was the result?
Sustainability: Will the project activities continue after with drawl it external supports? Collecting the information |  Financial / economic Sustainability  Institutional Sustainability  Environmental Sustainability  What is the level of ownership of the project by target groups and will it continue after the end of external support?  What is the level of policy support provided and the degree of interaction between project and policy level?  How well is the project contributing to institutional and management capacity?

## Sheet3
227.5
153.8462
162.5

## Sheet2
72.7273