## SRDW LM Revised
Ultimate Outcome | 1000 | Increased well-being for women domestic workers (DW) in Dhaka, Bangladesh
|  | ↑ |  |  |  | ↑
Intermediate Outcome | 1100 | Strengthened agency of women domestic workers to claim and defend their rights in relation to decent employement |  |  | 1200 | Improved social norms on DW rights, including increased recognition of DW as formal profession, promoted by policy makers, government and employers and the wider society
|  | ↑ |  | ↑ |  | ↑ |  | ↑
Immediate Outcome | 1110 | Improved accredited professional skills and competencies and formal placement enable women Domestic Workers to claim and defend their rights. | 1120 | Improved ability of Domestic Worker Groups (DWG) to provide services for women DW and advocate for their rights to live free from violence | 1210 | Strengthened capacity of civil society to develop and implement joint action plan and influence the government for the recognition of DW as formal profession. | 1220 | Improved positive attitudes and support of policy makers, employers and the wider society towards women domestic workers’ rights and entitlement
|  | ↑ |  | ↑ |  | ↑ |  | ↑
Outputs | 1111 | Business plan developed and implemented for skilled DW placement initiative | 1121 | National Domestic Workers network strengthened including exisitng groups/networks | 1211 | Establish and functional Consultative Forum involving government, civil society organizations and DWGs/DWN | 1221 | Campaign/advocacy strategy with key project stakeholders implemented on women DW rights and entitlements, including the right to live free from violence
| 1112 | Gender-sensitive competency based standards using rights-based multi-module training programme for domestic workers approved by Bangladesh Technical Education Board (BTEB) | 1122 | Women domestic workers and DWGs trained on life skills, leadership and rights, including the right to live free from violence | 1212 | Technical assistance provided to partners and key stakeholders on knowledge generation on DW rights, decent work and intersection with GBV | 1222 | Edu-tainment and other social media and marketing materials implemented for advocacy/campaigns on DW rights, including the right to live free from violence with policy makers, schools and wider community
| 1113 | Women domestic workers trained and accredited | 1123 | Technical/financial assistance provided to build capacity of support service providers | 1213 | National Plan of Action on the adoption and implementation of the Domestic Worker Protection and Welfare Policy developed and disseminated | 1223 | Mass and Social Media campaigns implemented on DW right, including the right to live free from violence
|  |  | 1124 | Technical/financial assistance provided for project partners based on capacity building action plan
Establish and functional Consultative Forum involving government, civil society organizations and DWGs/DWN

## SRDW OAM (Not finalized)
REVISED OUTPUTS FROM PROPOSAL |  |  | REVISIONS FROM OxBD ON OUTPUTS
Immediate Outcome | 1110 | Improved accredited professional skills and competencies and formal placement enable women Domestic Workers to claim and defend their rights.
Output | 1111 | Business plan developed and implemented for DW placement initiative
Activity | 1111.1 | Conduct scoping study, including mapping of private sector actors in the DW sector to develop business model
Activity | 1111.2 | Develop and implement business model with private sector companies for trained DW placement
Activity | 1111.3 | Link/match trained DW with private sector companies
Output | 1112 | Gender-sensitive competency based standards using rights-based multi-module training programme for domestic workers approved by Bangladesh Technical Education Board (BTEB)
Activity | 1112.1 | Workshops with BTEB and other stakeholders to set competency standards
Activity | 1112.2 | Design, testing and adoption of standards
Activity | 1112.3 | Develop, validate and adopt training programs
Activity | 1112.4 | Develop training package and materials (DWG: Rights & Life Skills; DWN: Organizational Development)
Output | 1113 | Women domestic workers trained and accredited
Activity | 1113.1 | Registration of RTOs (Registraion fees from BTEB)
Activity | 1113.2 | Hire trainers/instructors/training center managers, etc.
Activity | 1113.3 | Conduct vocational training with women domestic workers
Activity | 1113.5 | Conduct testing and certification
Immediate Outcome | 1120 | Improved ability of Domestic Worker Groups (DWG) to provide services for women DW and advocate for their rights to live free from violence
Output | 1121 | National Domestic Workers network strengthened including exisitng groups/networks
Activity | 1121.1 | Mapping of exisiting DW groups/networks
Activity | 1121.2 | Recruit and train social mobilizers
Activity | 1121.3 | Social mobilizers facilitate the establishment of new DW community groups as needed
Activity | 1121.4 | National Domestic Workers network strengthened including exisitng groups/networks
Activity | 1121.5 | Meeting with community leaders, different levels of government conducted by DWGs and Network to advocae for DW rights
Activity | 1121.6 | Communication/engagement material on DWs' issues and rights developed and distributed
Output | 1122 | Women domestic workers and DWGs trained on life skills, leadership and rights, including the right to live free from violence
Activity | 1122.1 | Development of education/training modules on life-skills, participation and leadership, rights, GBV
Activity | 1122.2 | Life skill and rights training for women domestic workers and DWG members
Activity | 1122.3 | Capacity building activities conducted to mobilize community support/Community mobilization to ensure DW rights.
Output | 1123 | Technical/financial assistance provided to build capacity of support service providers
Activity | 1123.1 | Mapping of existing support services (including support services for children who have experienced violence)
Activity | 1123.2 | Conduct awareness-raising sessions with DWG and DWN on support services
Activity | 1123.3 | Provide technical/financial assistance to support service providers on service delivery
Activity | 1123.4 | Formation of Apex body of DWGs & quarterly linkage meetings
Output | 1124 | Technical/financial assistance provided for project partners based on capacity building action plan
Activity | 1124.1 | Undertake capacity assessment of partner organisations Oxfam's capacity assessment tool for gender just organizations
Activity | 1124.2 | Develop awareness raising and training material on GBV and support services available
Activity | 1124.3 | Support partners to build their capacities based on CAT action plan including GBV support and prevention training
Immediate Outcome | 1210 | Strengthened capacity of civil society to develop and implement joint action plan and influence the government for the recognition of DW as formal profession.
Output | 1211 | Consultative Forum established in Dhaka with government, civil society organizations and DWGs/DWN | Consultative Forum established and operational in Dhaka……………………
Activity | 1211.1 | Formation and regular meetings of the Consultative Forum
Activity | 1211.2 | Conduct meetings/dialogues between Forum and with policy makers, Local govt., local administration and other stakeholders
Activity | 1211.3 | Lobby and arrange Inter-Ministerial and multi-stakeholders meetings related to Policy Implementation
Activity | 1211.4 | Arrange National Conference on Domestic Workers' Rights and a National Convention of Domestic Workers
Activity | 1211.5 | Document and publish research reports and awareness raising tools (journals, bulletins, booklets, posters, leaflets, etc.) on the DW Policy
Output | 1212 | Technical assistance provided to partners and key stakeholders on knowledge generation on DW rights, decent work and intersection with GBV
Activity | 1212.1 | Undertake baseline and project evaluations
Activity | 1212.2 | Consultative forum to conduct regional research on DW and protected workers' rights
Activity | 1212.3 | Conduct research on priroity issues related to decent work and how VAWG/GBV is addressed
Activity | 1212.4 | Produce policy brief and associated materials/position paper with recommendations on how to address GBV in DW sector in Bangladesh
Output | 1213 | National Plan of Action on the adoption and implementation of the Domestic Worker Protection and Welfare Policy developed and disseminated
Activity | 1213.1 | Convene a Policy Implemention Committee (PIC) to develop National Action Plan on the adoption of the Domestic Worker Protection and Welfare Policy
Activity | 1213.2 | Local and regional exchanges to learn about best practices around implementation of Domestic Worker Protection and Welfare policy or other similar policies
Activity | 1213.3 | Workshops to develop the National Action Plan to adopt and implement the Policy
Activity | 1213.4 | Establish and implement joint accountability mechanism to monitor the implementtion of the National Action Plan
Immediate Outcome | 1220 | Improved positive attitudes and support of policy makers, employers and the wider society towards women domestic workers’ rights and entitlement
Output | 1221 | Campaign/advocacy strategy with key project stakeholders implemented on women DW rights and entitlements, including the right to live free from violence
Activity | 1221.1 | Convene multi-stakeholder workshops to identify key stakeholders to engage in campaign and advocacy strategy
Activity | 1221.2 | Develop and implement communications/advocacy strategy
Activity | 1221.3 | Develop and implement mechanisms to jointly monitor implementation of campaign and advocacy strategy
Output | 1222 | Edu-tainment and other social media and marketing materials implemented for advocacy/campaigns on DW rights, including the right to live free from violence with policy makers, schools and wider community
Activity | 1222.1 | Develop best practice materials on positive gender attitudes/norms/behaviour change strategies/approaches
Activity | 1222.2 | Develop and distribute media and educational materials that promote positive ANB (attitude, norms and behabiour)
Activity | 1222.3 | Conduct awareness-raising sessions with policy makers and employers based on educational materials produced
Activity | 1222.4 | Develop 3-part video documentary on DW situation and vulnerability to GBV and disseminate via local TV, social media and schools etc.
Output | 1223 | Media campaigns designed and implemented on DW right, including the right to live free from violence
Activity | 1223.1 | Convene stakeholder workshop to design media change campaign
Activity | 1223.2 | Identify and engage "Campaign Ambassadors"
Activity | 1223.3 | Develop and implement tv, radio or social media materials on Domestic Workers' issues and rights, to promote domestic work as dignified employment
Activity | 1223.4 | Organize awareness-raising events on domestic workers' rights during key days (8 March - International women's Day; 1 May - May Day; 16 June - International Domestic Workers Day; 29 November - Day for the elimination of VAWG; 10 December - International Human Rights Day)
Note on C39: Farhana Ahmed: Consultative

## SRDW PMF
Expected Result |  | Indicator (Proposed by OXFAM Canada) |  | FEEDBACK FROM OxBD ON OUTCOME INDICATORS | Baseline | Targets |  |  |  | Data Sources | Data Collection Method | Frequency | Responsibility
[6 empty] | Year 1 | Year 2 | Year 3 | Year 4
Ultimate Outcome
1000 | Increased well-being for women domestic workers (DW) in Dhaka, Bangladesh | 1000.1 | %/total women domestic worker reporting job satisfaction | This will be determined based on 2-5 indicative questions in relation to job satisfaction that is in line with Bangladesh National Domoestic Worker Protection and Welfare Policy and any additional criteria idenified by the Domestic Worker Network | [5 empty] | Women domestic workers who are employed at the time of evaluation | Survey, focus groups | Baseline and final evaluation | OCA, Oxfam in Bangladesh and Partners
|  | 1000.2 | Perspectives of women domestic workers on workplace environment | This will be determined based on a 2-5 indicative questions in relation to essential workplace environment that is in line with Bangladesh National Domoestic Worker Protection and Welfare Policy and any additional criteria idenified by the Domestic Worker Network | [5 empty] | Women domestic workers who are employed at the time of evaluation | Survey, focus groups | Baseline and final evaluation | OCA, Oxfam in Bangladesh and Partners
Intermediate Outcome
1100 | Strengthened agency of women domestic workers to claim and defend their rights in relation to decent employment. | 1100.1 | Number of actions taken by women domestic workers or domestic workers groups to claim their rights | Number of domestic workers seeking redress or reporting abuse such as sexual harassment, nonpayment of wages to appropriate authorities and legal aid service providers | [5 empty] | Women domestic workers and domestic worker groups | Analysis of record, interviews, | Baseline and end of project | OCA, Oxfam in Bangladesh and Partners
|  | 1100.2 | Level of confidence of women domestic workers on their ability to advocate of their rights | Use of agency and soft skills reported by domestic workers | [5 empty] | Direct and indirect beneficiaries, intermediaries and key stakeholders | Surveys, focus groups | Baseline and end of project | OCA, Oxfam in Bangladesh and Partners
1200 | Improved social norms on DW rights, including increased recognition of DW as formal profession promoted by policy makers, government and employers and the wider society | 1200.1 | %/total of policy makers, employers and wider soceity recognizing domestic work as decent work/ formal work | %/total of policy makers, employers and wider society recognizing domestic work as formal work | [5 empty] | Policy makers, employers and wider society | Surveys, interviews | Baseline and end of project | OCA, Oxfam in Bangladesh and Partners
|  | 1200.2 | Perspectives of wider soceity (disaggregated by age/sex) on domestic worker rights and entitlements | Average score of stakeholders and service providers on an index for social norms with regards to domestic work | [5 empty] | Wider soceity | Surveys, focus groups | Baseline and end of project | OCA, Oxfam in Bangladesh and Partners
Immediate Outcome
1110 | Improved accredited professional skills and competencies and formal placement enable women Domestic Workers to claim and defend their rights. | 1110.1 | Number of accredited women domestic workers linked for employment placement | Number of accredited women domestic workers linked for employment placement | [5 empty] | Women domestic workers accredited through BTEB | Analysis of records, focus group | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
|  | 1110.2 | Perception of women domestic workers on the quality of vocational education provided through BTEB | Perception / level of satisfaction of women domestic workers on the quality of vocational education and life skils training provided through partners. | [5 empty] | Women domestic workers enrolled in vocational training and other training programmes | Survey, focus groups | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
1120 | Improved ability of Domestic Worker Groups (DWG) to provide services/support for DW and advocate for their rights to live free from violence | 1120.1 | %/total of women domestic workers reporting on improved knowledge and capacity on their rights, especially the right to live free from violence | %/Number of women domestic workers reporting on improved knowledge and capacity on their rights, especially the right to live free from violence | [5 empty] | Women domestic workers assciated with domestic worker groups | Survey, interviews | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
|  | 1120.2 | Ability of project partners to support domestic workers groups to access support services | Level of organizational capacity of DWG to provide comprehensive services for women DW | [5 empty] | Partners, domectic worker groups | Capacity Assessment workshop for project partners (Year 1 and 4), focus groups (Year 2,3,& 4) | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
1210 | Strengthened capacity of civil society to develop and implement joint action plan and influence the government for the recognition of DW as formal profession. | 1210.1 | %/total of civil society (disaggegated by age/sex) reporting on improved capacity of advocate for domestic workers rights and entitlements | Number of joint action plans implemented by civil society for domestic worker's rights and entitlements | [5 empty] | Civil society activisits directed reached through project activities | Survey, focus group | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
|  | 1210.2 | Perception of policy makers (disaggegated by age, sex) on domestic worker rights and entitlements | Level of capacity of civil society to develop and implement joint action plan and influence govt for the recognition of DW as formal profession | [5 empty] | Civil society engaged through project activities | Survey, interviews | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
1220 | Improved positive attitudes and support of policy makers, employers and the wider society towards women domestic workers’ rights and entitlement | 1220.1 | Attitudes of policy makers, employers, and wider society (disaggregated by age/sex) on women domestic worker rights and entitlements | %/total number of policy makers, employers and wider society (disaggregated by age/sex) reporting on improved knowledge of domestic wokers rights | [5 empty] | Policy makers, employers and wider society | Survey, focus group, interviews | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
|  | 1220.2 | %/total number of employers and wider society (disaggregated by age/sex) reporting on improved knowledge of domestic wokers rights | Attitudes of policy makers, employers, and wider society (disaggregated by age/sex) on women domestic worker rights and entitlements | [5 empty] | Policy makers, wider society & employers | Survey, focus group, interviews | Baseline and Annually starting Year 2 | Oxfam in Bangladesh and Partners
Outputs
1111 | Business plan developed and implemented for skilled DW placement initiative | 1111.1 | Number of private sector companies implementing business plan for DW placement | FEEDBACK will be given given after completion of the Baseline Study | [5 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1112 | Gender-sensitive competency based standards using rights-based multi-module training programme for domestic workers approved by Bangladesh Technical Education Board (BTEB) | 1112.1 | Number of gender-sensitive competency-based training programmes implemented by BTEB | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1113 | Women domestic workers trained and accredited | 1113.1 | Number of vocational trainings conducted for domestic workers | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
|  | 1113.2 | Number of domestic workers trained and accredited | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1121 | National Domestic Workers network strengthened including exisitng groups/networks | 1121.1 | Number of new or exisiting domestic workers groups strengthened | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
|  | 1121.2 | Number of meetings conducted by DWG with community leaders and duty-bearers | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1122 | Women domestic workers and DWGs trained on life skills, leadership and rights, including the right to live free from violence | 1122.1 | Number of workshops conducted with women domestic workers and DWG on life skills, leadership and rights including the right to live free from violence | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
|  | 1122.2 | Number of women domestic workers trained on life skills, leadership and rights, including the right to live free from violence | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1123 | Technical/financial assistance provided to build capacity of support service providers | 1123.1 | Number of support service providers supported on human-rights based approached to service delivery | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1124 | Technical/financial assistance provided for project partners based on capacity building action plan | 1124.1 | Number of project partners supported in implementing their capacity building action plan | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1211 | Establish and functional Consultative Forum involving government, civil society organizations and DWGs/DWN | 1211.1 | Number of advocacy/lobby meetings or dialogues organized between key government and non-governmental stakeholders | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
|  | 1211.2 | Number of national conferences/conventions implemented domestic workers rights | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1212 | Technical assistance provided to partners and key stakeholders on knowledge generation on DW rights, decent work and intersection with GBV | 1212.1 | Number of knowledge products created and disseminated on DW rights, decent work and intersection with GBV | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1213 | National Plan of Action on the adoption and implementation of the Domestic Worker Protection and Welfare Policy developed and disseminated | 1213.1 | Number of workshops/learning exchanges conducted for the development of the National Action Plan on the implementation of the Domestic Worker Protection and Welfare Policy | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1221 | Campaign/advocacy strategy with key project stakeholders implemented on women DW rights and entitlements, including the right to live free from violence | 1221.1 | Number of campaign/advocacy strategy implemented on women DW rights and entitlements, including the right to live free from violence | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1222 | Edu-tainment and other social media and marketing materials implemented for advocacy/campaigns on DW rights, including the right to live free from violence with policy makers, schools and wider community | 1222.1 | Number of edu-tainment and social media modules implemented with policy makers, schools and wider community that promote positive attitudes, norms and behaviors around domestic workers rights, especially the right to live free from violence | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
|  | 1222.2 | Number of people (age/sex disaggregated) reached through edu-tainment and social media modules implemented on domestic worker rights, especially the right to live free from violence | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
1223 | Mass and Social Media campaigns implemented on DW right, including the right to live free from violence | 1223.1 | Number of media campaigns implemented on domestic worker rights to promote domestic work as decent work with wider community | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners
|  | 1223.2 | Number of people (age/sex dissaggregated) reached through campaign on DW rights to promote domestic work as decent work | [6 empty] | Project records, documents | Analysis of records (or documents) | Semi-annual, starting Year 1 | Project Partners