Terms of Reference (ToR): Hiring a consultant for the Midterm Evaluation of “Shomotay Tarunno: Youth for Equality” project

1. About Plan International

Founded over 88 years ago, Plan International is one of the oldest and largest children's development organizations in the world. Plan International plays an important role in mobilizing children, communities, and civil society organizations to claim the rights of children, especially girls, and achieve agreed-upon local development priorities, towards a commitment to ensuring the well-being of children in support of the United Nations Convention on the Rights of the Child (UNCRC). Plan International works in over 80 countries to help create a world where we are all equal.

1.1 About Plan International Bangladesh

Plan Bangladesh’s vision is of a world in which all children realize their full potential in societies that respect people’s rights and dignity, with high-quality programs that deliver long-lasting benefits. Children are at the heart of everything we do.

Plan International has been operating in Bangladesh since 1993. Plan International Bangladesh’s Country Strategy 2020 – 2030, revised in 2024, is designed to support women and girls access quality education, skills, and decent work opportunities, empowering children and young people drive systemic change, enabling girls and young women realize their sexual and reproductive health, reducing all forms of gender- based violence, and strengthening resilience to the impacts of climate change through humanitarian assistance In doing so, Plan international Bangladesh will

•	Empower children and young people as drivers of systemic change to gender norms and power relationships;

•	Reduce gender-based violence and promote an enabling environment for children and youth in all their diversity to realize their sexual and reproductive health and live free from violence

•	Increase the resilience of vulnerable girls & young women to any shocks & stressors through prevention, preparedness, response & recovery

Plan International Bangladesh has its country office in Dhaka and has been implementing projects across Bangladesh since 2001. The organization has a strong presence in Cox’s Bazar district under Chittagong division since 2017. Along with our main office at Cox’s Bazar, we have one more field office at Ukhiya. As part of the current Disaster Preparedness Process (DPP) 4, Plan international Bangladesh supports both the Rohingya and host communities through different projects.

1.2 About JAAGO Foundation Trust

JAAGO Foundation Trust is a national non-government organisation in Bangladesh working to break the cycle of poverty through education, youth empowerment, gender equality and climate resilience. The organisation ensures that every child and young person, including girls and those with disabilities, has access to inclusive and quality learning opportunities. Together, these efforts reflect JAAGO Foundation Trust’s long-standing commitment to inclusion, equity and climate resilience. By integrating education, youth leadership, gender equality and community-based climate adaptation, the organisation supports vulnerable communities in building a sustainable and climate-resilient future for generations to come.

2. Project Details

2.1 Project Context

Shomotay Tarunno: Youth for Equality Project, funded by the Embassy of the Kingdom of the Netherlands (EKN), is implemented by a consortium of Plan International Bangladesh (PIB) and JAAGO Foundation Trust (JFT) from December 1, 2023 to November 30, 2027. The project aims to achieve the goal “Young people, in all their diversity especially Girls and Young Women (GYW), are able to live a life free of violence, voice their opinions, and resource their actions to challenge gender stereotypes”

This project objectives include: (a) Young people in all their diversity are equipped to combat gender stereotypes and increase positive social gender norms in society through enhanced inclusive, effective and meaningful engagement in decision making and activism. (b) Media organizations and outlets and influencers are more proactive and responsive to positive gender representation and produce gender sensitive content.  and (c) Improved legal frameworks and curriculum in place and strengthened commitment and accountability of duty bearers, media and education institutes to address harmful gender stereotypes

The project is  implemented in all 8 divisions in Bangladesh. As youth represent the fastest-growing segment of the population in Bangladesh, mobilizing their agency is highly imperative. This project recognizes that a sustained and comprehensive action at the individual, family, societal and national level is required. Hence, to transform power relations and to challenge gender stereotypes on all levels, we will resource and mobilize youth and youth-led organizations as key agents for collective action We are working with youths and youth led organizations so that young people in all their diversity are equipped to combat gender stereotypes and increase positive social gender norms in society through enhanced inclusive, effective and meaningful engagement in decision making and activism. We also working with the media (Print, online, broadcasting) entities, social media content creators, to enhance their sensitization and understanding to promote positive gender narratives in Bangladeshi media (traditional media & social media) and challenge harmful gender norms.

Additionally, we will work with private and public universities for promoting positive gender narratives and sensitize students & faculties from various departments—particularly those from Mass Communication and Journalism, members of the University Journalist Association (Sangbadik Somiti), and students engaged in online news portals—on the principles of gender-sensitive journalism, so they can apply these practices effectively as they enter the professional field. We want to create an appeal among faculty members—particularly in Mass Communication and Journalism— as they become sensitized on reviewing & initiate discussion on their existing curriculum, and integrating or revising content considering gender equality and gender-sensitive approach.

Furthermore, strategic partnerships with government ministries, departments, such as the Presss Institute Bangladesh under Ministry of Information and Broadcasting, Department of Youth Development under Ministry of Youth and Sports, Ministry of Women and Children Affairs, are being developed and strengthened to promote the reformation of laws, policies and regulations, as well as their budgeting and implementation, and to create their support for the project’s actions and creating a positive gender narrative in the society.

To achieve the goal the project will primarily work with three major stakeholders: 1) youth, youth led Organizations and; 2) media organizations, outlets and social media influencers and local content creators and 3) the government ministries, department and education institutes, including public and private universities.

2.1.1 Project Strategy

The strategy involves influencing power holders including media, community leaders, education institutes and duty bearers, strengthening their laws and policies, teaching skills and curricula, mobilizing young people and civil society and promoting positive attitudes, behaviours and practices from the individual, to the national and the global level. Our approach is aimed to be gender transformative, considering the following 6 elements which are embedded into our project interventions including 1) addressing gender norms throughout the life-course; 2) strengthening  girls and young women(GYW’s) agency; 3) advancing both the condition and position of girls, young women, and women; 4) working with boys, young men, and men to embrace gender equality and exercise positive and diverse masculinities; 5) responding to the needs and interests of girls and boys in all their diversity and 6) fostering an enabling environment for gender equality and girls’ rights.

The project is directly working with girls, boys, young women and men, Youth led organizations, families and communities, media houses and media professional, education institutes, public and private university and duty bearers to change the perception and norms about gender roles and images through collective action by youth agencies, as well as improving laws and policies, and curricula to eliminate gender stereotypes. The underlying assumption is that the reduction of gender stereotypes and masculine views and dominance in media, laws, and in education institutes, will empower youth in all their diversity including girls and young women and other minorities to gain equal rights, resources and representation.

The project, strategies and interventions are very much aligned with, and directly contribute to Sustainable Development Goal number 5, to end all forms of discrimination against women and girls everywhere. By advocating to block, amend or improve laws, policies and regulations that keep gender stereotypes in place, and by supporting countrywide youth-led capacity enhancement, campaigning and activism and media engagement to advocate for the positive and meaningful representation of youth including females and transform media narratives on gender transformation, this project aims to combat gender stereotypes in the society.

2.2 Project’s Overall Goal

Young people, in eight divisional districts in Bangladesh, in all their diversity [including girls and young women (GYW)], are able to live a life free of violence, voice their opinions, and resource their actions to challenge gender stereotypes in their communities, in the media and on a policy level.

2.3 Project’s Intended Objectives

The project’s intended objectives are as follows:

Objective 1: Young people in all their diversity are equipped to combat gender stereotypes and increase positive social gender norms in society through enhanced inclusive, effective and meaningful engagement in decision making and activism.

Objective 2: Media organizations and outlets and influencers are more proactive and responsive to positive gender representation and produce gender sensitive content.

Objective 3: Improved legal frameworks and curricula in place and strengthened commitment and accountability of duty bearers, media and education institutes to address harmful gender stereotypes

More details on the project’s Results Framework can be found in Annex 3.

2.4 Project’s Target Population and Location

Project location for the Midterm Study is in the 8 divisions (Dhaka, Photogram, Khulna, Rajshahi, Sylhet, Barishal, Mymensingh & Rangpur) of Bangladesh as implementation sites of the project.

The qualitative and quantitative data collection for this Midterm survey will require to cover among the national and local-level 316 numbers youth-led organizations, journalists of print, broadcast and online media, OTT Platforms, entertainment media personalities (actors and actress, film directors and producers), advertisement agencies, social media influencers, academic institutions, policy makers, relevant government officials of the ministries and non-government entities etc. reached through the projects.

Direct Project Participants: 13,515

Indirect Community Stakeholders: 4,000

Indirect Media & Advocacy Outreach: (±) 2 million people

- 12,690 youth of age 15 - 24 (50% female 50% male), men and women 5% youth with disabilities, 1% youth from diverse gender identities and indigenous people

- 350 Social Media Influencers and Local Content Creators 475 media, education institute authorities, teachers and government officials of age 24+

2.5 Roles and responsibilities of various stakeholders:

| Partner/Stakeholders | Main Roles in the Shomotay Tarunno Project |
| --- | --- |
| Youth Led Organization's (YLO) | Create scope for organizational development, Ensure rights, gender stereotype, lobby and advocacy of local youths through awareness and increase practice level. Engage with local youth in the community to create space for youth in decision making and to influence state and non-state actors Support to implement community action project. |
| Social media influencers and local content creators | Produce online contents/debates to combat gender stereotypes with positive gender narratives |
| Print, Broadcast, Online Media, and Related Entities | Ensure access to media Sensitize, through Strategic Partnerships, Capacity Building Training, Advocacy Dialogues, Intergenerational Engagement to Promote the Shaping of Positive Gender Narratives |
| Entertainment media entities (Directors’ Guild, OTT Platforms, Bangladesh Film Directors Association, Film Artists Association etc.) | Engage for Advocacy Dialogues, Intergenerational Engagement in order to promote the shaping of positive gender narratives |
| Selected universities/ education institute / Press Institute of Bangladesh | Review their education curricula/policy to be in more gender transformative language Design gender friendly curricula focusing gender transformative language Design activities to promote positive gender narratives |
| Ministry of Information and Broadcasting, Ministry of Youth and Sports, Information and Communication Technology (ICT) Division and Ministry of Women and Children Affairs (MoWCA) | Influence to the media and entertainment media Support to build the capacity of the youth and youth lead organization. Support for Improved implementation of policies Support to Policy Review and Analysis Support to Policy amendment and producing new policies (if required) |

3. Details of this Assignment

3.1 Purpose of the Midterm Evaluation

The midterm evaluation aims to assess the extent to which the project has achieved its intended outcomes within the allocated timeframe and resources. The study will collect and analyze data disaggregated by age, sex, disability, and ethnicity to ensure inclusivity and equity in findings.

This evaluation will provide evidence to address key questions related to relevance, effectiveness, efficiency, coherence, impact, and sustainability of the interventions. It will also generate actionable learning to inform future programming and similar initiatives focused on gender equity and youth empowerment.

Furthermore, the evaluation will examine:

- The intermediate impact, success, and sustainability of the so far completion of the project.

- How the project has influenced stakeholders, communities, and existing systems.

- The extent to which gender-transformative approaches were integrated and implemented.

- The appropriateness of the project strategies and direction towards scope of improvement

- The coordination and cooperation between various partners (YLOs, CBOs, GoB etc.) including the implementing partners- relationship dynamics and scope of improvement.

- The extent of achievement of Objective 3, policy advocacy, scope of strategic focus if any.

Finally, the evaluation will identify lessons learned, highlighting what worked well, challenges encountered, and areas for improvement to strengthen the rest of the ST project intervention in a focused way.

3.2 Specific objectives of the study

The specific objectives for this midterm evaluation are-

1.	Evaluate Effectiveness and Progress Towards Outcomes:  Assess the extent to which the project has achieved its intended outcomes and indicators to date, focusing on progress in influencing power holders, strengthening laws and policies, and achieving planned changes in positive attitudes and behaviors, as well as gender-transformative practices at individual, community, and institutional levels, in line with the project’s results framework.

2.	Determine Impact including value for money: Explore the early and emerging  higher-level effects of the project on reducing gender stereotypes and empowering youth, particularly girls and young women, beyond the project’s immediate outcomes. This includes assessing the extent to which the project is contributing to broader institutional, social, or systemic shifts and fostering an enabling environment for gender equality.

3.	Identify Lessons Learned and Ensure Sustainability: Document lessons learned, best practices, and scalable elements of the project to inform future programming. Assess the likelihood of sustaining positive changes in laws, policies, curricula, and community norms beyond the project period, and identify strategies to strengthen sustainability.

3.3 Key (possible) Questions of Midterm Evaluation

This table presents the key evaluation criteria, questions, and tools for the midterm evaluation of the Shomotay Tarunno: Youth for Equality Project. The evaluation focuses on relevance, effectiveness, efficiency, coherence, emerging impact, and sustainability, aligned with the project’s gender-transformative strategy.

| Evaluation Criteria | Key Questions | Tools to be Used |
| --- | --- | --- |
| Effectiveness (Progress towards outcomes & management) | 1.To what extent do the project’s strategies and interventions address the priority needs of diverse youth groups (girls, young women, boys, marginalized identities)? 2. To what extent has the project strengthened youth agency, leadership, participation in decision making, activism and influencing policy as well as gender norm change? 3. What measurable changes have occurred in gender attitudes, stereotypes, norms, and practices among youth, media, and institutions? 4. To what extent have media actors (journalists, influencers, content creators) adopted gender‑sensitive practices and produced positive gender‑transformative content? 5. What evidence emerges regarding the project’s contribution to observed outcomes? 6. To what extent do youth-led initiatives and influencing activities contribute to the log frame outcomes related to youth empowerment, meaningful participation, and evidence-based influencing? 7. What factors (internal/external) have facilitated or hindered progress during implementation? 8. How relevant and adaptive has the project been to contextual shifts (political/social) in the 2026 mid-term context? 9. How relevant is the project in addressing harmful gender stereotypes at individual, community, media, and institutional levels in 2026 (mid‑term context)? 10. What good practices and key lessons can be identified (for the remaining programme period and for similar programming in future)? 11. To what extent the ST partnership (consortium) has impacted the implementation. 12. What impact of the collaboration between the consortium and relevant external partners has been in achieving the three objectives of the project. | FGDs: Youth clubs, media trainees KIIs: Project staff, partners Case Studies: Youth empowerment stories Observation: Youth-led campaigns, training sessions Survey: Youth participants & media trainees Document Review: Logframe & progress reports |
| Emerging Impact (Emerging systemic changes & shifts) | 1. What signs of change are visible in gender norms, youth agency, and institutional practices as a result of the project interventions? 2. Has the project contributed to shifts in media narratives, journalistic standards, or public discourse on gender stereotypes? 3. To what extent are youth‑led actions influencing policies, curricula, or budget discussions? 4. What unintended effects (both positive and negative) have emerged from the interventions? 5. Is the project coherent with Plan’s gender-transformative approach? 6. To what extent is the project aligned and coherent with national policies, media regulations, youth development strategies, and gender-equality frameworks? | FGDs: Youth leaders, media trainees KIIs: Duty bearers, media professionals Case Studies: Gender norm shifts Observation: Campaigns, advocacy events Outcome Harvesting: Stakeholder inquiry sessions Media Analysis: Review of produced content |
| Sustainability & Learning (Continuity & Future Strategy) | 1. What mechanisms are in place to sustain progress (youth networks, media partnerships, policy reforms)? 2. How likely are interventions to continue without external support? 3. Did any contextual shifts (e.g., political, social media trends, policy changes) require adaptation of interventions? 4. What lessons can inform effective implementation of the ST project during rest of the project period? 5. What lessons can inform future programming and scale-up? 6. What factors support or threaten sustainability, and what strategic adjustments are needed in the remaining period? | FGDs: Youth clubs, community leaders KIIs: Government and partner staff Observation: Functionality of networks Survey: Youth participants Sustainability Audit: Analysis of network functionality & local ownership |

3.4 Scope of work

The scope of this midterm evaluation assignment will cover the full geographical, thematic, stakeholder, and temporal boundaries of the Shomotay Tarunno: Youth for Equality project. The consultant/firm will be responsible for conducting the evaluation across these dimensions and delivering all analytical, reporting, and validation tasks.

A. Geographical Scope

The evaluation will cover the project’s implementation areas across all 8 divisions of Bangladesh, which constitute the project’s operational geography:

- Dhaka

- Chattogram

- Khulna

- Rajshahi

- Sylhet

- Barishal

- Mymensingh

- Rangpur

Data collection will involve both national level stakeholders and local stakeholders engaged across these divisions.

B. Thematic Scope

The study will assess the project’s progress and contributions across its core gender transformative and youth focused priorities, including:

- Combating harmful gender stereotypes and influencing social norms

- Strengthening youth agency, leadership, and meaningful participation

- Enhancing gender sensitive practices in media and content production

- Supporting improvements in laws, policies, and curricula related to gender equality

- Strengthening institutional responsiveness within media, universities, and government bodies

- Advancing positive gender narratives through youth led and multi stakeholder initiatives

A concise summary of evaluation focus areas includes:

- Youth engagement and agency, YLOs empowerment to work independently in policy advocacy

- Media sensitization and gender transformative content creation

- Policy, curriculum, and institutional reforms

- Cross sector partnerships and coordination mechanisms

C. Stakeholder Scope

The evaluation will engage a wide range of internal and external stakeholders who are critical to understanding project performance, coherence, and influence. These include:

Internal Stakeholders

- Project team (Plan International Bangladesh)

- Plan Netherlands National Office (NLNO)

- JAAGO Foundation Trust (consortium partner)

- Plan MERL team

- Grants, Influencing, communications, and program teams

External Stakeholders

- Youth participants & youth led organizations (316+ YLOs)

- Journalists (print, broadcast, online), OTT platforms, entertainment media entities

- Social media influencers and local content creators

- Public and private university faculties & Students, especially Mass Communication & Journalism departments & Faculty of fine arts.

- Ministry of Information & Broadcasting; Ministry of Youth & Sports; Ministry of Women & Children Affairs and relevant line directorates

- Relevant government officials, policymakers, and regulators

- Community members, parents, and caregivers

- Indirect stakeholders (approx. 2 million reached through media & advocacy activities)

D. Project Implementation Period to Be Evaluated

The midterm evaluation will examine the project’s progress and results across the entire implementation period from project inception in 2023 to the midterm point in early 2026.

This includes:

- Progress toward outputs, outcomes, and log frame indicators

- Effectiveness of strategies and partnerships

- Emerging changes attributable to youth, media, and institutional engagement

- Responsiveness to contextual shifts during the implementation period

E. Tasks and Responsibilities

The assignment will include, but not be limited to, the following tasks:

- Review project proposal, intervention components, results framework, monitoring data, and relevant government and Plan International documents

- Assess and refine the mixed method evaluation methodology and all data collection tools (quantitative and qualitative)

- Conduct pre-testing and finalize all instruments

- Prepare and submit a comprehensive Inception Report with methodology and workplan

- Administer field data collection across the defined geographic scope, ensuring supervision, cross validation, and quality assurance

- Recruit and train qualified local enumerators, ensuring understanding of tools, safeguarding, and quality procedures

- Undertake systematic data management, cleaning, coding, and analysis

- Produce draft and final midterm evaluation reports incorporating feedback

- Maintain continuous communication with Plan International Bangladesh

- Submit all original raw and cleaned datasets, transcripts, and consent forms

- Prepare a PowerPoint presentation of findings

- Conduct an online validation workshop with relevant national and project stakeholders

3.5 Intended Users of the Midterm Evaluation

The findings of the midterm evaluation will serve as a critical resource for the project team, Plan International Bangladesh, Plan International Netherlands National Office, implementing partners, and other relevant stakeholders. These findings will be used to:

- Assess progress toward achieving project objectives and outcomes within the current implementation period.

- Review and refine strategies to ensure alignment with the project’s gender-transformative approach and evolving context.

- Identify lessons learned and emerging best practices to strengthen ongoing interventions and inform adjustments for the remaining project period.

- Provide actionable recommendations for improving efficiency, effectiveness, and coherence of interventions.

- Support adaptive management, enabling the project team to make evidence-based decisions for course correction and enhanced impact.

- Contribute to sectoral learning, allowing grants, communication, and program teams to share insights and promote best practices across similar initiatives.

The midterm evaluation will not only measure progress but also generate learning to optimize implementation and inform future programming focused on gender equality and youth empowerment.

4. Methodology, Data, and Ethical Guidelines

The midterm evaluation will employ a rigorous mixed-method and participatory approach to generate credible, triangulated evidence on the project’s relevance, coherence, effectiveness, efficiency, emerging impact, and sustainability. The approach will be gender-responsive, culturally sensitive, and ethically grounded to ensure safe and meaningful participation of youth in all their diversity, particularly girls and young women, as well as other marginalized groups.

Evaluation Design

A convergent mixed-methods design will be adopted, where qualitative and quantitative data are collected concurrently, analyzed independently, and integrated during interpretation. This design will enable a comprehensive understanding of progress toward project objectives, including changes in:

- Youth empowerment and agency

- Gender attitudes and norms

- Media engagement and representation

- Policy influence and institutional practices

Desk Review

The evaluation will begin with a comprehensive desk review of project documents, monitoring reports, partner reports, government policies, and relevant literature on gender equality, youth empowerment, and media influence. This will contextualize findings and support contribution analysis.

Qualitative Methods

The qualitative component will generate in-depth insights into participants’ experiences, perceptions, and the contribution of project interventions to observed changes. In line with the OECD-DAC evaluation criteria, Outcome Harvesting approach can be employed as a qualitative inquiry method to systematically identify, substantiate, and analyze significant outcomes—both intended and unintended—by engaging stakeholders in a participatory process. Purposive sampling will ensure representation across gender, age, and stakeholder groups, enabling a comprehensive understanding of diverse perspectives. This method will not only capture what changed but also explore how and why these changes occurred, providing actionable learning for future programming. The other methods could be included (but not limited to):

- Focus Group Discussions (FGDs): FGDs will be conducted with youth (girls, boys, diverse identities), parents/caregivers, and media trainees to explore empowerment, gender norms, participation, and barriers.

- Key Informant Interviews (KIIs): KIIs will involve duty bearers, media professionals, education institute representatives, and project staff to assess relevance, coherence, and sustainability prospects.

- Consultation Meetings: Two meetings will be held—one with Plan staff and one with partner organizations—to capture operational insights and adaptive management practices.

- Case Studies: 2–3 case studies will illustrate transformative changes in gender attitudes, youth agency, and media engagement.

Quantitative Methods

A structured quantitative survey will be implemented to assess progress on key indicators and provide robust evidence for triangulation with qualitative findings, thereby supporting contribution analysis during the midterm evaluation. The survey will target a representative sample of youth participants, including:

- Adolescents (10–17 years)

- Youth (18–24 years, mostly but in some cases up to 35 yrs.)

- Participants who received training, capacity enhancement sessions, and interactive session (conducted by YLOs)

- Participates who attended Divisional Advocacy Workshops

- Youth club members and volunteers

Data collection will be conducted digitally using platforms such as Kobo Toolbox or ODK, ensuring real-time data validation, GPS-enabled verification, and secure data management

Sampling

A stratified two-stage cluster sampling design will be applied to ensure representation across geographic and demographic strata. Sampling weights will be used during analysis to maintain representativeness.

Data analysis

The analysis will follow an integrated, multi-step process. Quantitative data should be cleaned, validated, and analyzed using descriptive and comparative techniques to identify patterns and trends across demographic groups. Qualitative data needs to be transcribed, coded, and analyzed thematically, gender, age, disability and other vulnerability. A rigorous triangulation process should be proposed to help validate or challenge emerging conclusions and strengthen the evaluation’s assessment against OECD-DAC evaluation criteria.

Ethical consideration

Ethical compliance needs to be central to the methodology. The evaluation will strictly follow Plan International’s Ethical MERL Framework, Global Safeguarding Policy, Child Protection Policy, and PSEA standards. All participants must provide informed consent or assent, with additional safeguards for minors and vulnerable individuals. Gender-matched enumerators need to be deployed, especially when interviewing adolescent girls or individuals discussing sensitive topics. Any safeguarding concerns identified during fieldwork will be referred immediately through established mechanisms. All data will be handled securely, with strict confidentiality measures in place.

The consultant(s)/firm will obtain the necessary ethical approval from relevant institutional review boards (IRB) before commencing the study. All applicants should include details in their proposal on how they will ensure accordance with ethics and child protection in the data collection process. Specifically, the consultant(s)/firm shall explain how appropriate, safe, non-discriminatory participation of all stakeholders will be ensured and how special attention will be paid to the needs of children and other vulnerable groups. The applicants should include details on how they will ensure that their methods uphold the dignity, safety, privacy, and sensitivities for the girls and young women that they interact with. The consultant(s) shall also explain how confidentiality and anonymity of participants will be guaranteed. The consultant must coordinate with PLAN to obtain and adhere to approval processes from a relevant authorized body before the commencement of data collection.

Limitations

Potential limitations such as governmental institutions access restrictions, cultural constraints on female and marginalized participation, protection sensitivities, and respondent fatigue need to be anticipated and mitigated through flexible scheduling, gender-responsive facilitation, safe data collection spaces, and the use of vignettes or indirect questioning for sensitive topics. Continuous data quality assurance measures including daily monitoring of digital submissions, back-checks, supervision visits, and qualitative debriefing sessions need to be incorporated throughout the process.

Overall, this methodology should be designed to produce a comprehensive, credible, and actionable assessment of the project’s performance, emphasizing learning, accountability, and practical recommendations for future youth empowerment and gender sensitive-focused programming in Bangladesh.

5. Deliverables

The consultant will be responsible for producing the following deliverables:

- Inception Report – outlining the finalized methodology, sampling strategy, data collection plan, and timeline.

- Finalized Data Collection Tools – translated, piloted, and ready for digital deployment.

- Digital Data Collection Setup – tools configured on platforms such as Kobo Toolbox or ODK.

- Cleaned and Validated Dataset – including raw data, cleaned dataset, transcripts, and consent forms.

- Draft Midterm Evaluation Report – presenting preliminary findings and analysis.

- Validation Workshop – conduct an online session with relevant stakeholders to present and validate findings.

- Final Midterm Evaluation Report with clear analysis and specific recommendations – incorporating feedback from Jaago Foundation, Plan International Bangladesh, Plan Netherlands National Office (NlNO), and the Embassy of the Kingdom of the Netherlands (EKN).

- A Short version of the Final Report

- Summary Presentation (PPT) – highlighting key findings and recommendations.

Note: All original data (paper or electronic), along with primary datasets, transcripts, and consent forms, must be submitted to Plan International Bangladesh for review and archiving.

6. Timeframe

The total duration of this study will be 90 calendar-days starting from the Mid-March 2026, the date of the agreement signing. The time will ideally be distributed as per the following table. In any case, the final report and the transfer of funds have to be finalized before the end of June 2026.

| Deliverables | Timeline | Responsible |
| --- | --- | --- |
| Inception meeting and submit inception report | 6 days | Consultant(s)/firm |
| Review and finalize inception report | 8 days | PLAN/ Consultant(s)/firm/NLNO |
| Understanding, develop & finalize and translation of tools | 15 days | Consultant(s)/firm/PLAN/NLNO/EKN |
| Ethical Approval from IRB, onboarding data enumerators, training of the data enumerators on the tools and policy and doing field test | 22 days | Consultant(s)/firm |
| Data collection, review and sharing | 12 days | Consultant(s)/firm/PLAN |
| Submit 1st draft report | 8 days | Consultant(s)/firm |
| Review 1st draft report | 7 days | PLAN MERL team/NLNO/EKN |
| Submit 2nd draft report | 5 days | Consultant(s)/firm |
| Organize a Validation Workshop with relevant stakeholders | 1 days | Consultant(s)/firm |
| Review 2nd draft report | 4 days | PLAN MERL team/ NLNO/EKN |
| Submit Final reports, Summery Version of the report and a PPT presentation | 3 days | Consultant(s)/firm |
| * The timeline may vary based on the contract signing date |  |  |

Proposed detail timeline (GANTT Chart view) of the task and deliverables can be:

| Month | March 2026 |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | RESPONSIBLE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TASK | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 |  |
| Inception report submission review inception report (strategy & methodology) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Final inception report sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTA NT/MERL/ PROJECT/NLNO/EKN |
| Understanding, develop & finalize tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTA NT/MERL/ PROJECT |
| Translation of the tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MERL/PRO JECT/NLNO/ CONSULTANT |
| IRB approval from ethical review board |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Data enumerator hiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Orientation & field test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Data collection, analysis & sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Submit 1st draft report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT/MERL/PROJECT |
| Review 1st draft report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Submit 2nd draft report & review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |
| Validation workshop with relevant stakeholders and address the comments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MERL/PROJECT/NLNO/ EKN/CONSULTANT |
| Finalize reports & deliverables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTA NT/MERL/ PROJECT/NLNO/EKN |
| Submit the final report with the presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTA NT/MERL/ PROJECT/NLNO/EKN |
| Inception report submission review inception report (strategy & methodology) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTA NT/MERL/ PROJECT/NLNO/EKN |
| Final inception report sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |

7. Supervision/Management of Assignment

The consultant will be required to work closely with Plan International Bangladesh, would address feedback and comments from Plan International Netherland National Office (NLNO), and PLAN’s MERL team (as appropriate). The consultant will be directly accountable to the PLAN’s focal person; M&E Specialist. The consultant will keep the focal person continually informed on the progress of the assignment updates via email.

8. Expected Competencies of Consultant(s)/Firm

Minimum Qualifications & Experience

- Minimum 7–10 years of proven experience in conducting large-scale evaluations, preferably midterm or endline studies for development or gender-equality projects.

- Advanced academic degree (Master’s or higher) in Social Sciences, Gender Studies, Development Studies, Public Policy, Media and Communication, or a related field for lead researcher

- Demonstrated experience with IRB approval processes in Bangladesh, including preparing protocols and navigating institutional review procedures.

- Proven experience conducting evaluations in the media sector, including assessments of media practices, content analysis, and journalist capacity building.

Technical Evaluation Skills

- Proven expertise in designing mixed-method research (surveys, KIIs, FGDs), including sampling design, instrument development, and tool pre-testing.

- Strong proficiency in quantitative and qualitative data collection, analysis, and interpretation, including ability to triangulate findings across methods.

- Demonstrated capacity to conduct media reviews, policy analysis, and institutional assessments, particularly in gender-sensitive journalism and media engagement.

Thematic & Sectoral Expertise

- Experience working with gender-transformative programming, including integrating gender analysis across all stages of evaluation.

- Prior engagement with youth-led organizations, diverse young people, and community-based actors, with sensitivity to cultural and socioeconomic contexts.

- Familiarity with child rights and protection principles, ensuring safe, ethical participation of adolescents and vulnerable populations.

Ethics & Safeguarding

- Knowledge of ethical research standards and safeguarding requirements for research involving minors and vulnerable groups.

- Ability to ensure confidentiality, informed consent, and compliance with Plan International’s MERL Ethical Framework and safeguarding policies.

Operational & Management Skills

- Demonstrated ability to manage complex field operations across multiple geographic sites, ensuring timely completion within tight deadlines.

- Capacity to coordinate and supervise data collection teams, ensuring strong quality assurance and adherence to protocols.

- Availability of a skilled multidisciplinary team for data collection, transcription, data entry, analysis, and report writing.

Communication & Reporting Skills

- Strong analytical writing skills, with proven ability to produce high-quality evaluation reports with actionable recommendations.

- Ability to present complex findings clearly to both technical and non-technical audiences.

- Effective communication and facilitation skills for engaging with Plan International Bangladesh, NLNO, EKN, government stakeholders, and partner organizations.

Technical Tools & Languages

- Proficiency in data analysis software (e.g., SPSS, Stata, R, NVivo, Atlas.ti).

- Fluency in English and Bangla (spoken and written).

Collaboration & Adaptability

- Proven ability to work collaboratively with Plan International teams (PLAN BD, NLNO, EKN) and incorporate feedback throughout the evaluation process.

- Demonstrated flexibility to adapt methods in response to contextual changes or limitations during fieldwork.

9. Application Process

The application should be submitted in two parts that include: a) technical and b) financial. The technical part of the proposal should not exceed 10 pages (excluding annexes) and will contain the following:

•	Detailed methodology of the study (sampling, data collection, enumerator training, data quality checks, and standards).

•	Proposed timelines as stated in the ToR.

•	Account of relevant experience (consulting team profile). Applications should elaborate on the consultant’s abilities to manage work within the tentative timelines shared in this ToR along with any challenges.

•	Consulting team profile including CVs of the team leader and every key members of the study team.

•	Copy of valid VAT registration certificate (for consulting firm).

•	Copy of valid TIN certificate and bank account details.

•	Two examples of previous and relevant work (in the annex)

•	Names and details of three references.

The consulting team profile should contain:

•	The full names of all participating consultants and their roles, including technical expertise

•	Physical address of the consultancy firm.

•	Telephone number(s) of the firm (if applicable) and participating consultants

•	Full name and contact information of the contact person within the consulting team (must be the team leader or a key member)

•	Full names of Directors/Proprietors.

The financial proposal should clearly identify, an itemized summary of the cost for the assignment with a detailed breakdown. The budget should not contain income tax as a separate head; it can be blended with the other costs, as it will be deducted from the source. However, VAT can be mentioned in the budget as per government regulation. PLAN will deduct VAT and Tax at source according to the Government of Bangladesh rules and deposit the said amount to the government treasury. The consultant/consulting firm is expected to provide a justified budget, which is consistent with the technical proposal, and should contain:

•	Itemized consultancy fees/costs

•	Itemized field data collection expenses

•	Itemized administrative expenses

•	Validity period of quotations

Proposal submission:

The application package that includes the technical and financial proposal should be submitted electronically to the email address: Planbd.consultant.hiring@plan-international.org with the title “Proposals for Mid Term Evaluation of Shomotay Tarunno: Youth for Equality Project” as subject line. Two separate folders, i.e., technical and financial, should be submitted into one zip folder with a cover letter.

The proposals should be submitted in PDF format. Proposal submitted to any other email account except the one stated above or in any other form will not be considered. Submissions after the deadline will be treated as disqualified.

Submissions after the deadline on 04 March, 2026 will be treated as disqualified.

For any clarification related to the content of the assignment, the consultant should contact with Md. Enamul Haque, Admin & Procurement Specialist through the E-mail: enamul.haque@plan-international.org

10. Payment Schedule

The payment for this assignment will be made in 3 (three) installments, following the below schedule-

| Installments | Percentage | Timeline |
| --- | --- | --- |
| First installment | 30 | After receiving the inception report |
| Second installment | 30 | After receiving the first draft report |
| Third installment | 40 | After the acceptance of final report |

11. Approval and Permissions:

The consultant/consulting firm will ensure necessary Governmental authority permission and approval for the Midterm evaluation where required. Permission from necessary government and others institutional Administration (if any) would require to be arranged by the consultant/consulting firm.

12. Parameters for Selection of Firm/Individual to Carry Out the Assignment

The following table outlines the selection criteria-

| Criteria | Score |
| --- | --- |
| Competencies, qualifications and expertise (including Qualifications in the relevant thematic area, Research. training, evaluation related qualifications, Contextual understanding, Type of the previous experience, Team composition & experience, and Diversity considerations of the proposed team) | 35 |
| Appropriate evaluation framework (including Task conceptualisation, Proposed methods, Data quality, Presentation and writing skills, and Equity, diversity and inclusion) | 40 |
| Amount of budget and justification | 25 |

13. Penalty Clause

The consultant/consulting firm is expected to provide services within the agreed timeframe as well as submit the final report maintaining the quality as mentioned in Section 6 of this ToR. If the quality is not maintained as agreed, Plan International Bangladesh will deduct 5% of the total agreement amount. If for any reason, the consultant(s)/firm fails to deliver services within the stipulated time, the consultant(s)/firm needs to inform Plan International Bangladesh in time with a valid and acceptable explanation. Failing to do this may invoke a penalty clause at the rate of 1% for each day of delay.

14. Bindings

All documents, papers and data produced during the assignment are to be treated as Plan International Bangladesh’s property and restricted for public use. The contracted consultant(s)/firm will submit all original documents, materials and data to Plan International Bangladesh.

15. Negotiations

Once the proposals are evaluated, Plan International Bangladesh may enter into a negotiation with one or more than one consultant(s)/firm for final selection. If negotiations fail, Plan International Bangladesh will invite a consultant(s)/firm who had submitted the proposal and received the next highest score to negotiate a contract. If none of the invited proposals lead to an agreement, a new Requests for Proposals (bidding document) will be called for.

16. Award of Contract

The consultant(s)/firm is expected to commence the assignment within one week of signing the contract.

17. Risk Management

The Consultant/s must take all reasonable measures to mitigate any potential risk to the delivery of the required outputs of this consultancy on time and meeting the expected quality. As such, applicants should submit a risk management plan that covers (at minimum):

•	Key assumptions underpinning the successful completion of the assignment, anticipated challenges, and estimates of the level of risk for each risk identified.

•	Contingency plans will be put in place to mitigate any occurrence of each of the identified risks.

18. Child Protection and Safeguarding, Child Rights, and Gender Policy: Safeguarding Children and Programme participant

The consultant(s)/firm acknowledges that it has received a copy of and has read and understood Plan’s Global Policy Safeguarding for Children and programme participant as attached to this ToR. The consultant(s)/firm shall (and shall ensure that its employees, agents, sub-contractors and any other party always engaged in the performance of services) and in all circumstances abide by the Global Safeguarding Policy for the period of this agreement.

The consultant(s)/firm represents and warrants that neither the consultant nor any of its (firm) employees, agents, sub-contractors and any party involved or likely to be involved in the performance of the services is suspected of involvement or has been suspected of such involvement in an incident of abuse of a child or children and programme participant whether as described in the Global Safeguarding Policy or otherwise in such a way that compromised or compromises the safety of children and programme participant.

If at any time during the performance of this agreement, it comes to the attention of Plan (or any of its officers, employees, agents, sub-contractors or any other party engaged in the performance of services) that the consultant(s)/firm’s or any of its officers, employees, agents, sub-contractors or any other party engaged in the performance of services was or is suspected of involvement or has been suspected of such involvement in an incident of abuse of a child or children, whether as described in the Global Safeguarding Policy or otherwise in such a way that compromised or compromises the safety of children and Programme participant, the consultant(s)/firm shall:

- immediately cease from performing the Services and or remove any such officer, employee, agent, sub-contractor or other party engaged in the performance of Services from the provision of the Services or any aspect connected or related to the provision of the Services; and

- immediately report such incident or suspicion to PLAN’s contact (Safeguarding & PSEA Focal) and in any event within 12 hours of such information coming to the attention of Plan.

Any breach of this clause and or the Global Safeguarding Policy shall constitute a material breach and shall entitle Plan (in its absolute discretion) immediately terminate this agreement without notice and or take such other appropriate action as PLAN shall in its absolute discretion determine including requesting the removal from the provision of the services of any suspected officer, employee or other party of the consultant(s)/firm (if applicable); reporting any incident of abuse to the police or instituting legal proceedings for a claim for damages against the consultant(s)/firm.

The consultant(s)/firm shall as well comply with the child and adult safeguarding, gender and conflict of interest policy of Plan International Bangladesh. Any violation/deviation in complying with the policy will not only result in termination of the agreement but also Plan International Bangladesh will initiate appropriate action to amend the damages/losses caused due to non-compliance of the policy.

Gender Equality

All parties agree to abide by the basic principles of gender equality and comply with the provisions of existing gender-related international and national conventions. Specifically, the parties shall ensure that no gender-based discriminations, bullying, and harassment such as sexual harassment takes place in the course and as part of this engagement (this includes, but is not limited to, physical, verbal, other forms analogous to the foregoing, the use of gender sensitive language in promotional materials, recordings and publications).

Importantly, parties behave in accordance, demonstrate compliance to, and support of prevailing policies and procedures related, be aware of the issues of harassment, bullying and discrimination and the forms it can take and of the damage it can do to individuals and to PLAN. Parties also agree to report potential breaches, speak out and fully comply confidentially with any investigation and importantly contribute to building an environment advocating and promoting gender equality and free from harassment, bullying and discrimination. An orientation on PLAN’s gender equality principle shall be provided by PLAN to the consultant(s)/firm as requested and/or as deemed necessary.

Child rights, gender and inclusion

Plan International Bangladesh is committed to the wellbeing of children together with Gender Equality and does not tolerate child abuse and sexual harassment. Plan International projects apply gender and inclusion sensitive approaches and explicitly aim for results that improve the rights of children and young people as well as gender equality. Thus, all of Plan International Bangladesh’s assessments and/or evaluation promote the equal participation of all age groups and especially of children, equal gender participation and inclusion of person with disabilities and all marginalized people. How those groups will be included must be reflected in the methodology proposed by the consultant.

19. Disclaimer

Plan International Bangladesh reserves the right to accept or reject any or all proposals without assigning any reason whatsoever.

20. Annexes

Annex 1: Plan International Global Policy Safeguarding

Annex 2: Reporting Structure

The final midterm report should be chapter based following structure not more than 40 pages (final version without annex.)

1. Title page

2. Acknowledgments

3. Executive summary (Summary of Objectives, Methodology, Key Findings, and Recommendations)

4. List of acronyms

5. Table of contents and lists of figures and tables

6. Introduction and Background

a. Overview of Project Context, Objectives, and Evaluation Purpose

b.   Alignment with the project objectives

7. Methodology

a. Evaluation Approach, Data Collection Methods, and Sampling

b. Data Disaggregation (age, gender, disability, etc.) and Analysis Techniques

8. Relevance of Interventions

a. Assessment of Project Alignment with Local Needs, Priorities, and Contextual Relevance

b. Evidence on Child Protection, Gender, and Social Inclusion Relevance

9. Efficiency of Resource Utilization

a. Examination of Resource Allocation, Cost-Effectiveness, and Alternative Approaches Considered

10. Impact Assessment

a. Validation of Long-term Effects on Child Protection, Gender Norms, and Community Capacity

b. Analysis of Intended and Unintended Effects, with a Focus on Gender and Social Inclusion

11. Sustainability and Lessons Learned

a. Assessment of Project Sustainability and Community Ownership

b. Lessons Learned, Best Practices, and Recommendations for Future Projects

12. Summary of Final Values for Indicators

13. References

14. Annexes

a. Supplementary Data, Detailed Analysis, Tools, and other Relevant Documents

Annex 3: Results Framework of the Project

Annex 4: MERL Ethical Framework

=====================================x====================================

Disaster Preparedness Process (DPP) 4, Plan International Bangladesh, 2021