Terms of Reference (ToR)

Capacity building of parents/caregivers by Family Centered Care (FCC) training package at selected facilities of Bangladesh

Saving Women and Premature Babies (SWAP) project

November 2023

Health and Nutrition Sector

Save the Children, Bangladesh

# Table of Content

Table of Content	1

1.	Project Summary	2

2.      Introduction	3

1.	Scope of research	5

1.1	Objectives and Scope	5

1.2	Stakeholders/Audience and Use of the Study	6

1.3	Key Study Questions	6

2.	Study Methodology	7

2.1	Study Design	7

2.2	Sampling	7

2.3	Data Sources and Data Collection Methods/Tools	7

2.4	Ethical Consideration	8

5.5 Known limitations.	9

3.	Expected Deliverables	9

4.	Reporting and governance	10

5.	Study management	10

6.	dissemination plan	12

7.	Research team and Selection Criteria	12

8.	schedule of payment	12

9.	TECHNICAL EVALUATION CRITERIA	13

10.	Annexes	14

# Project Summary

Save the Children (SC) in Bangladesh is implementing a thirty-two month (April 2022 – December 2024) Saving Women and Premature Babies (SWAP) project in selected five health facilities in Dhaka, Lakshmipur and Sylhet districts. This project assists the Ministry of Health and Family Welfare (MOHFW) including National Newborn Health Program (NNHP) and Integrated Management of Childhood Illness (IMCI) of Bangladesh, to improve the quality of care for mothers (particularly those likely to deliver premature/small babies), and small and sick newborns by supporting delivery and institutionalization of evidence-based lifesaving interventions in a network in selected facilities.  The overall goal of the project is to improve survival for small and sick newborns and pregnant women with complications leading to preterm birth. The project is funded by SCUS (Anonymous Donor).

| Type of evaluation | Capacity building of parents/caregivers by Family Centered Care (FCC) training package at selected facilities of Bangladesh |
| --- | --- |
| Name of the project | Saving Women And Premature babies (SWAP) Project |
| Project start and end dates | 1 April 2022 – 31 December 2024 |
| Project duration | 32 months |
| Project locations | - Dhaka: Bangabandhu Sheikh Mujib Medical University (BSMMU); M R Khan Shishu hospital, Mirpur; & Mohammadpur Fertility Services & Training Center (MFSTC), Dhaka. - Lakshmipur: Lakshmipur District Hospital. - Sylhet: Sylhet MAG Osmani Medical College & Hospital. |
| Thematic areas | Health and Nutrition |
| Sub themes | Maternal, Neonatal and Reproductive Health |
| Donor | Save the Children US (SCUS) |
| Estimated beneficiaries | Direct Beneficiaries: Approximately 29,970 children who will receive services from project supported facilities |
| Overall goal of the project | Improve survival for small and sick newborn and pregnant women with complications leading to preterm birth. |

# 2.      Introduction

The project works to improve the quality of care for mothers (particularly those likely to deliver premature/small babies), and small and sick newborns by supporting delivery and institutionalization of evidence-based lifesaving interventions along with new interventions in a network of five health facilities at selected three districts. As a part of that assistance, Saving Women and Premature Babies (SWAP) will introduce and implement the Training Module for the Providers on Family Centered Care (FCC) for Newborn at the Facility under the guidance of Directorate General of Health Services (DGHS). This initiative aims to develop and nurture the family's role in partnership with health care team in care of a newborn in five selected health facilities (Bangabandhu Sheikh Mujib Medical University, Laksmipur District Hospital, Sylhet Medical College Hospital, MR Khan Shishu Hospital and Mohammadpur Fertility Services and Training Centre (MFSTC).

3.    Background and context

To achieve the ambitious 2030-sustianable development goal (SDG) target of reducing the neonatal mortality rate to 12 or below per thousand live births, the Government of Bangladesh (GOB) and its development partners has been strengthening collaborative efforts to reach the SDG -3 in health with a strong focus to universal coverage with quality health care and facility-based services. With improvements in newborn survival rate, there is increasing attention and emphasis on improving quality of newborn care. A key strategy towards this is improving clinical care for sick neonates in health facilities. Facility based newborn care (FBNC) under the national health programme provisions for care of sick neonates at the Special Newborn Care Units at district levels. Human resource constraints in health facility settings is closely linked to overburdening of staff, low compliance with aseptic routines resulting in compromise of quality neonatal care. While the care provider continues to be in charge, involvement of parents leads to sharing of work and better delivery of care and staff satisfaction. Family Centered Care is low-cost simple innovative approach that can address the limitations and will improve quality of care. In this regard, SC Bangladesh has initiated SWAP Project at five health facilities of Dhaka, Lakshmipur, and Sylhet districts which is supported by anonymous donor through SC US.

Goal and Objectives:

Project Goal: The objective of this project is to improve survival for small and sick new-borns and pregnant women with complications leading to preterm birth. The are five following objectives:

- Improve pre-partum identification and management of pregnant women with complications that can potentially lead to preterm birth in hospitals.

- Improve essential care for all new-born and Improve facility-based care for small and sick new-borns in hospitals.

- Strengthen Quality Improvement (QI) processes to improve care for small and sick newborns and pregnant women in hospitals.

- Introduce innovation/innovative approaches to improve care for sick new-born in hospitals.

- Strengthening appropriate utilization of Maternal Newborn Health (MNH) services from the facility and practices of healthy MNH behaviours at household to improve care for small and sick new-born.

Intervention area:

This project has been implementing in 5 following health facilities:

- Bangabandhu Sheikh Mujib Medical University [BSMMU],

- M R Khan Shishu [Children] hospital, Mirpur Dhaka;

- Osmani medical college, Sylhet;

- Lakshmipur district hospital; and

- Mohammadpur Fertility Services & Training Center [MFSTC], Dhaka.

These facilities are a mix of facilities in different tier of health care service delivery, public-private, under two major directorate of MOHFW – DGHS & Directorate General of Family Planning ([DGFP].

The package is consisting of a set of existing evidence based MNH interventions plus new approaches/innovations. BSMMU is the country’s state of art facility for health care. Neonatology department of BSMMU is providing technical and policy guidance to MOHFW as well as generating evidence from new interventions and approach of newborn care. MR Khan Shishu hospital, Mirpur Dhaka is a specialized private sector facility for newborn care. Osmani medical college Sylhet and Lakshmipur district hospital are MOHFW facilities at regional and district level under the administrative control of DGHS. Again, MFSTC is under administrative control of another directorate under MOHFW, the DGFP.

Hence these 5 facilities are selected to represent national policy and guidance (BSMMU), Private sector specialized institute (MR Khan Shishu hospital), representation from DGHS referral level at different tiers (Osmani medical college and Lakshmipur district hospital) and representation of DGFP. Considering all these the 5 facilities have been selected for this project.

# Scope of research

## Objectives and Scope

- Objective:

The overall objective of the implementation research is to assess the feasibility of Family Centered Care by health care workers and to determine to what extent the capacity of parents/caregivers is improved to manage newborn after the training on Family Centered Care package at the selected facilities in Bangladesh.

The specific objectives are to:

- Assess the knowledge of the health care providers  before & after receiving FCC training

- Assess the knowledge of parents/caregivers before and after receiving FCC counselling  in the hospital setting

- Assess the skill of parents/caregivers before & after receiving  FCC counselling in the hospital setting.

- Assess the feasibility of Family Centered Care by health care workers at the hospital settings.

- Provide recommendations for scaling up and sustainability plan in similar healthcare settings in Bangladesh.

Scope:

- Conduct a comprehensive review of existing literature related to Family Centered Care, and similar interventions.

- Develop a detailed research protocol outlining the study design, methodology, inclusion/exclusion criteria, data collection tools, and ethical considerations.

- Obtain necessary approvals from institutional review boards (IRBs) and regulatory bodies to ensure compliance with ethical standards and legal requirements for human research.

- Implement a system for consistent and accurate data collection to address specific objectives.

- Develop a detailed report of the study including context, methodology, findings, recommendation and conclusion

- Formulate evidence-based recommendations and guidelines for the optimal use of Family centered care packages at hospital settings.

## Draft a scientific paper summarizing the research findings, methodology, results, and conclusions for publishing in the research journal and support Government of Bangladesh to incorporate in the next sector operational plan. Stakeholders/Audience and Use of the Study

The main audience of the study would be involved as follows:

| Stakeholder | Further information |
| --- | --- |
| Project donor | Save the Children US (SCUS) |
| Primary implementing organisation | Save the Children Bangladesh |
| Government stakeholders | - Line Director MNCAH, Directorate General of Health Services (DGHS), - National Newborn Health Program (NNHP) & Integrated Management of Childhood Illness (IMCI) , - Maternal Health Program, , - MCH unit, Directorate General of Family Planning (DGFP) |
| Other key stakeholders | UN Agencies; Bangladesh Neonatal Forum (BNF); Bangladesh Perinatal Society (BPS); Obstetrical & Gynecological Society of Bangladesh (OGSB); Bangladesh Perinatal Society (BPS), Neonatology department of BSMMU, icddr,b Private sector specialized institute |
| Beneficiaries | Health Care providers, Newborn including parents/caregivers in project area |

## Key Study Questions

The following study questions will be answered in the research:

- How do healthcare workers perceive and rate their acceptability of the Family Centered Care approach for both newborns and preterm newborns in hospital settings?

- How does participation in the Family Centered Care program enhance the knowledge and skills of parents/caregivers in managing newborns and preterm newborns in hospital settings?

- What specific elements of the Family Centered Care package contribute most significantly to the capacity development of parents/caregivers?

- What are the key learning outcomes and changes in behavior or practices observed in parents/caregivers who have undergone the program?

- What are the key factors that contribute to the sustainability of Family Centered Care programs in the long term?

# Study Methodology

## Study Design

This will be mixed method combination of qualitative and quantitative approaches where the project is keen to implement and determine to what extent the capacity of parents/caregivers is improved to manage newborn after the training on Family Centered Care package at the selected facilities in Bangladesh.Thus the consultant/firm is expected to propose the appropriate research design including data collection tools to meet the objectives of the research. The research should involve multiple stakeholders located in the project catchment areas and include triangulation in data collection methods. The methodology and relevant data collection tools should be adjusted in consultation with SCI and finalized before implementation.

The consultant (individual/firm) will prepare a comprehensive work plan with a budget. Adaptation and customization of the training package to Bangla is expected by the consultant. Additionally, selected SC colleagues will be engaged (in addition to consultant hired enumerators) during data collection and at the field level for better understanding of the data being collected.

## Sampling

It is expected that the consultant (individual/firm) will propose appropriate methodology including sample size and sampling methods. Sampling should consider the objective of the research and all the characteristics of the population of the project.

## Data Sources and Data Collection Methods/Tools

All primary data that will be collected during the study must facilitate disaggregation as appropriate. SC will provide guidance on tools and classification schemes for this minimum dataset. The consultant will translate the tools, convert them to KoBo, if needed, and propose data analysis plan as appropriate. Existing SC data sources that can be drawn in the research include:

- A list of participants from which the consultant team will draw the sample for the survey.

- SC will provide existing study reports, including project proposals, logical frameworks, matrixes, learning briefs, policies, and extracts of accessible data.

SC will provide support to communicate with stakeholders and provide access in communities for primary data collection. The team should also indicate how data triangulation will be realized.

A range of project documentation that provides information about project design, implementation, and operation will be made available to the research team.

The study team is required to adhere to the SC Child Safeguarding; Protection from Sexual Exploitation and Abuse; Anti-Harassment, Intimidation and Bullying; and Data Protection and Privacy policies throughout all project activities.

### Quality Control Mechanism

The consultant (individual/firm) team will collect the primary data. The consultant (individual/firm) will recruit well-reputed enumerator (who have relevant experience for data collection). The enumerators should also have previous experience on studies on public health and health service delivery system. A translator (who has relevant experience in adapting different training packages of Bangladesh) will be recruited by the consultant firm.

## Ethical Consideration

The consultant (individual or firm) will follow SCI procedure of below:

- Child participatory. Where appropriate and safe, children should be included in the research. Any child participation, whether consultative, collaborative or child-led, must abide by the 9 Basic Requirements for meaningful and ethical child participation.

- Inclusive. Ensure that children from different ethnic, social, and religious backgrounds have the chance to participate, as well as children with disabilities and children who may be excluded or discriminated against in their community.

- Ethical: The evaluation must be guided by the following ethical considerations:

  - Safeguarding – demonstrating the highest standards of behavior towards children

  - Sensitive – to child rights, gender, inclusion, and cultural contexts

  - Openness - of information given to the highest possible degree to all parties involved.

  - Confidentiality and data protection - measures will be put in place to protect the identity of all participants and any other information that may put them or others at risk.

  - Public access - to the results when there are no special considerations against this.

  - Broad participation - the relevant parties should be involved where possible.

  - Reliability and independence - the study should be conducted so that findings and conclusions are correct and trustworthy.

It is expected that:

- Data collection methods will be age and gender appropriate.

- Study activities will provide a safe, creative space where children feel that their thoughts and ideas are important.

- Informed consent will be used as appropriate.

## 5.5 Known limitations.

- Participants who choose to participate in the training program may have different characteristics compared to those who do not, introducing potential bias in the study results.

- Language differences or literacy levels among participants may affect their engagement with the Family Centered Care package.

- Changes in healthcare worker staffing levels or turnover may affect the consistency and quality of training and support provided to parents/caregivers.

# Expected Deliverables

The study deliverables and tentative timeline (subject to the commencement date of the study) are outlined below.

Deliverables and Tentative Timeline

| Deliverable/Milestones | Timeline |
| --- | --- |
| The Study team is contracted and commences work | 05 January 2024 |
| The study team will facilitate a consultation meeting | 07 January2024 |
| The study team will submit research protocol along with an inception report* in line with the provided template, including: - Study objectives, scope, and key study questions - Description of the methodology, including design, data collection methods, sampling strategy, data sources, and study matrix (includes evaluation objective, evaluation question, tools to be used, target participants, methods e.g., KII, FGD, and sample survey, and so on). - Data analysis and reporting plan, caveats and limitations of study, risks and mitigation plan, ethical considerations including details on consent. - Stakeholder and children communication and engagement plan. - Consultation protocols for consulting with children and other vulnerable groups (if applicable). - Key deliverables, responsibilities, and timelines. - Logistical or other support required from Save the Children. - Data collection tools (in line with the study matrix). | 20 January 2024 |
| Research protocol/Inception report review | 25 January 2024 |
| Final data collection tools (in the report language): - Survey instrument - Data collection mechanism - Tool orientation | 30 January 2024 |
| Adaptation and Customization of training package in Bangla | 28 February 2024 |
| IRB Approval (Potentially from BMRC) | 30 March 2024 |
| Data Collection (including enumerator training) | 1 April -30 June 2024 |
| A Study Report* (Draft Version) including the following elements: 30 pages maximum, excluding the Reference and Annex - Executive summary (1-2 page) - Program background and context relevant to the Study (1 page) - Purpose, objective, and scope of the research, including key research questions (1 page) - Overview of the study methodology and data collection methods, including any specific caveats or methodological limitations of the research (1-2 page) - Findings aligned to each of the key Study questions (15-18 pages) - Conclusions outlining implications of the findings or learnings (1 page) - Lesson learned, and recommendations. (1-2 page) - References - Annexes (Project log frame, Study ToR, Inception Report, Study schedule, List of people involved) | 20 July 2024 |
| Data and analyses including all raw data, databases, and analysis outputs | 30 July 2024 |
| Scientific Paper | 30 August 2024 |
| Final Study Report* Incorporating feedback from consultation on the Draft Study Report | 15 September 2024 |
| Knowledge translation materials: - PowerPoint presentation of study findings (Slide deck (8 slides) highlighting the: methodology and purpose -1 slide, key findings 4 slides, challenge 1 slide, lesson learned if any 1 slide, and recommendation 1 slide.) - Evidence & Learning Brief** - Formulation of Guideline | 30 September 2024 |

*Note: Budget of approval from BMRC need to be included by the Consultant (Individual/Firm)

*All reports are to use the Save the Children Final Study Report template.  Please also refer to Save the Children technical writing guide.

** The Evidence & Learning Brief is a 2-4 pages summary of the full report and will be created using the Save the Children Evidence & Learning Brief template.

# Reporting and governance

For this research, the SCI study manager will be Senior Manager – MEAL, E&L to whom the study team will report, and she/he will be responsible for approving all the deliverables. Project Manager will supervise the consultant’s work in the field. The following regular reporting and quality review processes will also be used:

- A written Progress Report (1-page) by email to the Save the Children study Manager every week, documenting progress, any emerging issues to be resolved and planned activities for the next month.

- Consultant team will share draft and full report as per Save the Children provided reporting template.

A draft and final report including the raw data should be submitted to Save the Children in Bangladesh in both hard and soft copy. The ownership of the report for publication rests with Save the Children in Bangladesh. All the data and reports including the findings and recommendations will remain the property of Save the Children in Bangladesh and must not be published or shared with a third party.

The Technical Director-Evidence and Learning will be accountable for approving the final study report.

# Study management

The Consultant team lead will report to the Senior Manager – MEAL, E&L, SCI. The below table outlines the timeline for the study, key activities, and deliverables (in bold), as well as who is involved and responsible for them. The final timeline and deliverables will be agreed upon at the inception phase.

| What | Who is responsible | By when | Who else is involved |
| --- | --- | --- | --- |
| Study tender submissions due | Project Finance, Admin | 10 November, 2023 | Procurement Team |
| Tender review and selection of study team | Procurement Bidding Committee member | 15 November, 2023 | Sr. Manager-MEAL |
| Documentation review, desk research | Study team | 07 January, 2024 | Sr. Manager-MEAL, Manager SWAP |
| Consultation | Study team | 07 January, 2024 | Sr. Manager-MEAL, Manager SWAP |
| Inception report, Review of inception report, Finalising Data collection tools | Sr. Manager-MEAL, Manager SWAP | 30 January 2024 | Sr. Manager-RLK |
| Logistical arrangements | Study team | 28 February, 2024 | Manager SWAP, Technical Specialist MEAL |
| Translate the training package to Bangla | Study team | 28 February, 2024 | Manager SWAP |
| Data collection | Study team | 1 April-30 June 2024 | Manager SWAP, Technical Specialist MEAL |
| Data management and analysis (coding, transcriptions, data cleaning, integration, and analysis) | Study team | 10 July, 2024 | Sr Manager-MEAL, Technical Specialist MEAL |
| First draft of the Final study report | Study team | 20 July, 2024 | Sr. Manager-MEAL, Manager SWAP |
| Review of first draft report | Sr. Manager-MEAL, Manager SWAP | 1 August, 2024 | Sr. Manager-RLK |
| Meeting with research team to finalize the report | Study team | 7 August, 2024 | Sr. Manager-MEAL, Manager SWAP |
| Validation of study findings and recommendations | Sr. Manager-MEAL, Manager SWAP | 16 August, 2024 | Sr. Manager-RLK |
| Scientific paper | Study Team | 30 August October, 2024 | Sr. Manager-MEAL, Manager SWAP |
| Final study report and submission of data and analyses | Study team | 15 September 2024 | Sr. Manager-MEAL, Manager SWAP |
| Knowledge translation materials | Study team | 30 September, 2024 | Sr. Manager-MEAL, Manager SWAP |

# dissemination plan

The study findings will be mainly used to make FCC a Global resource for sustainability. Also National Newborn Health Program & IMCI and GoB has already started piloting Immediate Kangaroo Mother Care (IKMC) and M-SCANU in districts of Bangladesh and FCC might be an effective intervention for successful integration of IKMC with the level-2 neonatal intensive care units in Bangladesh. There is a potential to incorporate FCC in the next sector plan for further scale up along with IKMC and M- SCANU. Furthermore, the study findings will be shared with the project team both internal and external. The report will be prepared as well as a brief will also be prepared and will be shared with the donor, member, country office and other project stakeholders to help inform further programming.

# Research team and Selection Criteria

The consultant (individual/firm) is expected to facilitate the process to collect IRB approval. To be considered, the research study team members together must have demonstrated skills, expertise and experience in:

The Consultant must have demonstrated skills, expertise, and experience in:

- Advanced degree in Public Health/Sociology/social science, health services research and at least 8 years of relevant experience in undertaking health service assessments, and outcome assessments or service availability mapping.

- Designing and conducting research using quantitative, qualitative and mixed methods in Bangladesh in the context of Maternal, Newborn, Child Health (MNCH) services in public and private sectors

- Conducting research and/or assessment in the of gender and power analysis.

- Conducting ethical and inclusive research and/or assessment involving children and child participatory techniques.

- Managing and coordinating a range of government, non-government, community groups and academic stakeholders

- Extensive experience of theories of change and how they can be used to carry out.

- Good report writing and communication skills in English.

- Timely delivery of expected outputs/deliverables, possession of good work ethics as well as punctuality and compliance with agreement in the contract.

- Knowledge and experience of using advanced statistical packages for analysis of data.

There is a high expectation that:

- Members of the research team have a track record of working together.

- Team leader will be appointed considering seniority and experience in leading complex situation analysis, and who has the ability and standing to lead a team on a common goal.

- Ability to commit to the terms of the project and have adequate and available skilled resources to dedicate to this complete the results over the period.

- Has a strong track record of working flexibly to accommodate changes as the project is implemented.

# schedule of payment

The payment will be made through account pay cheques/EFT with the following payment mode:

- Upon approval of inception report & study tools-30%

- Upon submission of first draft study Report: 50%

- Upon approval of final study report: 20%

# TECHNICAL EVALUATION CRITERIA

The organization will assign a committee composed of management and technical team to evaluate the proposals submitted by consultant (individual/firm). The selection committee will evaluate the bidders based on the criteria set below. The submitted proposals will be reviewed based on the set criteria.

| Criteria | Score |
| --- | --- |
| Technical Proposal (Desk Review) | 50 |
| Appropriateness of the study design and elaboration for choosing the specified study design | 15 |
| Sampling strategy, data collection methods (including the data collection tools), and data quality assurance plan | 15 |
| Required expertise (skills) and experience of the personnel of consultant (individual/firm) to conduct the study. | 10 |
| Roles and responsibilities assigned in undertaking and managing the study | 5 |
| Capability of the consultant/firm (management, technical and financial capacity) | 5 |
| Sustainability criteria2 Bangladesh-based consultant (individual/firm) using local resources (e.g., research assistants, note-takers) (10), Otherwise (0) | 10 |
| Oral presentation | 10 |
| Financial Proposal | 30 |
| Total | 100 |

Benchmark scoring point:

Step 1: To be a potential candidate to conduct the assessment, the bidder must score at least 50% in technical proposal.

Step 2: During the evaluation of technical proposals, from those obtaining at least 50% score in technical score, the top three proposals will be selected for further screening through oral presentation. The overall scoring should consider the technical proposal, the financial proposal, and oral presentation.

Step 3: Financial proposal will be reviewed and scored out of 30 for the top three proposals having scored at least 50% in technical proposal and the combined comparative statement will be conducted for only the top three candidates. Finally, SC will award the research to the highest scorer consulting firm.

### Financial Proposal

SC seeks value for money in its work. This does not necessarily mean "lowest cost", but quality of the service and reasonableness of the proposed costs. Proposals shall include personnel allocation (role / number of days / daily rates / taxes), as well as any other applicable costs.

# Annexes

Annex 1: SCI Child safeguarding policy

Annex 2: Major indicators

- Improve pre-partum identification and management of pregnant women with complications that can potentially lead to preterm birth in hospitals.

- Proportion of skilled birth attendants in program-supported health facilities demonstrating knowledge of pre-eclampsia/eclampsia (PE/E) early detection and management

- Proportion women who gave birth in program-supported facilities in the last 3 months at < 34 completed weeks and received one dose of ACS for risk of preterm birth

- Proportion of women with the diagnosis of severe pre-eclampsia and/or eclampsia who received the MgSo4 treatment according to MOHFW protocol in program-supported health facilities

- % of women with diagnosis of pPROM at <34 weeks GA who received treatment according to MOH protocol

- Improve essential care for all newborns and Improve facility-based care for small and sick newborns in hospitals.

- Proportion of newborns in the program-supported health facilities breastfed within 1h of birth

- Proportion of newborns born in the   program-supported health facilities who received immediate and thorough drying

- Proportion of newborns born in the program-supported health facilities who received immediate skin-to-skin contact

- Proportion of liveborns who were not breathing after additional stimulation who were resuscitated with a bag & mask in program-supported health facilities

- Strengthen QI processes to improve care for small and sick newborns and pregnant women in hospitals

- Proportion of project’s supported health facilities with functional QI process to improve care for small and sick newborns and pregnant women in hospitals

- Proportion of project’s supported health facilities with functional QI committee (at least 1 meeting in 3 months period)

- Introduce innovation/innovative approach to improve care for sick newborns in hospitals.

- Proportion of project’s supported health facilities with functional innovative approach to improve care for small and sick newborns in hospitals

- Proportion of project’s supported health facilities with functional ENC Live approach to improve care for small and sick newborns in hospitals

- Proportion of project’s supported health facilities with functional Vayu cPAP to improve care for small and sick newborns in hospitals

- Strengthening appropriate utilization of MNH services from the facility and practices of healthy MNH behaviours at household to improve care for small and sick newborns.

- Proportion of project’s supported health facilities with functional mechanism for appropriate utilization of MNH services from the facility and practices of healthy MNH behaviours at household to improve care for small and sick newborns

- Proportion of mother who have a Liveborn in the facility and received PNC 1 for newborn in the facility

- Proportion of mother who have a Liveborn in the facility and received PNC 1 for mother in the facility

| TOR prepared by: | Mohammad Sarwar Basher, Senior Manager – MEAL, E&L |
| --- | --- |
| TOR reviewed by: | Dr Goutom Banik, Advisor-Child Health |
| TOR endorsed by: | Dr Irtifa Aziz Oishee, Project Manager- SWAP |
| TOR approved by: | Md. Nasirul Islam, Technical Director – Evidence and Learning |
| Date of sign off: | 30 October 2023 |

If any Consultancy Service Provider, Freelancer or Contingent worker will have direct contact with children and/or vulnerable adults and/or beneficiaries and/or have access to any sensitive data on safeguarding and/or children and/or beneficiaries, it is the responsibility of the person receiving the consulting service to contact the local HR team and child safeguarding focal point to ensure vetting checks and on-boarding are conducted in line with statutory requirements, local policies and best practices guidance.