## Terms of Reference MAM (Moderate Acute Malnutrition) Research

| PROJECT NAME | Positive Deviance/Hearth (PDH) to treat Uncomplicated Moderate Wasting in Children under 60 months in Mymensingh, Bangladesh |
| --- | --- |

# PROJECT MANAGEMENT

Project Manager’s Name: Diane Baik

Stakeholders’ Names: Sunghyun Lee (WV Korea), Mezanur Rahman (WV Bangladesh) and Grana Selvi (SAPO)

# BACKGROUND/DESCRIPTION OF CONTEXT

#### 2.1 Acute Malnutrition

Acute malnutrition (AM), or wasting, is a life-threatening yet preventable condition caused by rapid weight loss or failure to gain weight, often due to inadequate food intake or disease. Children under five are especially vulnerable, with AM defined by weight-for-height z-score (WHZ/WLZ) <-2 SD, mid-upper-arm circumference (MUAC) <125 mm, or nutritional oedema.

Global crises—conflict, climate change, pandemics—have worsened AM. In 2022, 45 million children under five were wasted: 31.7 million with moderate acute malnutrition (MAM) and 13.3 million with severe acute malnutrition (SAM). SAM raises mortality risk 12-fold and contributes to over 1 million child deaths annually, though only 30% of affected children receive treatment. MAM coverage is likely even lower, as it’s often deprioritized. Notably, 75% of AM cases are outside humanitarian contexts, mostly in Asia (70%) and Africa (27%), highlighting the need for integrated, long-term strategies beyond emergency responses.

#### 2.2 2023 WHO Guidelines and New Evidence

In 2023, WHO released updated guidelines for preventing and managing AM in children under five. Current systems treat SAM and MAM separately using specialized formulated foods (SFFs) such as Ready-to-Use Therapeutic Foods (RUTF) and Supplementary Foods (RUSF), but these face major challenges: stockouts, high costs, and poor MAM treatment coverage.

While WHO supports separate strategies for SAM and MAM, SFFs show only moderate improvements in anthropometric recovery and have limited effect on MUAC or prevention of deterioration to SAM. Costs remain high—e.g., RUSF at $163 per child in Sierra Leone—while non-SFF alternatives show promise. World Vision reports its Positive Deviance/Hearth (PDH) model cost as little as $2–$9 per child across Vietnam, Bangladesh, and India.

WHO guidelines acknowledge the lack of high-quality evidence on sustainable, food-based MAM approaches, issuing only a good practice statement to promote nutrient-dense, local diets. Rohloff et al. argue these approaches could be more cost-effective than SFFs in contexts like India, but further research is needed.

Only one study has examined non-SFFs for SAM, not MAM, in India. Though outcomes (e.g., recovery time and weight gain) favored RUTF, methodological limitations obscure whether home-prepared foods were used as supplements or replacements.

#### 2.3 Child Nutrition in Bangladesh

Bangladesh is a strong context to test sustainable, non-SFF approaches given dense markets, active agriculture, and wide social behaviour change programme reach, but acute malnutrition (wasting) remains a persistent challenge.

According to Bangladesh DHS (BDHS) data from 2022, stunting and underweight prevalence have significantly reduced in the last 5-10 years. Historically, wasting fell from 16% (2011) to 8% (2017–18), but has since rebounded to 11% (2022)—underscoring vulnerability to shocks. Recent global estimates likewise place Bangladesh above 10% wasting, which is above WHO’s high threshold for wasting. Recent 2025 surveillance data shows acute malnutrition rates remain above 10% in Mymensingh Division such as Purbadhala Upazila which showed 15% prevalence.

Literature states persistent drivers and social determinants contributing to malnutrition include poor infant and young child feeding (IYCF) practices with minimum acceptable diet (MAD) among children 6–23 months at approximately 28.7% (BDHS 2022) and minimum dietary diversity at 38% (MICS, 2019), highlighting sub-optimal complementary feeding and the need for careful messaging on diverse local foods; low birthweight (about 14.5% of newborns), poverty/food insecurity, and WASH constraints. —pointing to the importance of nutrition-sensitive, multisectoral actions alongside targeted nutrition services.

Non-SFF, locally sourced, SBC-led strategies can be both relevant and scalable in Bangladesh—but should be paired with strengthened regular screening, IYCF counseling, proper referral and community-based rehabilitation programs integrated with WASH interventions, and increasing food access for hotspots with seasonal flooding or flash floods that disrupt crops and food access, such as Purbadhala Upazila in Netrakona District that have some village AM levels above 60%. Programs like PDH can help to prevent and stabilize wasting levels.

#### 2.4 National AM Protocols and Implementation Gaps

Bangladesh’s 2017 National Guidelines for Community-based Management of Acute Malnutrition in Bangladesh recommends treating MAM using energy and nutrient dense family food for MAM management (providing at least 700-1000 kcal/child/day with 25-30% energy from fat and 10-12% energy from protein additional to home food) or at an outpatient site or community outreach sites. It also states that children with uncomplicated SAM with good appetite and no bi-pedal odema could be treated in the community if there is a provision of such. However, World Vision Bangladesh reports no specific interventions are implemented in communities and SAM children are usually referred to health centres to be treated with RUTF. Instead, MAM and SAM children without medical complications are provided with basic health and nutrition services including timed and targeted counseling, growth monitoring and promotion (GMP) and infant and young child feeding (IYCF) counselling, health committee meetings for cooking demonstrations and health and nutrition and WASH education, Integrated Management Childhood Illness (IMCI) screening, Vitamin A, deworming and age-appropriate immunization.

Thus, limited targeted support is provided to uncomplicated MAM and SAM children and children’s health need to deteriorate further to be treated at a higher center for facility-based management of SAM according to national protocols. With acute malnutrition prevalence well above WHO’s critical threshold of 15%, the Bangladesh Ministry of Health needs to explore alternatives like PDH, especially given low adherence to national protocols.

#### 2.5 Positive Deviance/Hearth (PDH)

2.5.1 Overview:
Developed in 1990 in Asia, PDH is a non-SFF, community-based approach for underweight, MAM, and uncomplicated SAM children. It identifies “Positive Deviant” families whose nutrition practices promote better outcomes despite poverty. Caregivers attend 12-day Hearth sessions using local, nutrient-rich ingredients to prepare meals meeting calorie, protein, and micronutrient targets.

2.5.2 Suitability and Integration:
PDH is best suited for food-secure settings and close-knit communities. It may also complement food-aid programs, using these resources in menu design.

2.5.3 Effectiveness:
Evidence is mixed but promising. A 2023 meta-analysis showed greater improvements in WHZ, WAZ, and LAZ for PDH over SOC, though results weren’t statistically significant due to limited studies. However, more recent trials show PDH significantly reduced underweight and AM rates. In Burundi, PDH halved MAM prevalence in 12 days (from 17.9% to 8.3%, p<0.001). These results suggest PDH could reduce relapse and progression to SAM.

2.5.4 Cost-Effectiveness:
PDH is cost-efficient, with early implementation costs dropping dramatically at scale—from $17 to $8 per child. Integrated programs may cost up to $100 annually per child, still lower than RUSF.

- RATIONALE, AIMS, AND OBJECTIVES

Addressing AM sustainably requires exploring alternatives to SFFs, yet no studies globally have assessed the effectiveness of nutrient-dense diets for treating uncomplicated MAM (13,50). Rohloff et al. highlight in their review of WHO’s AM guidelines that relying on SFFs is unsustainable and call for more research on local, sustainable food solutions (15).

PDH is a low-cost, community-based dietary intervention effective for underweight children in food-secure settings (38,39,41). Grey literature shows its potential in treating uncomplicated AM in Burundian children with limited relapse and low implementation costs per child in Asia and Africa (34).

Currently, SFF treatments for AM typically use recovery from AM status alone as the discharge criterion. However, studies in Senegal and other countries show that children with both WAZ<-3 and MAM face lower recovery  (28.3% vs. 48.7%) and higher mortality risks (51,52). Given these findings, PDH should be explored as a sustainable non-SFF treatment for uncomplicated MAM, with a revised protocol incorporating both AM and a WAZ-based discharge criteria (38).

Mymensingh, Bangladesh has AM prevalence above 15% despite food security. National AM protocols exist, but interviews with World Vision Bangladesh reveal that improved nutrient-dense diets at home, SFF, and/or food-aid for MAM treatment is not widely implemented. This suggests the Ministry of Health could adopt a more cost-effective, sustainable approach if supported by evidence.

A multi-country study shows WHZ and MUAC should be used independently to diagnose acutely malnourished children (42) due to diagnostic discrepancies across countries (43). Accurate height and length measurements are critical for timely referrals, but CHWs often struggle with precision (43). Thus, the laser device that was validated in a recent study in Vietnam will be used to diagnose the children with wasting (WHZ/WLZ<-2.0SD).

### 3.1.1 Aim:

Overall aim of the research is to investigate sustainable approaches to treat children 6-59 months of age with uncomplicated moderate AM (WHZ/WLZ<-2.0SD and ≥-3.0SD or MUAC<125mm and ≥-115mm without oedema) in resource constrained settings with relative food security.

### 3.1.2 Objectives and Hypothesis:

- Objective 1: To evaluate the effectiveness of a non-SFF treatment intervention, Positive Deviance/Hearth (PDH), to treat (WHZ/WLZ≥-2.0SD or MUAC≥125mm (dependent on which criteria the child was admitted on), and WAZ≥-3.0SD and no oedema) uncomplicated MAM children 6-59 months of age compared to a SOC only group after a 12-week program in Purbadhala Upazila and to assess the likelihood of relapse by at 6 months (after recovery, child becomes WHZ/WLZ<-2.0SD or MUAC<125mm again).

- Hypothesis 1: The PDH+SOC program is more effective in rehabilitating uncomplicated MAM children compared to the SOC only group.

- Objective 2: To qualitatively assess the caregiver acceptance of the program, sustainability of the program by Ministry of Health, and scalability of PDH Programming in Bangladesh’s context.

# DETAILS OF METHODS

4.1 Study Design and Study Sites. A cluster-randomized controlled superiority trial will be conducted in Purbadhala Upazila in the Mymensingh Division of Bangladesh. Purbadhala faces seasonal or flash flooding contributing to season food insecurity and is known for the poor IYCF and WASH practices in communities. MAM prevalence in the last unpublished annual census was slightly above 15% (2025).

The units of randomization will be union and will be randomly assigned to the intervention or control group to limit contamination between groups. The intervention unions will receive the non-SFF protocol through PDH along with the SOC and the control group will receive only the SOC through the Ministry of Health. The study includes a total of 20 clusters. See Table 2 which outlines the interventions and protocols for PDH and SOC.

Table 2 – Nutritional protocol and interventions for PDH and SOC for Study 2

| Topics | PDH | SOC |
| --- | --- | --- |
| Program preparation and design | - Formative research conducted using WV PDH Trainer of Facilitator manual to design 6 key contextualized messages and design 2 nutrient-dense meals (Hearth meal) consisting of locally available low-cost foods | - Provide health and nutrition counselling to caregivers using the timed and targeting counselling manual (IYCF practices, disease prevention and basic treatment (diarrhoea, acute respiratory infection) and nutrition care during illness - Ensure all children are given age-appropriate immunization, deworming, and Vitamin A in past 6 months |
| Admission Criteria | - WHZ/WLZ <-2SD and ≥-3SD or MUAC <125mm and ≥115mm - No medical complications (e.g. no features of severe illness as defined by Integrated Management of Childhood Illness – no severe nausea/vomiting, no severe dehydration or pneumonia) (68) - No Oedema on feet - Pass Appetite Test (consumption of 30g of Hearth meal within 20 mins) | - WHZ/WLZ <-2SD and ≥-3SD or MUAC <125mm and ≥115mm - No medical complications (e.g. no features of severe illness as defined by Integrated Management of Childhood Illness – no severe nausea/vomiting, no severe dehydration or pneumonia) (68) - No Oedema on feet - Pass Appetite Test (consumption of 30g of Hearth meal within 20 mins) |
| Treatment Frequency and Group Size | - 12 Days of Hearth (8-10 caregivers-children pair per Hearth session) every month for 3 months - Caregivers bring all low cost, nutrient-dense ingredients for Hearth meal and cook it together to practice and learn (if too poor, caregivers are allowed to bring firewood or water to be used at the session); children fed Hearth meal (consecutive 12 times), Caregivers given 6 key Hearth messages twice in 12 days (1 message per day) | - Meet at least once a month with health workers during GMP (10 mins) and community health meetings (about 2 hours per session). Cooking demonstration is provided during community health meetings and caregivers hear comprehensive messaging. |
| Source of Food Contribution | - Caregivers bring all ingredients for Hearth meal and cook it together to practice and learn (use low cost, nutrient-dense foods identified through formative research) | - Caregivers bring some ingredients for cooking demonstration and Ministry of Health/WV provides some |
| Follow-up protocol | - 2 weeks of Follow-up by volunteers using mobile phones (2-3 times a week to ensure behaviour change sustained at home) - Repeat Hearth if child did not rehabilitate at 3 months - Hearth sessions repeat once every 3 months - Assess recovery at 3 months (Day 90) - Assess relapse at 6 month follow-up (Day 180) | - Caregivers are included in Savings Groups - SOC group will be provided opportunity to join PDH program at end of study - Assess recovery at 3 months (Day 90) - Assess relapse at 6 month follow-up (Day 180) |
| Dosage of non-SFF | Supplementary Nutrient Dense Hearth Meal given for 12 days each month for 3 months: - Calorie (600–800 kcal), protein (25–27g), vitamin A (300 RAE), vitamin C (15–25mg), iron (≥8mg), and zinc (≥3mg) requirements - electronic menu calculator used | Cooking demonstration conducted once a month: - Utilize same menu as PDH |
| Criteria for Cured/Recovered | - WHZ/WLZ≥-2.0SD and/or MUAC≥125mm (dependent on which criteria the child was admitted on) and WAZ≥-3.0SD up to Day 90 - No Oedema on feet - The children who did not recover after 1 round of Hearth in the first 3 months will repeat in another round of Hearth (recovery criteria of WAZ≥-2SD in addition to above) | - WHZ/WLZ≥-2.0SD and/or MUAC≥125mm (dependent on which criteria the child was admitted on) and WAZ≥-3.0SD up to Day 90 - No Oedema on feet |
| Criteria for Defaulter | - Absent more than 2 times each month | - Absent more than 2 times over 90 days |
| Relapse | - Become MAM or SAM after recovery at Day 180 and 1 year | - Become MAM or SAM after recovery at Day 180 |
| CHW Supervision | - Project staff supervise Hearth volunteers monthly | - Project staff supervise CHWs monthly |
| Referral to Health Facility | - If child does not gain minimum 400g within 30 days after second round of Hearth, child is referred to health facility for underlying medical complications | - Child referred to health facility if child is SAM (MUAC<115mm and/or WHZ/WLZ<3.0SD or oedema present), or has medical complications or poor appetite |

Data will be collected at Baseline (Day 1) and Endline (Day 90/Week 12), except relapse data will be collected at Day 180. All data at Baseline and Endline will be collected by hired enumerators with previous experience in anthropometry and data collection with a minimum high school diploma (different enumerators than Study 1). Detailed schedule of enrolment, intervention, and assessments for PDH Intervention group can be found in Figure 4. The PDH+SOC group and SOC only group will also be followed up for weight, height/length, and MUAC data at Day 12, 30, and 60 using volunteers for routine program monitoring. An interviewer administered questionnaire will be collected from caregivers at Baseline and Endline to collect information on the descriptive data, length/height, weight, and MUAC.  Hired enumerators will also collect height, weight, and MUAC data at Day 180 to identify relapse cases. To control for bias, the data will be collected from both groups by the same team of anthropometrists at the same time of day since height/length declines over the day.

In addition, 4 enumerators from the local academic partner will conduct Focus Group Discussions with PDH caregivers participating in PDH sessions at assess acceptability of the PDH intervention and barriers and facilitators to participation in behaviour change. We will conduct 8 key informant interviews with PDH volunteers, commune and health centre staff to obtain information on, PDH approach’s sustainability and ownership (what factors shape local government and community willingness and capacity to continue PDH beyond the study period), and scalability (what systems, organizational and policy factors – e.g. health worker support, supply chain, political will – might affect the integration or expansion of PDH.

Primary outcome: Comparison of Recovery Rate of uncomplicated MAM children in PDH+SOC group vs. SOC only group at 90 Days after enrollment (Recovery defined as WHZ/WLZ ≥-2SD or MUAC ≥125mm (dependent on which criteria the child was admitted on) and WAZ≥-3.0SD of the WHO standards and absence of oedema of feet)

Secondary outcomes (all measured pre- and post-intervention (90 Days), except relapse measured at 180 Days):

- Defaulter,

- Average daily weight gain by 90 days,

- Average daily MUAC gain by 90 days,

- Average length time until MAM recovery (in days)

- Relapse to MAM (at Day 180/6 month)

- Difference in Relapse comparing discharge criteria

- Comparison of MAM recovery rate for High risk vs. low risk MAM

- Program Cost per beneficiary

- Qualitative Data Analysis: Scaling-up PDH to address MAM in Bangladesh (FGDs, KIIs)

Graduation Criteria: WAZ≥-3SD AND i) WHZ/WLZ≥-2SD and/or ii) MUAC≥125mm and no oedema (depending on which criteria was used for admission)

Graduation Criteria not met

Measure Weight, MUAC, and Length/Height

*Note: Children with disabilities that make assessing weight difficult (e.g. missing a limb) will graduate if WAZ remains same or improves by 3 Months

*

Measure WAZ, WHZ/WLZ and MUAC

Figure 4. Schedule of enrolment, interventions, and assessment (PDH protocol)

Sample Size. Sample size calculation was made using R Studio. Assuming a conservative intra-cluster correlation coefficient (ICC) of 0.1 based on results of another study assessing stunting in Bangladesh, then with 10 clusters in each arm – each recruiting 20 children (having adjusted for a 30% loss-to-follow up rate), we would have 90% power to detect a 30% inter-group difference in the percentage of children recovered at 90 days comparing the PDH+SOC group vs. SOC only group and estimating the recovery from uncomplicated MAM to be 5% for the SOC only group, a conservative difference in recovery because Asia seems to have a trend of slower rehabilitation than most African countries (19,39), using a two-sided statistical test at the 5% level of significance. Therefore, with a cluster size of 20 and 20 clusters (20 villages), a total of 400 children 6-59.9 months of age will be recruited in this Bangladesh study.

4 total Focus Group Discussions (FGD) will be conducted with 10 caregivers per FGD and 10 PDH volunteers per FGD in 4 randomly selected villages (in the PDH arm) and 4 key informant interviews (KIIs) including Ministry of Health staff.

Sampling. A preliminary nutrition survey was conducted in the Purbadhala Upazila in February 2025. The list will be utilized to estimate the number of MAM children per cluster to ensure adequate sample size is met. All uncomplicated MAM and SAM children will be included in the study, but only MAM children will be included in the sample size. At times when there are <6 MAM children to run a Hearth session, some children who are not AM, but has a WAZ<-2 may be included in the PDH program, but not in the study. An additional preliminary nutrition survey will be conducted 2-4 weeks before the baseline assessment to identify all the MAM children to be included in the study. Simple random sampling will be used from those who meet the inclusion criteria to select the children to be admitted for the study. Randomization sequence will be generated using an online sequence generator (70) to select the clusters and assign them to the PDH+SOC or SOC only group. Due to the nature of the interventions, this is not a fully blinded study. CHWs and project staff must know if they are implementing PDH+SOC so they know how to treat the MAM children and follow-up. However, since clusters are divided at village level, it will reduce contamination between the intervention and control groups (see Figure 5 for detailed sampling diagram).

Figure 5. Sampling flow diagram for Study 2

Trainings and Tools. An 8-day training will be provided for PDH using World Vision’s Positive Deviance/Hearth (PDH) Training of Facilitators Manual and on Child-Caregiver Clubs using the Child-Caregiver Club Training Manual and a 3-Day refresher training will be given after the first month. All CHWs and enumerators will be trained in how to collect height/length (using laser device), weight, and MUAC measurements accurately as mentioned in Study 1.

Statistical Analysis Plan. Statistical analysis will be conducted at the individual level with appropriate adjustment for clustering within 20 clusters. Descriptive summaries of participant characteristics by arm will be tabulated. Descriptive statistics for continuous variables will include the mean, standard deviation, median, range and number of observations. Categorical variables will be presented as counts and percentages. The main analysis of the primary and secondary outcomes will be intention-to-treat given that this is a superiority trial. Additionally, per-protocol analyses will be presented for all secondary outcomes. To estimate the treatment effect, a Difference-in-Difference model will compare the mean change in WHZ/WLZ, MUAC, and WAZ.

For the qualitative data analysis, FGDs and Key Informant Interviews will be recorded and transcribed verbatim in Bangla translated into English using MS Word, and checked by bilingual enumerators for accuracy. Transcripts will be uploaded to MAXQDA and analyzed using both deductive (predefined themes) and inductive (emerging themes) coding. A code mapping exercise will be conducted and finalized as a codebook. Frequency analysis will be used to measure how often themes appear and report as raw counts or percentages.

Roles and Responsibilities:

- London School of Hygiene and Tropical Medicine and WVI will be the PI and lead in managing the overall research project and stakeholders, providing technical guidance and leading design workshop for the PDH MAM research.

- WVK will be funding the project in FY25-FY27, provide project management support.

- WVB will be the field partner that obtains permission from the Ministry of Health and other in-country partners (e.g. local academic partner) to conduct the field visits and the research. WVB will oversee the day-to-day program implementation for the research.

- Local Partner will assist in data collection at Baseline, 3 months and 6 months to avoid conflict of interest and will assist in the translation and data cleaning of the qualitative data analysis and drafting parts of manuscripts.

# ASSIGNMENT OBJECTIVE

The main objective of this research proposal is to conduct the PDH MAM research in Mymensingh Division This will serve as evidence for the National Institute of Nutrition (NIN) and Ministry of Health to consider PDH as an appropriate approach to treat and prevent moderate wasting in Bangladesh. It will also address a large evidence gap in literature in non-specially formulated foods (dietary approach) to treat and prevent moderate wasting, especially in Asia where greater than 70% of wasting is found, yet limited studies have been conducted.

# METHODOLOGY

- Prior to attending the field visit, LSHTM/WVI will facilitate a design workshop to finalize the research design and study protocols including developing the quantitative and qualitative tools. We will work on preparing for the field visit, ensure all permission is granted by appropriate partners in-country, and finalize an agenda for data collection logistics.

- LSHTM/WVI will work with WVB to develop consent forms and finalize all tools to submit for IRB approval in Bangladesh to Dhaka University and LSHTM. The consent forms will all be translated and printed prior to the field visit.

- PDH, CCC, and anthropometry refresher trainings will be conducted for project staff so they could conduct the refresher trainings for the volunteers and commune health staff.

- Baseline will be conducted by the local academic partner.

- Program will begin and data collected at appropriate times.

- Midline will be conducted by the local academic partner at 3 Month.

- Endline will be conducted by the local academic partner at 6 Months.

- Data analysis will be conducted by the local partner and LSHTM.

- LSHTM/WVI will organize a dissemination workshop with WVB, NIN, and MOH.

# DATA COLLECTION TIMELINE (Tentative)

| Start Date | October 1, 2025 (Project Start date) (Data Collection: April 2026 (Baseline) and July 2026 (Midline) and if funding allows, Oct 2026 (Relapse) |
| --- | --- |
| End Date | Sept. 30, 2027 |

# EXPECTED TANGIBLE DELIVERABLES

Table 1.0 – Expected Tangible Deliverables

| Deliverables |  | Tasks | Actors | End Date |
| --- | --- | --- | --- | --- |
| 1 | Study Protocol for the overall research | Develop the research proposal for the pilot of the laser height/length measuring device with detailed timeline and budget for FY24 | Diane Baik (LSHTM/WVI), WVB | Oct. 2025 |
| 2 | Submit IRB package for local and international approval | Consolidate all the docs needed for the IRB package Submit the IRB package to Dhaka University | Mezan/Diane | Dec. 2025 |
| 3 | Get Local IRB approval | Pay for IRB when approved | Mezan/Diane Baik | Jan/Feb 2026 |
| 4 | PDH, SOC, and Anthro refresher training workshop and conducting formative research (Situational Analysis and PDI to design Hearth messages and menus) | Facilitate refresher training workshop for Commune Health workers and volunteers | WVB and Diane Baik (Share all findings with Diane from Formative Research) | Jan/Feb 2026 |
| 5 | Formative Research | PDH – Situational Analysis and Positive Deviance Inquiry | WVB | Jan – March 2026 |
| 6 | Logistical Field Prep | Book hotels, mobilize community, mobilize volunteers, health centre staff and experts (WVB) | Mezan/Diane | Mar 2026 |
| 7 | Enumerator Training | Training Enumerators in Anthropometry Techniques, Caregiver Survey, KII/FGD tools | Local Partner (overseen by LSHTM/WVB) | March 29-31, 2026 (4 days) |
| 8 | Baseline Data Collection | Quantitative data collection | Local Partner with support from WVB and LSHTM | April 2-7, 2026 (5 Days) |
| 9 | PDH Implementation in 10 villages SOC Implementation in 10 villages | PDH rollout in 10 intervention villages Provide basic health and nutrition services to SOC villages | WVB | Apr – Jul 2026 |
| 10 | Data Analysis Output | Data analysis led by Diane | Local academic partner, Diane Baik | Apr 2026 |
| 11 | Midline Evaluation Data Collection | Follow-up at Month 3 | Local Partner, WVB, Diane Baik | July 2026 |
| 12 | Data Analysis Output | Data analysis led by Diane | Diane Baik, Local Partner | Jul/Aug 2026 |
| 13 | Relapse Evaluation Data Collection (6 month) | Follow-up at Month 6 | Local Partner | Oct 2026 |
| 14 | Relapse Data Analysis Output | Data analysis led by Diane | Diane Baik, Local Partner | Nov-Jan 2026 |
| 15 | Manuscript Draft (Quantitative) | Delegate different sections of manuscript to various team members to write up | Diane Baik Local Academic Partner WVB | Jan-April 2026 |
| 16 | Manuscript Draft (Qualitative) | Delegate different sections of manuscript to various team members to write up | Diane Baik Local Partner WVB | July 31, 2027 |
| 17 | Dissemination Workshop | Develop PowerPoint presentation | Organized by WVB and Diane Baik All | November 2027 |

# Timeline

| Topic | Tasks/Activities | FY25 | FY26 |  |  |  | FY27 |  |  |  | FY28 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Jul 25-Sep 25 | Oct 26-Dec 26 | Jan 26-Mar 26 | Apr 26-Jun 26 | Jul 26-Sep 26 | Oct 26-Dec 26 | Jan 27-Mar 27 | Apr 27-Jun 27 | Jul 27-Sep 27 | Oct 27-Dec 27 |
| PDH MAM cRCT Study 2 | Study Protocol for the overall research |  |  |  |  |  |  |  |  |  |  |
|  | Submit IRB package for local and international approval |  |  |  |  |  |  |  |  |  |  |
|  | Get IRB approval |  |  |  |  |  |  |  |  |  |  |
|  | PDH, CCC, and Anthro refresher training workshop |  |  |  |  |  |  |  |  |  |  |
|  | Logistical Field Prep |  |  |  |  |  |  |  |  |  |  |
|  | Baseline Evaluation Data Collection |  |  |  |  |  |  |  |  |  |  |
|  | Data Analysis Output |  |  |  |  |  |  |  |  |  |  |
|  | Midline Evaluation Data Collection |  |  |  |  |  |  |  |  |  |  |
|  | Data Analysis Output |  |  |  |  |  |  |  |  |  |  |
|  | Manuscript Draft (Quantitative) |  |  |  |  |  |  |  |  |  |  |
|  | Manuscript Draft (Qualitative) |  |  |  |  |  |  |  |  |  |  |
|  | Dissemination Workshop |  |  |  |  |  |  |  |  |  |  |

- BUDGET

As per requirement.

# REQUIRED INPUTS AND RESPONSIBILITIES OF DIFFERENT STAKEHOLDERS

# WVI/LSHTM will:

- Provide research design and technical leadership

- Build capacity of project staff and provide field support

- Be responsible for leading the develop of data collection tools, data management and analysis

- Serve as the coordinating body between WVB, external partners (LSHTM and local academic partner), and donor (WVK)

- Responsible for resource mobilization, other donor engagement and budget management

- Lead advocacy and dissemination activities

WV Bangladesh will:

- Get approval by all appropriate partners in-country prior to the field visit

- Invite appropriate National Ministry of Health (MOH) staff and National Institute of Nutrition staff

- Submit IRB package to Dhaka University and obtain IRB approval prior to data collection

- Make arrangements for the field visit to Mymensingh Division and in Purbadhala AP

- Liaise between local academic partner and WVI

- Provide invitation letters so visa can be received in time for WVI staff

- Arrange for airport pickup and drop off for WVI, WVB, local partners

- Timely coordination when inputs/meetings are required to maintain agreed schedules and quality of end deliverables

- Review and provide feedback for the Final Presentation of findings

- Write, review and provide feedback for final draft of manuscript

- Assist in data cleaning, developing M&E data collection AP, and translation of consent forms (if needed)

WV Korea will:

- Provide funds once WVI and WVB issues Direct Charge or PA/SA for the travel expenses

- Review and provide feedback for the Final Presentations of Final Research Findings

- OUTCOMES FROM RESEARCH:

### 12.1 Global Health Impact:

- Generation of Robust Evidence on Non-Specially Formulated Food (non-SFF) Approaches

  - Demonstrate that PDH, using locally available, non-SFF diets, is a viable alternative to traditional supplementary feeding for treating uncomplicated MAM.

  - Address the global evidence gap for dietary approaches that do not rely on RUSF or other SFFs, especially critical in low-resource or non-supply chain dependent settings.

- Thought Leadership in Asia and Beyond

  - Position World Vision as a leading voice and innovator in community-based, sustainable solutions for MAM management—especially in the Asian context where local foods are available year-round

  - Open opportunities for cross-learning and replication in similar LMIC settings globally.

- Contribution to Global Nutrition Policy Dialogue

  - Add empirical data to ongoing debates around integrating treatment and prevention of MAM within existing health and community systems.

  - Inform broader discussions on revising WHO and national protocols to include alternative, community-based approaches to acute malnutrition.

12.2 Strategic and Programmatic Impact for World Vision:

- National-Level Advocacy in Bangladesh

  - Inform direct advocacy efforts with the Bangladesh Ministry of Health to revise in-country protocols on MAM treatment and prevention.

  - Support policy-level recommendations to integrate PDH as a nationally endorsed, scalable approach to MAM.

- Programmatic Strengthening through Revised PDH+ Manuals

  - Revisions of World Vision’s PDH+ training manuals, incorporating updated admission and graduation criteria aligned with research findings.

  - Enhance operational guidance for field teams implementing PDH in nutrition-sensitive and nutrition-specific programs.

- Global Knowledge Dissemination via Webinars

  - Conduct internal and external webinars targeting practitioners, donors, and ministries of health.

  - Facilitate cross-country learning and engagement with the broader nutrition and health community.

- Evidence-Based Resource Mobilization

  - Provide compelling data and success stories for funding proposals to scale PDH in other regions (e.g., Africa, South Asia).

  - Increase donor confidence in investing in sustainable, community-owned solutions to acute malnutrition.

- Study Protocol

- Selection criteria and payment milestones.

Technical Proposal – Understanding of the Objectives/ToR-40, Relevant working experience-25, Team Composition-15, Presentation (only who get pass score) 20.

| Criteria Category | Specific Considerations | Weight (%) |
| --- | --- | --- |
| 1. Technical Proposal Quality |  | 40% |
| a. Methodological soundness | Mixed-methods design, sampling rigor, data triangulation plan, ethical compliance, and alignment with ToR | 15% |
| b. Understanding of program context and ToR | Ability to reflect key objectives, context, and constraints in Bangladesh and program complexity | 10% |
| c. Secondary data integration and learning focus | Approach to literature review, use of program data, and learning/adaptive management strategy | 5% |
| d. Work plan and timeline feasibility | Realistic and detailed timeline, risk mitigation plan, flexibility | 10% |
| 2. Relevant Experience |  | 25% |
| a. Inclusive market systems, WEE, nutrition | Experience evaluating similar research/studies, or nutrition programs | 15% |
| b. Experience in Bangladesh or South Asia | Contextual knowledge, Bangla-speaking team members, past work with rural and vulnerable populations | 5% |
| c. Experience with mixed-methods project reviews | Showcasing at least 2 similar past assignments with samples | 5% |
| 3. Team Composition & Expertise |  | 15% |
| a. Lead consultant qualifications | Advanced degree, 7–10+ years in evaluation/research, sector experience (nutrition/anthropometric survey/food security) | 5% |
| b. Team skills mix | Nutrition, Public Health, enumerators with gender balance, disability inclusion expertise. | 5% |
| c. Data analysis / software skills | Proficiency in Epi Info/ENA for SMART/SPSS/Stata and mobile data collection (e.g., Kobo, ODK) | 5% |
| 4. Presentation (only who get pass score) |  | 20% |

Note:

1st stage: Technical proposal will be reviewed within 80 marks, firms who score 70% (56) will call for presentation summary sharing and Q&A

2nd Stage: Presentation consists for 40/50 minutes where consulting firm/consultant will share details discussion on the study process. Score 20 and pass marks 70% (14).

3rd stage: Only those bidders who achieve at least 70% in 1st Stage and 70% in 2nd Stage separately will be shortlisted for QCBS evaluation.

- Payment for Services and Expenses

| Milestone |  | % of Total value |
| --- | --- | --- |
| 1. | After submission of inception report with tools 20% of the total amount shall be made | 20% |
| 2. | After submission of final baseline report accepted by WVB 15% of the total amount shall be made | 15% |
| 3. | After submission of midline draft report 20% of the total amount shall be made | 20% |
| 4. | After submission of midline final report accepted by WVB 15% of the total amount shall be made | 15% |
| 5 | After submission of endline draft report accepted by WVB 15% of the total amount shall be made | 15% |
| 6 | After submission of endline final report accepted by WVB 15% of the total amount shall be made | 15% |
| Total |  | 100% |

Note: VAT and Tax will be deducted as per government rules and regulations. Quoted price should be including VAT/TAX and all other service prices.

- Contact Person Details

| Name | Mezanur Rahman |
| --- | --- |
| Designation | Lead- Health, Nutrition and WASH, World Vision Bangladesh |
| Email | MdMezanur_Rahman@wvi.org |
| Mobile No: | +88 01713490725 |

globalnutritionreport.org+3unicef.org+3etoolkits.dghs.gov.bd+3

Data on the situation of children in Bangladesh | UNICEF Bangladesh

Mapping the prevalence and socioeconomic predictors of low birth weight among Bangladeshi newborns: evidence from the 2019 Multiple Indicator Cluster Survey | International Health | Oxford Academic

WAZ is included in the rehabilitation criteria based on recent findings that children with WHZ<-2 or MUAC<125mm and WAZ<-3 are an especially vulnerable group that requires a higher intensity of nutritional support than currently recommended. It is recommended that longer or improved treatment may be necessary and the timeline and definition of recovery likely needs to be reviewed (52)

https://journals.plos.org/globalpublichealth/article?id=10.1371/journal.pgph.0004890