Draft Gann Chart for

End Evaluation of Mithapukur AP FY-2025

Phase out FY 2026

| Date | Description of activity | Remarks |
| --- | --- | --- |
| 25/11/2024 | Developed End Evaluation ToR |  |
| 26/11/2024 | ToR Sent to NO, PQ Manager for review |  |
| 05/12/2024 | Received feedback from NO, PQ Manager |  |
| 10/12/2024 | Re-worked and finalize the ToR and |  |
| 10/12/2024 | ToR will be sent Sr. Manager for final review |  |
| 12/12/2024 | ToR will be sent SO, for review and suggestion |  |
| 19/12/2024 | Received feedback from SO |  |
| 22/12/2024 | Incorporation SO feedback & finalize the ToR |  |
| 29/12/2024 | ToR will be sent SCM department for tendering | If the firm the mentioning criterion as per the ToR then re-tendering process might take place which will be time consuming and affect the time line. |
| 15/01/2025 | Evaluation consulting firms technical & financial proposal |  |
| 16/01/2025 | First meeting with selected consulting firm |  |
| 20/01/2024 | Final contract sign with consulting firm |  |
| 25/01/2024 | Firm will develop questionnaires and send to Pirganj AP for review |  |
| 30/01/2025 | Provide feedback on End evaluation questionnaire to the firm |  |
| 01-02/02/2025 | Enumerator’s training |  |
| 04-12/02/2025 | Field level quantitative and qualitative data collection |  |
| End of February 2025 | The firm will share draft report |  |
| March 10, 2025 | Provide feedback to the firm |  |
| March 20, 2025 | Produce final report and submit to Mithapukur AP |  |
| End of March 2025 | Final report will send to SO |  |

Prepared by: Mithapukur AP team

Rangpur ACO, PLC, WVB