Terms of Reference (ToR)

for

Project Impact Study (EVPRA) in Bangladesh

Establishing Vulnerable Peoples’ Rights and Access to Social Safety Net Programmes (EVPRA) Project

This Project is funded by the European Union and implemented by the World Vision, Pollisree and PUMDO.

World Vision

The contents of this publication are the sole responsibility of World Vision, Pollisree and PUMDO and can in no way be taken to reflect the views of the European Union.

Impact Study Summary

| Project | Establishing Vulnerable Peoples' Rights and Access to Social Safety Net Programmes - EVPRA |
| --- | --- |
| Project timeline | January 2016 – December 2019 |
| Assignment type | Project Impact Study |
| Impact Study Purpose | To identify and document the changes in Govt. Institutions/Authorities, Policy documents, Civil Society Organizations and Individual households because of the EVPRA action in the form of case study and a video documentary. |
| Primary Methodologies | 1. Conduct Lesson Learned Workshop 2. In-Depth Interview (IDI) of beneficiaries and govt. officials 3. Focus Group Discussions (FGDs) 4. Case Study and Videography 5. Exploratory walk |
| Study duration (Start date) | 01/09/2019 |
| Anticipated release date of the study outputs | 31/10/2019 (60 days including weekends and holidays) |

- Background/Introduction

World Vision Bangladesh (WVB) is looking for an individual consultant/consulting firm to conduct the Project Impact Study for the EU funded action; “Establishing Vulnerable Peoples' Rights and Access to Social Safety Net Programmes” (EVPRA) in Bangladesh. This project is implemented through a partnership led by World Vision United Kingdom (WVUK) and direct implementation by World Vision Bangladesh (WVB), Pollisree and PUMDO (Peoples Union of the Marginalized Development Organization) in three sub districts(Fulbari, Birampur and Dinajpur Sadar) of Dinajpur District led by Pollisree and two sub-districts(Panchbibi and Sadar) of Joypurhat District where PUMDO is leading implementation. WVB provides day to day oversight management, Monitoring & Evaluation and technical support to both Pollisree and PUMDO based in Dinajpur.  The Project started in January 2016 and will end by December, 2019 total budget of € 1656683 with the overall objective of the Project is to Empower Civil Society Organisations (CSOs) working for the rights and development of ethnic minority groups, Local Authorities (LAs) and communities, to promote the most vulnerable peoples' social development through access to Social Safety Net Programmes (SSNPs) in targeted two Districts.

Total population of those selected sub-districts are 1,356,052 of which 40,678 are ethnic minority. The Project targets 278,668 extremely poor people of these working areas among them 39,953 are ethnic minority (Source: Population and Housing Census 2011). Over the implementation period, EVPRA has worked with 100 Civil Society Organisations (CSOs) composed of/led by ethnic minority people.

The Project has utilised Citizen Voice and Action (CVA) which is a proven WV's local level social accountability approach, by empowering CSOs, their membership and communities to increase their influence on access to SSNPs and related policies, and strengthen the capacity of duty bearers to respond positively to citizen participation in service delivery decision-making and monitoring processes. Trained local CSOs and CVA working group members have run that approach, targeted all vulnerable people (ethnic minority and other extreme poor) in the local communities to participate in the CVA process, together with Local Authorities-LAs.

This is being achieved through 3 Specific Objectives

SO1. To strengthen organisational capacity and sustainability of targeted local CSOs that are working for the rights and development of ethnic minority groups

SO2. To promote transparency and accountability of existing government SSNPs

SO3. Increase the total number of vulnerable people with access to SSNPs from the government

The expected results of the Project are as follows

R1.1 Functional CSOs that are working for the rights of ethnic minority groups, exist with effective leadership in practice

R1.2 CSOs working for the rights of ethnic minority groups have increased their understanding of human rights and entitlements

R1.3 Effective networking and collaboration between relevant government and non-government organisations (GOs and NGOs) is established

R2.1 Inclusion of CSO representatives working for the rights of ethnic minority groups in local government committees

R2.2 Target communities satisfied with access to SSNPs information

R3.1The vulnerable are demanding rights and entitlements set out in SSNP policies

R3.2 Evidence of barriers to vulnerable peoples’ access to SSNPs are presented at national level and solutions sought in collaboration with key stakeholders

Overall Objective Indicators

O.1.1 Percentage of the target population with increased satisfaction regarding the delivery of SSNPs by the end of the Project

O.1.2 Number of policy, system, structure, practice or programmatic changes to improve access to SSNPs by the most vulnerable people, specifically including ethnic minority groups and women, contributed to by EVPRA by the end of the Project

Strategic Objective Indicators

SO1.1 Increased percentage of targeted local CSOs, that are exhibiting improved organisational and management capacity by the end of the Project

SO2.1 Percentage of vulnerable people (specifically including ethnic minority groups and women) with increased knowledge of target SSNPs, specifically eligibility criteria and/or grievance and redress mechanisms by the end of the Project

SO2.2 Number of new mechanisms (e.g. inclusion of CSO representatives, including ethnic minority groups and women, in local government committees, establishment of complaints and redress systems, transparency and accountability boards etc.) introduced by local government to enable vulnerable communities to voice concerns on the delivery of SSNPs by the end of the Project

SO3.1 Increased percentage of vulnerable people, including ethnic minority groups and women, who report accessing 1 or more of the 9 targeted SSNPs by the end of the Project

Results Indicators

R1.1.1 Percentage of targeted CSOs implementing new organisational leadership mechanisms in at least one of the areas being measured (e.g. new board standards, periodic/annual elections, inclusion of women, operational structures and systems etc) for effective CSO governance

R1.1.2 Percentage of CSOs with either women, or other vulnerable people in a leadership position by the end of year 2 of the project

R1.2.1 Increased access to knowledge and information about human rights and SSNP entitlements by the most vulnerable, including ethnic minority groups and women, by the end of the Project

R1.3.1 Increased effective engagement between GO and NGOs on issues which promote vulnerable peoples' access to SSNPs, specifically including ethnic minority groups and women

R2.1.1 Percentage increase in the number of CSO representatives included in local government committees, specifically including CSO representatives from ethnic minorities, women and other most vulnerable groups

R2.2.1 Increased proportion of people in the target communities with satisfactory access to SSNP information by the end of the Project

R3.1.1 Increased % of people (disaggregated by gender, ethnic minority and other vulnerable groups) in the target communities with access to SSNPs by the end of the Project

R3.2.1 Number of contributions to national level policy consultations with government to facilitate policy changes by the end of the Project

R3.2.2 Number of publications items and research pieces presented and disseminated at national level, to government and civil society, to advance access to SSNPs by the most vulnerable.

EVPRA has particularly focused on increasing access to the following 9 SSNPS

- Old Age Allowance - Ministry of Social Welfare

- Allowances for the financially insolvent disabled - Ministry of Social Welfare

- Allowance for the widowed, deserted and destitute women - Ministry of Social Welfare

- Maternity allowance program for poor lactating mothers - Ministry of Women and Children Affairs

- Vulnerable group development (VGD)- Ministry of Women and Children Affairs

- Vulnerable group feeding (VGF)– Ministry of Disaster Management and Relief

- Food for works (FFW)- Ministry of Disaster Management and Relief

- Secondary Education Stipend Project (SESP)- Ministry of Education

- Primary Education Stipend Project (PESP)- Ministry of Primary and Mass Education

- Key Objectives of the Project Impact Study

- To identify the impact of the Project interventions among the people of ethnic minorities and other vulnerable groups living in the Project areas

- To find out the changes happened in local government elected bodies in Union Parishad level specifically in the process and practice of delivering SSNPs

- To assess the changes in the Civil Society Organizations’ organizational management and sustainability

- To see how Grievance Redress Mechanism (GRM) is positively impacting on government service delivery process

- Study Target Audience

The targeted audience for the impact study will include; community members from the selected project areas specifically targeting ethnic minority and other disadvantaged communities. Local community leadership (District, Sub-district & Union Parishad) and SSNP committee, CSO organisations, Apex bodies, national level policy makers for SSNP project, line Ministries. Other specific targets include:

- World Vision United Kingdom

- World Vision Bangladesh

- EU delegation Bangladesh

- PUMDO

- Pollsiree

- Government Officials relevant to 9 SSNPs

- Study Type

The impact study will use case-based method which identifies different combinations of factors that are critical to a given result. The study intends to capture and communicate project impacts over targeted beneficiary, government structure and community based organizations for lessons learned and future programming.

- Proposes Methodology and Instruments

The impact study will use lesson learned workshop to identify potential impact cases, conduct in-depth interviews with beneficiary, CSO leaders, local government elected bodies, government officials and Project staffs as well.

- Desk review:

The assessment team will examine project documents, project data, and Implementation Programme agreements. The main purpose of this desk review is to build a good understanding of the available information on EVPRA programme within the wider context before conducting an in-depth study of this intervention. This review will aid in understanding the long term trends in terms of programme implementation and outputs since its inception, design of the sampling frame, defining the original scope of this programme, geographical coverage, and target populations; determining sampling methodology; and analyzing the risks posed by various contextual realities.

- Case studies:

The assessment team may pick 12 to 15 fact based case studies of beneficiaries who successfully changes their livelihood and their socio economic status in their society. The team may also want to select a few government staff who are direct beneficiaries of EVPRA project at both national and sub-national levels. The team will assess the impact on institutional and organizational capacities.

- Field visits:

The assessment team will study EVPRA activities in the Project working area, and will interview beneficiaries who agree to share information, survey target population, conduct focus groups randomly- selected beneficiaries who benefited from project.

- Interviews with stakeholders:

The assessment team should pay particular attention to the interviewing of stakeholders, namely staff, beneficiaries targeted and CSO members. The main purpose for employing this methodology is to understand the impact of EVPRA programme both from the perspective of those involved and how they have benefited or affected by this interventions of this programme.

For the study will be follow the footprint of baseline, CSO Capacity Assessment Report and Mid-Term Evaluation Report for quantitative and qualitative data collection.

- Duties and Responsibilities

Major tasks and responsibilities of the consultant/firm

- Form and manage his/her team in order to conduct all activities and processes required to achieve the quality and fulfil the requirements of the assignment as agreed with World Vision. All types of costs related to the study such as training of the interviewer, field movement, story writing, video capturing, video editing and mixing, presentation and other logistics associated with their food, accommodation and transportations will be borne by the consultant/firm;

- Remunerate all members of the team. The male-female ratio of data enumerators should be 50:50 and enumerators must be able to explain the questions using the local dialect of the Project area;

- Read all Project background documentation, Baseline Survey, CSOs Capacity Assessment and Midterm Evaluation report and all necessary Government documentation on SSNPs; e.g. National Social Security Strategy 2015; Office order of respective ministry or department on SSNP administration, Union Parishad Manual, etc). The consultant/firm must share with World Vision a list of all the documents and verify the current relevancy of the documents with the Government of Bangladesh;

- The consultant/firm will work closely with EVPRA team identify impact cases, issues to focus, understand challenges and potential way forward;

- Develop an assignment plan and schedule and seeking approval from World Vision.  The plan must include the schedule and outline of the assessment design and methodologies;

- Ensure compliance with child protection policies and informed consent of participants in the various steps of the assessment

- S/he will sign the behaviour protocol after confirming this assignment

Major tasks of the EVPRA Project and World Vision Bangladesh

The Monitoring and Evaluation Coordinator of the EVPRA Project will provide overall guidance and coordination support to the consultant/firm. World Vision, Pollisree and PUMDO will facilitate the field level activities, specific to the locations/Sub Districts each organisation is covering. If necessary, the Monitoring & Evaluation Coordinator will provide relevant and required contacts of the division or district level CSO, government department or EVPRA Project beneficiaries to the team. Specifically, World Vision will-

- Provide relevant Project documents to the selected consultant/firm

- Monitor the progress of the study process as per the agreed plan

- Review and feedback on the work plan, tools in applicable languages, draft reports within a reasonable timeframe

- Coordinate within World Vision departments, PUMDO, and Pollisree in order to support the implementation of assignment plan and schedule of the study

- EVPRA will ensure review of the stories and video clips through World Vision Communication team so that WV’s communication complaints are met

- Coordinate with all reviewers (EVPRA team, World Vision National and Regional Office and WVUK Office) to ensure that comments from different reviewers are consolidated and shared  with the consultant/firm in a timely manner and ensure that all comments are incorporated in the report

- Make payments based on agreed terms (the payment agreed terms i.e. 40% upon submission of 1st draft on time, 60% at final submission with agreed quality and on time)

- Key deliverables

At the start of the assignment, an inception report will be submitted including any changes of the technical proposal and final action plan for the study. However, following are the key deliverable that the consultant/firm should submit as outputs of the assignment.

- A study report (10-12 pages) with the support of most significant changes aligned with the theory of changes of the project in English and Bangla language with adequate action picture including appropriate caption necessary to visualize.

- 200 copy high quality colour printed study report. The study report specification is, five colour with all logos, front page will be 350 gm art card with mat printing, and inner page will be glossy offset 120 gm, binding: stich binding, cutting: Machine cut, all the inner page will be four colour with appropriate design standards

- e-Book of the success story as it is printed with appropriate file type playable using adobe flush player or any other appropriate applications

- 4-5 minutes video documentary  Bangla and English subtitlesEach version of video need to provided 25 copy in DVD along with raw footage in a separate hard-drive. The video footage resolutions at least: 1920 X 1080 pixels, during shooting vendor will use the separate microphone for capturing sound, and noise will be zero, if necessary use the graphics information as suggested by the project

- e-Book of success story and video documentary can be submitted with DVD with appropriate paperback. Vendor also will provide all the raw materials of the documentary with external hard drive

- Lesson Learned workshop report

- Duration and timeline

This impact study assignment should be completed (with the final product submitted) by no later than (31st October 2019) following the timeline below:

| Duration |  |
| --- | --- |
| Expected Start Date | 1st September 2019 |
| Estimated End Date | 31st October 2019 |
| Proposed Milestones to be included in Consultant Work Plan |  |
| Study design including final detailed work plan | 5th September 2019 |
| Draft story book and video clip | 15th October 2019 |
| Final story book and video clip | 31st October 2019 |

- Work plan

As part of the application process, the consultant/firm must submit a proposed work plan covering the following broad elements as a minimum, and indicating the proposed number of billable days against each task:

- Review of secondary sources

- Preparation of assessment framework, methodology, tools, final work plan

- Travel to/from Project areas

- Field work (visits, interviews, takes video shots, etc.)

- Preparation of first draft of stories and video documentary including presentation to EVPRA team, World Vision National and Northern Bangladesh Regional staff

- Assignment Location

The Impact Study will focus on the EVPRA Project sites namely Joypurhat Sadar and Panchbibi sub-districts in Joypurhat district, and Fulbari and Birampur sub-districts, Dinajpur Sadar, and in Dinajpur district, Rajshahi and Rangpur Division, Bangladesh.

- Competencies, Required Skills and Experience

WVB is seeking services from a consultant and/or firm with the following specifications:

Essential:

- Proven track record for delivering quality project impact studies for a similar / comparable organisation

- Experience and understanding of the Bangladesh working context, specifically working with Government at National and Local levels

- Lead Consultant MUST at least have a master’s degree in Mass Communication and Journalism or English or International Relations or relevant areas with a strong research and can demonstrate prior published/completed work

- Ability to be hands on for overseeing the impact study documentation process, including spending time at the field.

- Superior communication skills, specifically professional writing in English (sample writing may be needed)

Desirable:

- An understanding of the Bangladesh SSNP strategy

- Experience for working at the project areas, local cultures and customs

- Knowledge of Bangla and English language

The prospective consultants should show sample work done (impact story book, video documentary)

- To Apply

Applications (in English) must be sent by email to wvb_scm@wvi.org by16th August, at 23:59 Bangladesh time indicating ‘Proposal for “EVPRA Project Impact Study” in the subject line. It should contain the following elements:

- Consultant profile: To include organisational and legal details, core competencies of organisation/individual, relevant experiences in doing impact study, a statement of confirmation that the applicant is a registered company, with its own business bank account, and its own professional liability insurance. Attach curriculum vitae of each member of the team (maximum 3 pages each) clearly spelling out qualifications and experience.

- Detailed impact study outline for the assignment including an outline of methods (maximum 10 pages)

- Evidence of how the consultant/firm meet the Terms of References (ToR) requirements, setting out the conceptual framework on how the work will be undertaken. This part will be based on the information provided in the ToR.

- Detailed work plan and detailed timeframe, covering the items listed under the work plan section heading above (and including ethical considerations, internal monitoring etc.)

- Detailed Cost estimate in BDT (Bangladesh Taka), demonstrating value for money and including human resource mobilisation, travel expenses for interviewing, story writing and video recording, supplies, salary and remuneration (separating  core consultancy costs and daily rates of team members), one day workshop cost, cost of relevant tools, administrative costs and other costs in separate line items. Please specify if VAT or any local taxes have been included where applicable. All quotations submitted must be inclusive of all costs;

- Indication of availability (in relation to start and end dates).  The deadline is not negotiable.

- A statement regarding the legal, financial and professional independence of the consultant/firm from World Vision, PUMDO and POLLISREE, and a declaration of any real or perceived conflict of interest with any of the Project stakeholder.

- The selected consultant/firm will be required to undergo Child Protection screening, training and adhere to WV's Child Protection Policy.

- For consulting firm/agency/organisation a copy of VAT registration certificate and valid TIN are to be presented;

- One sample of previous relevant and related work to be attached.

- Management of Applications

World Vision will not be able to acknowledge or reply to all applications received. Applicants being considered will hear from World Vision within 10 calendar days after the closing date of this request for application either for additional information or for a face–to-face presentation.

Annexes

Annex A

Project Logframe

Annex B

Baseline Survey Report

Annex C

CSOs Capacity Assessment Report

Annex D

Midterm Evaluation Report

Annex E

Ethical principles for World Vision evaluation and research